## WIP
Mar-2025
# | Estimate Code | Contract Code | Customer | Contract Description | Type | Estimate Value | Budgeted GP | Budgeted GP % | Start Date | Completion Date | Completion % | Status | WIP | Overbill | Processing | Fabrication | Delivery | Completed
1 | E00008972 | J-965 | Hutchinson Builders | VSBA School, Greenvale Secondary- Bundle B | GSI | 1699999.9953 | -97671.0723 | -5.745% | 7 Aug 2020 | 8 Jul 2020 | 58.57% | Open | 257987.8769
2 | E00009967 | J-1085 | Hadi Hayek | 5 Brympton Avenue, Park Orchards | GSR | 112897.9205 | 56768.8502 | 50.28% | 26 Oct 2021 | 29 Apr 2021 | 59.66% | Open | 78291.3588
3 | E00010737 | J-1328 | Alchemy Construct | 8 Langs Road, Ascot Vale | GSI | 732123.9998 | 151830.7312 | 20.74% | 1 May 2022 | 19 Nov 2021 | 75.65% | Open |  | 127050.0312
4 | E00010958 | J-1373 | Empire Property Builders Pty Ltd | 50 Mainview Boulevard, Truganina- LOT D | GSI | 364899.9937 | 63636.2067 | 17.44% | 28 Jun 2022 | 18 Feb 2022 | 101.9% | Open | 147119.1835
5 |  | J-1407 | Corplex Pty Ltd | Maddox Road, Altona- Newport | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | Difference (GP Exc)
6 |  | J-1408 | Corplex Pty Ltd | Mountain Highway, Bayswater | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | Difference (GP Exc)
7 |  | J-1410 | Corplex Pty Ltd | Ozco Trucks, Colardo Drive | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | Difference (GP Exc)
8 |  | J-1411 | Corplex Pty Ltd | Palmers Road, Truganina | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | Difference (GP Exc)
9 |  | J-1413 | Corplex Pty Ltd | Servo | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | Difference (GP Exc)
10 |  | J-1414 | Corplex Pty Ltd | Galleghars Road, Epping- S. A | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | Difference (GP Exc)
11 | E00010748 | J-1431 | Vaughan Constructions Pty Ltd | 30-68 Taras Avenue, Altona North - Nascap | GSI | 4681514.9886 | 2106198.8784 | 44.99% | 19 May 2022 | 24 Nov 2021 | 100% | Open | 842122.8112
12 | E00010294 | J-1444 | Forte Group Pty Ltd | 240 High Street, Thomastown- Level 5 | GSI | 178280.0002 | 24000.0989 | 13.46% | 26 Jan 2022 | 27 Jul 2021 | 74.25% | Open | 15656.3435
13 | E00010453 | J-1460 | Tilt Construct Pty Ltd | Lot 6 & 7, 36-40 Taryn Drive, Epping | GSI | 500000.001 | 122646.9203 | 24.53% | 7 Mar 2022 | 6 Sep 2021 | 100% | Open | 67923.5488
14 | E00011339 | J-1544 | Maddox 27 to 28 Pty Ltd | 42-44 Robbins Circuit, Williamstown | GSI | 295000.0006 | 62968.5596 | 21.35% | 4 Oct 2022 | 8 Jun 2022 | 0.03717% | Open | 86.25
15 | E00011809 | J-1609 | Zonzo | 997 Healesville- Yarra Glen Road, Yarra Glen | GSI | 88000.0005 | 22532.7363 | 25.61% | 9 Feb 2023 | 19 Oct 2022 | 0% | Open |  | 17600
16 | E00011909 | J-1613 | Grow Constructions | Steel | GSI | 15000 | 3000 | 20% | 0 | On-Going | 69.17% | Open | 8300
17 | E00012152 | J-1700 | Kiel & Co | Lot 425, 501-502 (18-22) Castle Drive, Torquay | GSI | 324999.9982 | 79103.2166 | 24.34% | 1 May 2023 | 16 Feb 2023 | 100% | Open | 0.0020245
18 | E00011537 | J-1718 | Monde Construction & Refrigeration PtyLtd | 572 Stockinbingal Road, Coottamudra- Link Building | GSI | 589600.0049 | 138359.6238 | 23.47% | 16 Nov 2022 | 5 Aug 2022 | 15.42% | Open | 17460.3542
19 | E00012570 | J-1749 | Geelong | Geelong | GSM | 0 | 0 | #DIV/0! | 0 | 14 Jun 2023 | #DIV/0! | Open | #DIV/0! | #DIV/0!
20 | E00010535 | J-1751 | Design Electrical Pty Ltd | 3 Dyson Court, Breakwater- Mezzanine @ Factory 8 | GSI | 24999.9999 | 5146.3048 | 20.59% | 23 Mar 2022 | 29 Sep 2021 | 0% | Open
21 | E00012606 | J-1763 | Malibu Properties | 25 Carrick Drive, Tullamarine- Mezzanine | GSI | 30000.0002 | 6710.4468 | 22.37% | 16 Aug 2023 | 20 Jun 2023 | 100% | Open |  | 0.0064126
22 |  | J-1791 | John Brincat JB Rigging | 18 Hampden Road, Cranbourne West | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | #DIV/0! | #DIV/0!
23 | E00014853 | J-1800 | Corplex Pty Ltd | Verandah Beams (Dominic Cullia) | GSI | 0 | 0 | #DIV/0! | 0 | 16 Dec 2024 | #DIV/0! | Open | #DIV/0! | #DIV/0!
24 | E00012492 | J-1804 | Bellafia Homes | Lot 77 Literary Way (15 Robbins Court) Williamspoi | GSI | 157999.9997 | 23119.926 | 14.63% | 18 Jul 2023 | 22 May 2023 | 100% | Open | 9296.4804
25 | E00012771 | J-1829 | The Ci Group | 210-216 Jumping Creek Road, Wonga Park | GSR | 136900.0052 | 30610.6569 | 22.36% | 18 Sep 2023 | 2 Aug 2023 | 60.96% | Open |  | 17841.8764
26 | E00012900 | J-1847 | Albert Infelice | 13 Yarra Braes Road Eltham | GSR | 54199.9994 | 12821.7556 | 23.66% | 1 Dec 2023 | On-Going | 85.57% | Open | 2303.9736
27 | E00012952 | J-1863 | Texco Construction Pty Ltd | 15-33 Macedon Way, Melbourne Airport- WH 1 & 4 | GSI | 4824999.9902 | 980585.1831 | 20.32% | 7 Nov 2023 | 19 Sep 2023 | 97.26% | Open |  | 174382.0606
28 | E00012050 | J-1864 | C3 Constructions Group | 17-31 Franklyn Street, Huntingdale | GSI | 2109993.4874 | 320046.292 | 15.17% | 13 Apr 2023 | 25 Jan 2023 | 77.18% | Open |  | 23647.1785
29 |  | J-1873 | Shark Screens Pty Ltd | Brackets | GSM | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | #DIV/0! | #DIV/0!
30 | E00013061 | J-1877 | Chick Constructions Pty Ltd | AGPC CCTV Temporary Forklift Sleeves | GSI | 0 | 0 | #DIV/0! | 0 | 27 Oct 2023 | #DIV/0! | Open | #DIV/0! | #DIV/0!
31 | E00012982 | J-1898 | Texco Construction Pty Ltd | 285 Palmers Road, Truganina | GSI | 1615599.9965 | 285146.3617 | 17.65% | 16 Nov 2023 | 28 Sep 2023 | 0% | Open
32 | E00012997 | J-1900 | Qanstruct (Aust) Pty Ltd | 131-149 Somerton Road, Campbellfield- WH 1.1-1.3 & | GSI | 8409011.2355 | 1707266.6904 | 20.3% | 19 Nov 2023 | 10 Oct 2023 | 100.2% | Open | 452987.7353
33 | E00013162 | J-1905 | Erilyan | Roof Louvre Works | GSI | 0 | 0 | #DIV/0! | 0 | 28 Nov 2023 | #DIV/0! | Open | Difference (GP Exc)
34 | E00012841 | J-1911 | Mainbrace Constructions (Victoria) | 144 Northcorp Boulevard, Broadmeadows | GSI | 2354334.9989 | 507149 | 21.54% | 0 | 16 Aug 2023 | 52.2% | Open | 277970.4553
35 | E00013252 | J-1915 | Valiant Framing | 43 Danaher Drive, South Morang | GSI | 98102.1655 | 0 | 0% | 0 | 16 Jan 2024 | #DIV/0! | Open | #DIV/0! | #DIV/0!
36 | E00013164 | J-1944 | Qanstruct (Aust) Pty Ltd | Lot 3B Oakdale West Estate, Horsley Park - Precinc | GSI | 8535785.149 | 1497706.3863 | 17.55% | 31 Jan 2024 | 28 Nov 2023 | 101% | Open | 290030.9627
37 | E00012113 | J-1949 | C3 Constructions Group | 1076-1078 Centre Road, Oakleigh South | GSI | 1156475.0001 | 164700.9885 | 14.24% | 21 Apr 2023 | 9 Feb 2023 | 75.99% | Open |  | 283586.3113
38 | E00013426 | J-1951 | FORTEK | 365-455 Melbourne Rd Norlane - Factory19 - Crane | GSM | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | #DIV/0! | #DIV/0!
39 | E00012595 | J-1960 | Leone Constructions Pty Ltd | 1 & 2 Montrose Court, Toorak | GSR | 214292.0198 | 26527.1664 | 12.38% | 14 Aug 2023 | 19 Jun 2023 | 72.26% | Open |  | 21992.7916
40 | E00013182 | J-1962 | FDC Construction & Fitout (Vic) Pty Ltd | Moorebank Intermodal Precinct South Warehouse | GSI - Genis Steel (NSW) Pty Ltd | 7837000 | -100000 | -1.276% | 0 | 5 Dec 2023 | 7055% | Open |  | 7654999.59
41 | E00014854 | J-1968 | GSR Cranes | Cranes | GSI | 0 | 0 | #DIV/0! | 0 | 16 Dec 2024 | #DIV/0! | Open | #DIV/0! | #DIV/0!
42 | E00012992 | J-1970 | Corplex Pty Ltd | 144-150 Hall Street, Spotswood | GSI | 313500.0033 | 30532.1684 | 9.739% | 17 Nov 2023 | 9 Oct 2023 | 100% | Open |  | 0.0058457
43 | E00012694 | J-1978 | Juscot Construction & Management | Lot 60, 188 Maddox Road, Williamstown North | GSI | 507070.0011 | 80968.6071 | 15.97% | 31 Aug 2023 | 12 Jul 2023 | 62.57% | Open |  | 12138.4973
44 |  | J-1981 | Qanstruct (Aust) Pty Ltd | 85-87 High Street, South Kew | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | #DIV/0! | #DIV/0!
45 | E00012972 | J-1988 | Texco Construction Pty Ltd | 427-451 Somerville Road, Tottenham- Stage 3 Freeze | GSI | 4677999.9999 | 813501.3396 | 17.39% | 12 Nov 2023 | 25 Sep 2023 | 97.62% | Open | 106624.3731
46 | E00013601 | J-1989 | Mannfield Group | 1161 High Street Road, Wantirna South - Extra | GSR | 22500.0022 | 4838.7931 | 21.51% | 0 | On-Going | 4.328% | Open | 764.37
47 | E00008172 | J-1999 | Able Constructions & Management Pty Ltd | 35 Decco Drive, Campbellfield | GSI | 570000.0005 | 100707.2116 | 17.67% | 30 Mar 2020 | 28 Oct 2019 | 16.86% | Open | 79119.9491
48 | E00013336 | J-2012 | Michael Hill | 220 Sunday Creek Road, Broadford | GSI | 14999.9996 | 3844.1011 | 25.63% | 0 | 1 Feb 2024 | 32.38% | Open | 3611.9591
49 | E00013356 | J-2015 | Forte Group Pty Ltd | 1 Zenith Drive, 2-4 Pinnicle Drive, Warrenheip | GSI | 485000.002 | 83532.3649 | 17.22% | 15 Mar 2024 | 6 Feb 2024 | 35.17% | Open | 11321.2477
50 | E00013258 | J-2019 | Melbourne Industrial Builders | 754 Princess Highway, Laverton North- Mezzanine | GSI | 110000.0004 | 19340.6827 | 17.58% | 21 Feb 2024 | 16 Jan 2024 | 0% | Open
51 | E00012426 | J-2024 | Lowther Builders Pty Ltd | 22 Avoca Street South Yarra | GSR | 72000.0079 | 13579.7014 | 18.86% | 1 Aug 2023 | On-Going | 87.48% | Open |  | 3015.7896
52 | E9991 | J-2026 | Genis Steel Internal | RESIDENTIAL OVERHEAD | GSR | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | Difference (GP Exc)
53 |  | J-2033 | Corplex Pty Ltd | Kingspan | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | #DIV/0! | #DIV/0!
54 | E00013808 | J-2039 | Chick Constructions Pty Ltd | Sorbent | GSM | 6300 | 1300 | 20.63% | 0 | 15 May 2024 | 279.3% | Open | 1427.1266
55 | E00013756 | J-2047 | Mitah | Lot 3, 4 Ponting Street, Williamstown | GSI | 663699.9946 | 144579.67 | 21.78% | 19 Jul 2024 | 13 May 2024 | 100% | Open | 0.010529
56 |  | J-2049 | Valiant Framing | Millers Road, Altona North | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | Difference (GP Exc)
57 | E00013278 | J-2053 | C3 Constructions Group | 1 The Esplanade, North Shore Geelong- D & C | GSI | 1807875.7788 | 346352.8313 | 19.16% | 26 Feb 2024 | 19 Jan 2024 | 88.6% | Open |  | 184909.853
58 | E00013185 | J-2055 | Protilt Constructions | 39 Launceston Street, Williamstown | GSI | 394500.0005 | 73822.2349 | 18.71% | 6 Feb 2024 | 5 Dec 2023 | 100% | Open | 3657.9244
59 | E00012647 | J-2061 | Qanstruct (Aust) Pty Ltd | Lot 2, 1005 Boundary Road, Tarneit- ALDI DC | GSI | 46930604.5637 | 7463194.0009 | 15.9% | 21 Aug 2023 | 29 Jun 2023 | 12.34% | Open |  | 1837327.2022
60 | E00013681 | J-2062 | Impact Designer Homes | 492 Fullarton Road, Airport West | GSI | 479900.0071 | 140195.5793 | 29.21% | 14 Jun 2024 | 19 Apr 2024 | 100% | Open | 0.00047212
61 | E00013175 | J-2064 | CIP Constructions Group | Hobson Engineering, Perth WA | GSI - Genis Steel (NSW) Pty Ltd | 1584900 | 0 | 0% | 0 | 1 Dec 2023 | #DIV/0! | Open | #DIV/0! | #DIV/0!
62 | E00013951 | J-2066 | GSR Steel Allocation | 45-65 O'Herns Road Somerton | GSR | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | #DIV/0! | #DIV/0!
63 | E00012344 | J-2072 | Gama Homes Pty Ltd | 10 Eureka Street, Richmond | GSR | 32500.0006 | 7642.322 | 23.51% | 19 Jun 2023 | 13 Apr 2023 | 16.68% | Open | 4147.5
64 | E00012120 | J-2082 | Mitah | 202 Osborne Street, Williamstown | GSR | 49000.0015 | 10761.9268 | 21.96% | 24 Apr 2023 | 10 Feb 2023 | 57.48% | Open |  | 10112.6146
65 | E00013838 | J-2084 | Group Technologies Australasia | 156-160 Memorial Drive, Plenty | GSR | 29000.0001 | 6423.335 | 22.15% | 1 Aug 2024 | 21 May 2024 | 18.56% | Open |  | 417.893
66 | E00010322 | J-2093 | VP Homes | 43 Ferdinand Avenue, North Balwyn | GSR | 97999.9994 | 20620.721 | 21.04% | 2 Feb 2022 | 3 Aug 2021 | 75.88% | Open |  | 23633.5917
67 | E00013882 | J-2094 | Protilt Constructions | 153-163 Fitzgerald Road, Laverton North | GSI | 116500.0002 | 35073.5205 | 30.11% | 13 Aug 2024 | 31 May 2024 | 100% | Open |  | 0.0023911
68 | E00012660 | J-2098 | C3 Constructions Group | 89 Lewis Road, Wantirna South | GSI | 1022399.9874 | 155555.2024 | 15.21% | 17 Nov 2023 | 3 Jul 2023 | 91.55% | Open | 261875.2
69 | E00012033 | J-2099 | Khuan M Kon | 3 Gold Court Deer Park, Melbourne- Buddha Hall | GSI | 819999.9933 | 142106.9951 | 17.33% | 3 Apr 2023 | 20 Jan 2023 | 80% | Open |  | 164035.9148
70 | E00013992 | J-2100 | Impact Designer Homes | Lot 8, 60 Logistics Street, Keilor Park | GSI | 228999.9993 | 35421.5853 | 15.47% | 0 | 25 Jun 2024 | 59.38% | Open |  | 1423.792
71 | E00013993 | J-2101 | Impact Designer Homes | Lot 9, 66 Logistics Street, Keilor Park | GSI | 228999.9993 | 35421.5853 | 15.47% | 0 | 25 Jun 2024 | 43.31% | Open | 83839.8127
72 | E9991 | J-2103 | Tohme Hayek | 122 Berringa Rd Park Orchards | GSI | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | #DIV/0! | #DIV/0!
73 | E9991 | J-2104 | Genis Steel | Caretakers Building | GSI | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | #DIV/0! | #DIV/0!
74 | E00014104 | J-2109 | Maice Constructions Pty Ltd | 110 Yale Drive, Epping | GSI | 395000.0011 | 68449.7319 | 17.33% | 30 Sep 2024 | 17 Jul 2024 | 5.052% | Open |  | 126045.6793
75 | E00014162 | J-2110 | Leomilla | 5 Thelma Avenue Essendon North | GSR | 45000.0003 | 8609.1219 | 19.13% | 1 Oct 2024 | On-Going | 56.6% | Open | 4424.1414
76 | E00013053 | J-2118 | Protilt Constructions | 50 Bakers Road, Coburg | GSI | 886699.9953 | 155472.1791 | 17.53% | 30 Nov 2023 | 26 Oct 2023 | 94.54% | Open |  | 4103.6575
77 | E00013081 | J-2121 | Richard Crookes Constructions | 124 Hollinsworth Road, Marsden Park, NSW- Newcold | GSI - Genis Steel (NSW) Pty Ltd | 4495000.0112 | 0 | 0% | 7 Dec 2023 | 6 Nov 2023 | #DIV/0! | Open | #DIV/0! | #DIV/0!
78 | E00013805 | J-2123 | North | Baiada Freezer Store, Beresfield | GSI | 1869900 | 315857 | 16.89% | 0 | 15 May 2024 | 67.43% | Open | 248030.4176
79 | E00013366 | J-2124 | C3 Constructions Group | 27 Piper Road, East Bendigo | GSI | 389479.9975 | 66717.4809 | 17.13% | 1 Apr 2024 | 12 Feb 2024 | 82.1% | Open | 17288.7559
80 | E00013906 | J-2130 | Forte Group Pty Ltd | 75-105 Bolinda Road, Campbellfield- Stage 2 | GSI | 1798000.0075 | 276375.3154 | 15.37% | 15 Aug 2024 | 6 Jun 2024 | 16.12% | Open | 247186.5291
81 | E00013073 | J-2131 | C3 Constructions Group | 248-252 Wickham Road, Highett | GSI | 438680.0003 | 73683.7277 | 16.8% | 4 Dec 2023 | 1 Nov 2023 | 61.66% | Open | 26575.0365
82 | E00013364 | J-2133 | Davies Henderson Pty Ltd | 10-12 Irving Road, Toorak | GSR | 63000.0003 | 10540.2161 | 16.73% | 1 Apr 2024 | 8 Feb 2024 | 43.92% | Open | 6388.1867
83 | E00014205 | J-2134 | Cota Group | Rangebank Drive, Cranbourne West- Terra Mater | GSI | 624645.0004 | 74661.0176 | 11.95% | 8 Nov 2024 | 5 Aug 2024 | 99.95% | Open | 29822.776
84 | E00012609 | J-2136 | Flowrite Construction Developments | 7 Logic Court, Truganina | GSI | 379999.9954 | 106532.3234 | 28.03% | 18 Aug 2023 | 21 Jun 2023 | 100% | Open |  | 0.0054092
85 | E00014317 | J-2138 | Richard Crookes Constructions | Lot 5A & B Bankstown Airport, South West Precinct, | GSI | 2845999.9876 | 288987.5044 | 10.15% | 0 | 2 Sep 2024 | 89.44% | Open | 445937.6815
86 | E00012913 | J-2139 | Richard Crookes Constructions | Light Horse Lot 3, 165 Wallgrove Rd & 475 Ferrers | GSI - Genis Steel (NSW) Pty Ltd | 2655000.0002 | 0 | 0% | 29 Oct 2023 | 8 Sep 2023 | #DIV/0! | Open | #DIV/0! | #DIV/0!
87 | E00014117 | J-2140 | Ark Industrial Pty Ltd | 365-466 Melbourne Road, Geelong- Site A & Site B F | GSI | 1094539.0052 | 159418.7645 | 14.56% | 27 Sep 2024 | 18 Jul 2024 | 105.2% | Open | 196260.2883
88 | E00013961 | J-2142 | Maxim-Built | 49 Wangara Road, 7 Melaleuca Drive, Cheltenham | GSI | 1505999.9968 | 261374.1963 | 17.36% | 28 Aug 2024 | 19 Jun 2024 | 0% | Open
89 | E00013803 | J-2143 | Protilt Constructions | 110-116 Greens Road, Dandenong South | GSI | 1151699.9947 | 179746.6751 | 15.61% | 26 Jul 2024 | 14 May 2024 | 64.74% | Open | 206358.9844
90 | E00013887 | J-2145 | DTC Family Builders | 45 Wallan Whittlesea Road, Wallan- Stage 1 | GSI | 660499.9978 | 113472.3606 | 17.18% | 16 Aug 2024 | 3 Jun 2024 | 1.719% | Open |  | 121242.8719
91 | E00013130 | J-2146 | C3 Constructions Group | 30 Dairy Drive, Coburg North- Stage 1 | GSI | 1025535.0797 | 0 | 0% | 22 Jan 2024 | 17 Nov 2023 | #DIV/0! | Open | #DIV/0! | #DIV/0!
92 | E00013612 | J-2147 | Flowrite Construction Developments | 1-3 Salisbury Street, Sunshine North | GSI | 102200.0002 | 17718.6744 | 17.34% | 27 May 2024 | 5 Apr 2024 | 0.1012% | Open | 85.5
93 | E00014387 | J-2148 | C3 Constructions Group | 30 Dairy Drive, Coburg North- Stgae 2 | GSI | 485000.0009 | 0 | 0% | 0 | 11 Sep 2024 | #DIV/0! | Open | #DIV/0! | #DIV/0!
94 | E00013389 | J-2149 | Flowrite Construction Developments | Lot 18, 11 Sant Court, Ravenhall | GSI | 94999.9991 | 13979.2329 | 14.71% | 4 Apr 2024 | 15 Feb 2024 | 90.14% | Open |  | 3930.3776
95 | E00014241 | J-2150 | Flowrite Construction Developments | Lot 16, 15 Sant Court, Ravenhall | GSI | 92199.9991 | 13283.4977 | 14.41% | 30 Oct 2024 | 13 Aug 2024 | 96.08% | Open | 65158.9421
96 | E00014242 | J-2151 | Flowrite Construction Developments | Lot 15, 17 Sant Court, Ravenhall | GSI | 102500.0014 | 15190.6087 | 14.82% | 30 Oct 2024 | 13 Aug 2024 | 88.92% | Open | 69190.5258
97 | E00014244 | J-2152 | Flowrite Construction Developments | Lot 7 Sant Court, Ravenhall | GSI | 88300.0003 | 14053.2169 | 15.92% | 30 Oct 2024 | 13 Aug 2024 | 30.63% | Open | 22738.5091
98 | E00014243 | J-2153 | Flowrite Construction Developments | Lot 8, 12 Sant Court, Ravenhall | GSI | 88500.0002 | 14570.7704 | 16.46% | 30 Oct 2024 | 13 Aug 2024 | 53.26% | Open | 39375.1273
99 | E00013296 | J-2155 | Texco Construction Pty Ltd | 4 Westgate Drive, Laverton North | GSI | 339999.9989 | 51499.7784 | 15.15% | 4 Mar 2024 | 23 Jan 2024 | 39.93% | Open | 115198.7173
100 | E00014240 | J-2157 | Flowrite Construction Developments | Lot 19, 9 Sant Court, Ravenhall | GSI | 92199.9992 | 15508.7802 | 16.82% | 30 Oct 2024 | 13 Aug 2024 | 86.73% | Open |  | 2031.7654
101 | E00013537 | J-2158 | Quadrant Building | 650 Hume Highway, Craigieburn- The Base Precinct 3 | GSI | 370000.0007 | 67552.4528 | 18.26% | 7 May 2024 | 18 Mar 2024 | 100.9% | Open | 19358.1944
102 | E00013933 | J-2159 | Mainbrace Constructions (NSW) | FPI- Bisley Workwear Australia- Lot 8, The Yards | GSI | 1700000.008 | 85338.8498 | 5.02% | 0 | 13 Jun 2024 | 97.38% | Open | 55980.8808
103 | E00014092 | J-2160 | LSR Construction Group Pty Ltd | 469 Somerville Road, Brooklyn | GSI | 720000 | 113036.6881 | 15.7% | 24 Sep 2024 | 15 Jul 2024 | 102.1% | Open | 78254.8255
104 | E00013163 | J-2161 | Able Constructions & Management Pty Ltd | 264-270 Craigieburn Road, Craigieburn | GSI | 557700.0005 | 95994.0773 | 17.21% | 30 Jan 2024 | 28 Nov 2023 | 55.05% | Open |  | 52799.4881
105 | E00014402 | J-2162 | Comfy Pod Pty Ltd | Kitchen | GSM | 10100 | 1500 | 14.85% | 0 | 16 Sep 2024 | 0% | Open
106 | E00013907 | J-2163 | Impact Designer Homes | Lot 25 Reddish Close, Epping | GSI | 223400.0004 | 40714.7374 | 18.23% | 15 Aug 2024 | 5 Jun 2024 | 83.55% | Open |  | 36760.272
107 | E9991 | J-3500 | EPX Build | J-3500 - 76 Beach Rd, Sandringham | GSI | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | #DIV/0! | #DIV/0!
108 | E00014299 | J-2165 | Corplex Pty Ltd | 441-459 Kororoit Creek Road, Altona- WH A | GSI | 1259999.9963 | 156883.9392 | 12.45% | 18 Nov 2024 | 26 Aug 2024 | 98.59% | Open | 173910.8579
109 | E00014152 | J-2166 | Leomilla | 56 McNamara Street Preston | GSR | 18000.0041 | 2068.5849 | 11.49% | 1 Sep 2024 | On-Going | 83.83% | Open | 13355.2364
110 | E9991 | J-2168 | Genis Steel Somerton Factory 2 | Genis Steel Somerton Factory 2 | GSM | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | #DIV/0! | #DIV/0!
111 | E00014478 | J-2170 | ATG Projects | MACS 20 X 5 Mods | GSM | 770000 | -117902.2 | -15.31% | 0 | 1 Oct 2024 | 100% | Open | 50886.9896
112 | E00012665 | J-2171 | C3 Constructions Group | 121-125 Northern Road, Heidelberg West | GSI | 813670.1572 | 136123.9993 | 16.73% | 24 Aug 2023 | 4 Jul 2023 | 7.545% | Open | 51598.0864
113 | E00014167 | J-2173 | FDC Construction & Fitout (Vic) Pty Ltd | McGrath, 2 Helles Avenue, Moorebank NSW | GSI - Genis Steel (NSW) Pty Ltd | 1203000 | 0 | 0% | 0 | 30 Jul 2024 | #DIV/0! | Open | #DIV/0! | #DIV/0!
114 | E00014217 | J-2175 | Atwal Investment Group | Lot 747 Trafalgar Road, Epping | GSI | 249999.9987 | 37713.275 | 15.09% | 25 Oct 2024 | 8 Aug 2024 | 65.59% | Open |  | 86023.2873
115 | E00013890 | J-2176 | Built Environs (VIC) | Pegasus Drive, Weir Views- Toolern Waters School | GSI | 3555514.9998 | 0 | 0% | 0 | 5 Jun 2024 | #DIV/0! | Open | #DIV/0! | #DIV/0!
116 | E00012938 | J-2179 | Mercs Projects & Developments Pty Ltd | 37 Golf Road, Coburg North | GSR | 21000.0001 | 4160.1051 | 19.81% | 3 Nov 2023 | 14 Sep 2023 | 16.91% | Open | 2846.7864
117 | E00013830 | J-2181 | Sage Group | Garage and Farm Shed | GSI | 9150.0299 | 0.00015 | 1.639e-06% | 0 | 21 May 2024 | 119.7% | Open | 10953.5191
118 | E00013810 | J-2184 | Hutchinson Builders | 28-32 Carrick Drive, Tullamarine- NS Tullamarine | GSI | 1450000.0005 | 303218.748 | 20.91% | 25 Jul 2024 | 15 May 2024 | 91.12% | Open | 350779.9689
119 | E00013927 | J-2190 | Texco Construction Pty Ltd | 813-913 Wallgrove Road, Eastern Creek- Chanel Lot | GSI | 1889179.998 | 311235.1253 | 16.47% | 21 Aug 2024 | 13 Jun 2024 | 27.52% | Open | 434311.5182
120 | E00014346 | J-2191 | A Grade Concrete Pty Ltd | Lot 65 Forefront Drive, Mickleham- Factory 1 | GSI | 351100.0005 | 0 | 0% | 2 Dec 2024 | 4 Sep 2024 | #DIV/0! | Open | Difference (GP Exc)
121 | E00014347 | J-2192 | A Grade Concrete Pty Ltd | Lot 65 Forefront Drive, Mickleham- Factory 2 | GSI | 274800.0002 | 0 | 0% | 2 Dec 2024 | 4 Sep 2024 | #DIV/0! | Open | Difference (GP Exc)
122 | E00014426 | J-2193 | A Grade Concrete Pty Ltd | 35 Prime Street, Thomastown | GSI | 61600.0003 | 9955.6476 | 16.16% | 17 Jan 2025 | 19 Sep 2024 | 0% | Open
123 | E00014396 | J-2194 | Lane Con Building | 6 Hardinge Street, Beaumaris | GSR | 27000.0005 | 5430.3089 | 20.11% | 13 Jan 2025 | 12 Sep 2024 | 52.79% | Open |  | 2747.8424
124 | E00013843 | J-2195 | Marven Construction | 17 Martin Street Brighton | GSR | 28800.0004 | 6434.3351 | 22.34% | 1 Aug 2024 | On-Going | 55.58% | Open | 12430.3773
125 | E00014427 | J-2196 | Corplex Pty Ltd | 144-150 Hall Street, Spotwood- Building A, B & C | GSI | 345000.0008 | 59806.276 | 17.34% | 20 Jan 2025 | 20 Sep 2024 | 42.12% | Open | 70696.5284
126 |  | J-2197 | AusPro Steel | Lot 41, 9 Interchange Drive, Mickleham | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | #DIV/0! | #DIV/0!
127 | E00014293 | J-2199 | Squared | Beon Energy-BUW Substation | GSI | 324599.9988 | 0 | 0% | 18 Nov 2024 | 21 Aug 2024 | 132.5% | Open |  | 73005.6511
128 | E00013652 | J-2200 | LSR Construction Group Pty Ltd | 32-36 Peet Street, Pakenham | GSI | 1500000.0118 | 260609.2866 | 17.37% | 11 Jun 2024 | 12 Apr 2024 | 27.57% | Open | 341751.0421
129 | E00014349 | J-2201 | Flowrite Construction Developments | Lot 69, 31 East Derrimut Crescent, Derrimut | GSI | 220000.0004 | 0 | 0% | 3 Dec 2024 | 5 Sep 2024 | #DIV/0! | Open | #DIV/0! | #DIV/0!
130 | E00014623 | J-2202 | Corplex Pty Ltd | 441-459 Kororoit Creek Road, Altona- WH B | GSI | 1270000.0037 | 175337.181 | 13.81% | 18 Feb 2025 | On-Going | 82.72% | Open | 289883.7563
131 | E00014200 | J-2203 | Balo Built | 650 Hume Highway, Craigieburn- The Base Precinct 2 | GSI | 1930719.9957 | 270844.9346 | 14.03% | 22 Oct 2024 | 3 Aug 2024 | 53.01% | Open | 456069.7488
132 | E00013692 | J-2204 | Quadrant Building | 17 Elmhurst Avenue, Aintree- Woodlea Swim School | GSI | 233699.9991 | 40420.8842 | 17.3% | 0 | 22 Apr 2024 | 10.34% | Open |  | 9533.9873
133 | E9991 | J-2205 | Genis Steel Victoria | Form Work | GSI | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | #DIV/0! | #DIV/0!
134 | E00013772 | J-2206 | LSR Construction Group Pty Ltd | 9-11 Maria Street, Laverton North | GSI | 434000.0009 | 79880.0504 | 18.41% | 17 Jul 2024 | 7 May 2024 | 48.08% | Open | 2813.7259
135 | E00013204 | J-2209 | Panache Developments | 39 Maling Road, Canterbury | GSR | 126000 | 34153.2662 | 27.11% | 9 Feb 2024 | 12 Dec 2023 | 2.787% | Open |  | 21688.0624
136 | E00014446 | J-2210 | Number 34 | 551, 553A & 553B Geelong Road, Brooklyn | GSR | 128400.0002 | 21676.6211 | 16.88% | 16 Jan 2025 | 24 Sep 2024 | 1.658% | Open | 1770
137 | E00014733 | J-2215 | Nexus Communities | Sommers Nexus | GSM | 25050 | 3600 | 14.37% | 0 | 21 Nov 2024 | 76.75% | Open |  | 2603.8622
138 | E00014505 | J-2216 | Corplex Pty Ltd | Lot 2, 100 Missens Road, Cranbourne West | GSI | 2099999.9958 | 261472.0597 | 12.45% | 29 Jan 2025 | 8 Oct 2024 | 33.61% | Open | 322358.2134
139 | E00014315 | J-2217 | Rockford Building Group | 85 New Street Brighton | GSR | 34000.0007 | 7624.4343 | 22.42% | 1 Nov 2024 | On-Going | 50.14% | Open | 13225.6064
140 | E00014408 | J-2218 | Kiel & Co | Lot 507-509, 9-13 Supertubes Drive, Torquay | GSI | 347000.0004 | 64094.2925 | 18.47% | 15 Jan 2025 | 16 Sep 2024 | 38.29% | Open | 108332.6577
141 | E00014551 | J-2219 | Pristine Building Services Pty Ltd | 2 Joseph Street, Bundoora | GSR | 23999.9997 | 4762.5757 | 19.84% | 29 Jan 2025 | 16 Oct 2024 | 94.61% | Open | 14352.8233
142 | E00014750 | J-2220 | Asta Developments (Aust) P/L | Lot 9, 19 Stanley Drive, Somerton | GSI | 102000.0014 | 17736.6604 | 17.39% | 0 | 25 Nov 2024 | 0.04747% | Open | 40
143 | E00014758.1 | J-2221 | Arkit | 66 Walter St Seddon | GSR | 52000.0004 | 10066.5366 | 19.36% | 0 | On-Going | 97.69% | Open |  | 1203.5081
144 | E00014199 | J-2222 | Leone Constructions Pty Ltd | 8 Miller Street, Brighton | GSR | 20850.0006 | 4278.3049 | 20.52% | 21 Oct 2024 | 2 Aug 2024 | 11.2% | Open | 1856.4727
145 | E00014643 | J-2224 | Gravcon | 61 Slater Parade, Keior East | GSI | 160399.999 | 27768.3782 | 17.31% | 20 Feb 2025 | 6 Nov 2024 | 79.44% | Open | 34082.3924
146 | E00014677 | J-2227 | Davies Henderson Pty Ltd | 29-31 St Georges Road Toorak | GSR | 28999.9998 | 6836.8239 | 23.58% | 1 Feb 2025 | On-Going | 67.77% | Open | 15019.3755
147 | E9991 | J-2228 | Genis Steel | Factory 19, 365-455 Melbourne Rd, Norlane | GSM | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | #DIV/0! | #DIV/0!
148 | E00014178 | J-2229 | Ducon Building Solutions | Eramosa Road E, Somerville- Somerville PS Cola | GSI | 279999.9956 | 47845.1128 | 17.09% | 16 Oct 2024 | 26 Jul 2024 | 34.55% | Open | 80219.0036
149 | E00014163 | J-2230 | Ducon Building Solutions | Somers & Somerville Primary School Cola | GSI | 224999.9987 | 38902.3935 | 17.29% | 16 Oct 2024 | 26 Jul 2024 | 65.33% | Open | 121572.6627
150 | E00014839 | J-2232 | PreBuilt | Point Cook SL 1.1 | GSM | 341400 | 114334.33 | 33.49% | 0 | 11 Dec 2024 | 100% | Open |  | 26099.9973
151 | E00014842 | J-2235 | PreBuilt | Point Cook SL 2.2 | GSM | 341400 | 144973.93 | 42.46% | 0 | 11 Dec 2024 | 100% | Open |  | 27530.0071
152 | E00014844 | J-2236 | Arkit | Neometro Display Suit | GSM | 75100 | 11000 | 14.65% | 0 | 12 Dec 2024 | 75.44% | Open |  | 14341.7897
153 |  | J-2237 | Remington | Storage Racks | GSM | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | #DIV/0! | #DIV/0!
154 | E00014823 | J-2238 | Corplex Pty Ltd | 20 Wright Road, Keilor Park | GSI | 6100 | 1279 | 20.97% | 0 | 9 Dec 2024 | 80.15% | Open |  | 1210.8151
155 | E00014766 | J-2239 | Corplex Pty Ltd | 449-459 Kororoit Creek Road, Altona- Service Stati | GSI | 99999.9996 | 14061.4047 | 14.06% | 0 | 26 Nov 2024 | 0% | Open
156 | E00014488 | J-2241 | Protilt Constructions | 1 Carson Road, Deer Park | GSI | 34800.0006 | 0 | 0% | 24 Jan 2025 | 4 Oct 2024 | #DIV/0! | Open | Difference (GP Exc)
157 | E9991 | J-2242 | Genis Steel Internal | Wine Cellar | GSI | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | Difference (GP Exc)
158 | E00014844 | J-2243 | Arkit | Neometro Display Suit | GSM | 75100 | 0 | 0% | 0 | 12 Dec 2024 | #DIV/0! | Open | #DIV/0! | #DIV/0!
159 | E00014213 | J-2244 | EAZ Crane Hire Pty Ltd | 1-2 Wandarri Court, Cheltenham | GSI | 77899.9999 | 12125.2729 | 15.57% | 25 Oct 2024 | 8 Aug 2024 | 73.6% | Open | 35257.175
160 | E00013875 | J-2245 | Total Construction | 130-140 Parraweena Road, Miranda NSW- Storhub | GSI | 510990.0064 | 89491.161 | 17.51% | 0 | 30 May 2024 | 0% | Open
161 | E00014489 | J-2246 | North | Sanitarium Berkeley Vale- Pallet Bridge | GSI | 2160600.0004 | 311899.7054 | 14.44% | 0 | 4 Oct 2024 | 1.28% | Open | 19028.75
162 | E00013666 | J-2247 | Aliya Homes | 17 Little John Road Warranwood | GSR | 93500.0049 | 19047.8992 | 20.37% | 1 Jul 2024 | On-Going | 40.99% | Open |  | 36471.2831
163 | E00013134 | J-2248 | Gama Homes Pty Ltd | 17 Monash Street Reservoir | GSR | 15500.0004 | 3562.2987 | 22.98% | 1 Feb 2024 | On-Going | 40.63% | Open | 4849.9182
164 | E00014797 | J-2249 | Mainbrace Constructions (NSW) | 4-6 Messenger Avenue, Boorooma- Coles Boorooma Sho | GSI | 1209999.9978 | 194587.5323 | 16.08% | 26 Mar 2025 | 29 Nov 2024 | 2.057% | Open | 18105.8418
165 | E00014828 | J-2250 | Corplex Pty Ltd | 23 Westwood Drive, Ravenhall- Wern Lift | GSI | 20600 | 3534.494 | 17.16% | 31 Mar 2025 | 8 Dec 2024 | 94.24% | Open | 16081.9118
166 | E00012700 | J-2251 | Diggers Rest Construction Pty Ltd | Lot 209 Craftsman Drive, Diggers Rest | GSI | 136999.999 | 26369.4722 | 19.25% | 1 Sep 2023 | 12 Jul 2023 | 1.898% | Open | 2100
167 | E00014943 | J-2252 | Comfy Pod Pty Ltd | 1 Base 12180 x 4650 | GSM | 10850 | 4777.59 | 44.03% | 0 | 22 Jan 2025 | 100% | Open |  | 2850.0081
168 | E00014944 | J-2253 | Comfy Pod Pty Ltd | 1 Base 15110 x 4110 | GSM | 12400 | 1900 | 15.32% | 0 | 22 Jan 2025 | 132.1% | Open | 703.6886
169 | E00014945 | J-2254 | Pino Tilt Constructions Pty Ltd | Carport | GSM | 0 | 0 | #DIV/0! | 0 | 22 Jan 2025 | #DIV/0! | Open | #DIV/0! | #DIV/0!
170 | E00013554 | J-2256 | Bayston Pty Ltd | 77-81 Forsyth Road, Hoppers Crossing | GSI | 615000.0033 | 97177.8657 | 15.8% | 8 May 2024 | 20 Mar 2024 | 0% | Open |  | 123000
171 | E00014759 | J-2257 | ISG Frames | Ballarto Road, Clyde VIC- Evergreen Land Lease | GSR | 110000.0005 | 23585.8535 | 21.44% | 20 Feb 2025 | On-Going | 77.34% | Open | 22053.4559
172 | E00013202 | J-2258 | Bellafia Homes | Lot 11, 37 Launceston Street, Williamstown | GSI | 408000.0011 | 84700.9689 | 20.76% | 9 Feb 2024 | 11 Dec 2023 | 2.569% | Open |  | 71117.1553
173 | E00013238 | J-2259 | Bellafia Homes | 7 Kelly Court, Bell Park | GSI | 660000.0042 | 96350.71 | 14.6% | 13 Feb 2024 | 22 Dec 2023 | 17.69% | Open | 14298.0215
174 | E00014683 | J-2260 | Alpha Truss | 20 Begonia Street, Box Hill | GSR | 8999.9998 | 1782.525 | 19.81% | 27 Feb 2025 | On-Going | 39.03% | Open | 2817.2
175 | E00013825 | J-2261 | Leone Constructions Pty Ltd | 175 Bulla- Diggers Rest Road, Diggers Rest | GSR | 33880 | 8745.9038 | 25.81% | 30 Jul 2024 | 21 May 2024 | 8.427% | Open |  | 3145.0002
176 | E00013354 | J-2262 | Taylors Construction Group | Astra Aerolab, Lot 109-1 Cabbage Tree Road, Willia | GSI | 829999.9937 | 146110.5826 | 17.6% | 0 | 7 Feb 2024 | 0% | Open
177 | E00014558 | J-2264 | Vaughan Constructions Pty Ltd | Link Road, Melbourne Airport | GSI | 488500.0001 | 67718.3811 | 13.86% | 31 Jan 2025 | 18 Oct 2024 | 0% | Open
178 | E00015049 | J-2265 | Impact Designer Homes | 40 McKellar Way, Epping- Factory 5 Mezzanine | GSI | 23000 | 2598 | 11.3% | 0 | 12 Feb 2025 | 22.43% | Open | 4576.3364
179 | E00012154 | J-2267 | Marven Construction | 51 Ewart Street, Malvern | GSR | 8500 | 1967.798 | 23.15% | 28 Apr 2023 | 17 Feb 2023 | 43.73% | Open | 2856.7
180 | E00014516 | J-2268 | Impact Designer Homes | 44 Freight Drive, Somerton | GSI | 370499.9991 | 61321.4131 | 16.55% | 29 Jan 2025 | 8 Oct 2024 | 0.2594% | Open | 802
181 | E00014821 | J-2269 | A Grade Concrete Pty Ltd | 29 Woodberry Way, Epping | GSI | 171199.9993 | 29441.782 | 17.2% | 28 Mar 2025 | 6 Dec 2024 | 0% | Open
182 | E00013831 | J-2270 | Rousson Constructions | 40 Petrik Drive Keilor | GSR | 49500.0037 | 10581.0712 | 21.38% | 1 Aug 2024 | On-Going | 3.237% | Open | 1260
183 | E00014969 | J-2271 | WB Built | 1689 Malvern Road, Glen Iris - Basement | GSR | 13499.9999 | 2272.101 | 16.83% | 1 Mar 2025 | On-Going | 14.13% | Open | 1586.5091
184 | E00012670 | J-2272 | Davies Henderson Pty Ltd | 9 North Road, Brighton | GSR | 82999.9994 | 16544.1047 | 19.93% | 24 Aug 2023 | 5 Jul 2023 | 2.633% | Open | 1750
185 | E00014397 | J-2273 | Arch 10 Pty Ltd | 10 Leyland Street, Mount Waverley | GSR | 28399.9996 | 3773.2408 | 13.29% | 13 Jan 2025 | 13 Sep 2024 | 3.228% | Open | 795
186 | E00014958 | J-2274 | LSR Construction Group Pty Ltd | 50 Wirraway Drive, Port Melbourne | GSI | 261899.9992 | 45297.1043 | 17.3% | 20 Mar 2025 | 23 Jan 2025 | 0% | Open
187 | E00014789 | J-2275 | Rosemont Property Developments | 21 Two Bays Crescent Mount Martha | GSR | 111000.0007 | 15446.2929 | 13.92% | 1 Mar 2025 | On-Going | 3.025% | Open | 2800
188 | E00014805 | J-2276 | VP Homes | 196 Brooklyn Road Brookfield | GSR | 10000.0003 | 1665.5359 | 16.66% | 0 | On-Going | 20.63% | Open | 1719.2
189 | E00011757 | J-2277 | AAA Above Group | 23-25 Seaside Parade, North Shore | GSI | 107500 | 18187.4336 | 16.92% | 27 Jan 2023 | 7 Oct 2022 | 0% | Open
190 | E00014904 | J-2278 | Story Built Pty Ltd | 7 Fir Street, Bulleen | GSR | 37000.0005 | 4692.5928 | 12.68% | 7 Mar 2025 | 8 Jan 2025 | 12.22% | Open | 3947.6364
191 | E00014423 | J-2279 | LSR Construction Group Pty Ltd | 128 Paramount Boulevard, Derrimut | GSI | 507999.9991 | 88000.1617 | 17.32% | 17 Jan 2025 | 20 Sep 2024 | 0% | Open
192 |  | J-2280 | Comfy Pod Pty Ltd | 1 Base 5110 x 31100 | GSM | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | #DIV/0! | #DIV/0!
193 |  | J-2281 | Arkit | Subfloor Components | GSM | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | #DIV/0! | #DIV/0!
194 | E00015127 | J-2282 | C3 Constructions Group | 561 Grieve Parade, Brooklyn- Beams & PFC - HDG | GSI | 49648.5007 | 0 | 0% | 0 | 25 Feb 2025 | #DIV/0! | Open | #DIV/0! | #DIV/0!
195 | E00014778 | J-2283 | A Grade Concrete Pty Ltd | Lot 14 Woodberry Way, Epping- Factory 1 & 2 | GSI | 181999.9996 | 0 | 0% | 21 Mar 2025 | 28 Nov 2024 | #DIV/0! | Open | Difference (GP Exc)
196 | E00015158 | J-2284 | PIPETEK Plumbing Pty Ltd | 15 Everlasting Chase Whittlesea | GSR | 5499.9996 | 1556.77 | 28.3% | 25 Mar 2025 | On-Going | 12.17% | Open |  | 4830.4981
197 | E00014996 | J-2285 | C3 Constructions Group | 122 Harrick Road, Keilor Park | GSI | 329999.9989 | 0 | 0% | 8 Apr 2025 | 31 Jan 2025 | #DIV/0! | Open | #DIV/0! | #DIV/0!
198 | E00015147 | J-2286 | Davies Henderson Pty Ltd | 29-31 St Georges Road, Toorak - Straight Fence Pos | GSR | 111000.0027 | 14283.0026 | 12.87% | 0 | 3 Mar 2025 | 0% | Open
199 | E00014014 | J-2287 | RBM Construction Group Pty Ltd | 36 King Street, Airport West | GSR | 48000.0002 | 0 | 0% | 0 | 1 Jul 2024 | #DIV/0! | Open | Difference (GP Exc)
200 | E9991 | J-2288 | Arjay Modular | Gate 22, Melbourne Airport | GSM | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | Difference (GP Exc)
201 | E00015089 | J-2289 | Quadrant Building | 2335 Mickleham Road, Mickleham | GSR | 18999.9999 | 0 | 0% | 1 Mar 2025 | On-Going | #DIV/0! | Open | Difference (GP Exc)
202 | E00014487 | J-2290 | Grow Constructions | 166 New Street, Brighton | GSR | 23500.0001 | 5511.2361 | 23.45% | 23 Jan 2025 | 3 Oct 2024 | 0% | Open
203 | E00013684 | J-2291 | Arcon Developments Pty Ltd | 1-11 Cherry Lane, Laverton North- Canopy Extension | GSI | 169500.0001 | 31728.3342 | 18.72% | 13 Jun 2024 | 19 Apr 2024 | 0% | Open
204 | E00015203 | J-2292 | John Palazzolo | 3 Caroline Street Thomastown | GSR | 23000.0001 | 4506.584 | 19.59% | 1 Apr 2025 | On-Going | 0% | Open
205 | E00012848 | J-2293 | Arch 10 Pty Ltd | 58 Whitehall Street, Footscray | GSR | 34000.0004 | 8637.4913 | 25.4% | 5 Oct 2023 | 17 Aug 2023 | 0% | Open
206 | E00015220 | J-2294 | Arjay Modular | 3 Battery Enclosure | GSM | 0 | 0 | #DIV/0! | 0 | 20 Mar 2025 | #DIV/0! | Open | #DIV/0! | #DIV/0!
207 | E00015221 | J-2295 | Arjay Modular | Melbourne Airport | GSM | 0 | 0 | #DIV/0! | 0 | 20 Mar 2025 | #DIV/0! | Open | #DIV/0! | #DIV/0!
208 | E00015222 | J-2296 | Arjay Modular | Zoo Project | GSM | 0 | 0 | #DIV/0! | 0 | 20 Mar 2025 | #DIV/0! | Open | #DIV/0! | #DIV/0!
209 | E9991 | J-2297 | Genis Steel (NSW) Pty Ltd | Moorebank Intermodal – WH S2 Signify Office Mezzan | GSI | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | #DIV/0! | #DIV/0!
210 | E00012852 | J-2298 | C3 Constructions Group | 561-569 GrieveParade, Brooklyn | GSI | 165000.0012 | 0 | 0% | 6 Oct 2023 | 18 Aug 2023 | #DIV/0! | Open | Difference (GP Exc)
211 | E00015069 | J-2299 | Futura Homes | 4 Stennis Street Pascoe Vale | GSR | 36999.9998 | 7449.4089 | 20.13% | 1 Apr 2025 | On-Going | 0% | Open
212 | E00015230 | J-2300 | AusPro Steel | Lot 39, 13 Interchange Drive, Mickleham | GSI | 1560 | 0 | 0% | 0 | 21 Mar 2025 | 0% | Open
213 | E00015231 | J-2301 | Leeda Projects Pty Ltd | Swanston Street Brunetti Oro - Screen Frames | GSR | 0 | 0 | #DIV/0! | 1 Apr 2025 | On-Going | #DIV/0! | Open | Difference (GP Exc)
214 | E00015205 | J-2302 | Protilt Constructions | 405-407 Hammond Road, Dandenong South | GSI | 8977.5471 | 0 | 0% | 2 Jun 2025 | 17 Mar 2025 | #DIV/0! | Open | #DIV/0! | #DIV/0!
215 | E9991 | J-2303 | Genis Steel (NSW) Pty Ltd | NSW McGrath Fit-out | GSI | 0 | 0 | #DIV/0! | 1 Mar 2021 | 31 Mar 2021 | #DIV/0! | Open | Difference (GP Exc)
216 |  | J-2304 | Corplex Pty Ltd | 10-15 Peet Street, Pakenham- Broadpro Pakenham | GSI | 0 | 0 | #DIV/0! | 0 | On-Going | #DIV/0! | Open | Difference (GP Exc)
217 | E00014509 | J-2305 | FDC Construction & Fitout (Vic) Pty Ltd | 6 Ferntree Place, Notting Hill- Olympus New Build | GSI | 1943365.2523 | 0 | 0% | 29 Jan 2025 | 8 Oct 2024 | #DIV/0! | Open | Difference (GP Exc)
218 | E00013359 | J-2306 | FDC Construction & Fitout (Vic) Pty Ltd | Lot 21-22 Melbourne Business Park- Makita | GSI | 4236264.5006 | 0 | 0% | 29 Mar 2024 | 7 Feb 2024 | #DIV/0! | Open | Difference (GP Exc)
219 | E00014331 | J-2307 | Cig Fab | Steel Truss Pedestrian Bridge- M80 Ring Road | GSI | 780000.0019 | 0 | 0% | 0 | 2 Sep 2024 | #DIV/0! | Open | Difference (GP Exc)
220 | E00014278 | J-2308 | Squared | Silk Street Pedestrian Bridge | GSI | 237700.0021 | 0 | 0% | 7 Nov 2024 | 20 Aug 2024 | #DIV/0! | Open | Difference (GP Exc)
221 | E00014456 | J-2309 | Squared | WTP Administration Building | GSI | 222461.8347 | 0 | 0% | 0 | 23 Sep 2024 | #DIV/0! | Open | Difference (GP Exc)
222 | E00015024 | J-2310 | Tony Gacovski | 491 Greenhalghs Road, Winter Valley | GSR | 99000.0004 | 7799.9286 | 7.879% | 16 Apr 2025 | 7 Feb 2025 | 0% | Open
[12 empty] | Total | 8050047.5233 | 11412431.8745

## J-965
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Hutchinson Builders |  |  |  |  | Steel | 374174.2921 | 0 | 313177.13 | 0
Estimate Code |  | E00008972 |  |  |  |  | Bolts | 32342.2754 | 0 | 19345.33 | 0
Contract Code |  | J-965 |  |  |  |  | Purlin | 269160.5237 | 0 | 137720.84 | 0
Contract Name |  | VSBA School, Greenvale Secondary- Bundle B |  |  |  |  | Labour | 207751.9643 | 0 | 116414.5 | 34200
Customer |  | Hutchinson Builders |  |  |  |  | Processing | 58650.2891 | 0 | 87947.5 | 0
Start Date |  | 7 Aug 2020 |  |  |  |  | Rigging | 360955.2031 | 0 | 252734.0909 | 0
Completion Date |  | 8 Jul 2020 |  |  |  |  | Freight | 15829.4072 | 0 | 12699.54 | 0
Budgeted Revenue |  | 1700000.06 |  |  |  |  | Shop Drawings | 64575.9258 | 0 | 20838 | 0
Budgeted Job Expenditure |  | 1407671.0923 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.2% |  |  |  |  | Box Frame | 0 | 0 | 36136.64 | 0
Estimated Weight |  | 254.1179 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 161.4584 |  |  |  |  | Stairs | 0 | 0 | 8867 | 0
Current GP% |  | -5.745% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 11207.655 | 0 | 4697.75 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 5400 | 0 | 5912.5 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 7623.5361 | 0 | 2356 | 0
[7 empty] | OH & Profit | 292328.9234 | 0 | 0 | -390000
[7 empty] | Total | 1699999.9953 | 0 | 1018846.8209 | -355800
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1700000.02 | 1700000.02 | 1407671.0923 | 1407671.0923 | 292328.9277 | 17.2% | 0 | 0 | 0 | 0 | 0%
Aug 2020 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 0 | 0 | 0 | 0 | 0%
Sep 2020 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 0 | 0 | 0 | 0 | 0%
Oct 2020 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 0 | 0 | 0 | 0 | 0%
Nov 2020 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 0 | 0 | 0 | 0 | 0%
Dec 2020 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 0 | 0 | 0 | 0 | 0%
Jan 2021 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 0 | 0 | 0 | 0 | 0%
Feb 2021 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 0 | 0 | 1570.98 | 1570.98 | 0.1116%
Mar 2021 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 120000 | 120000 | 156671.44 | 158242.42 | 11.24%
Apr 2021 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 135428 | 255428 | 298470 | 456712.42 | 32.44%
May 2021 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 361902.92 | 617330.92 | 220191.08 | 676903.5 | 48.09%
Jun 2021 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | 108353.29 | 725684.21 | 368325.2373 | 1045228.7373 | 74.25%
Jul 2021 | 0 | 1700000.02 | 0 | 1407671.0923 | 292328.9277 | 17.2% | -71703.9 | 653980.31 | 14629.5627 | 1059858.3 | 75.29%
Aug 2021 | 0 | 1700000.02 | 130000 | 1537671.0923 | 162328.9277 | 9.549% | 98706 | 752686.31 | 6569.68 | 1066427.98 | 69.35%
Sep 2021 | 0 | 1700000.02 | 0 | 1537671.0923 | 162328.9277 | 9.549% | -1027.83 | 751658.48 | -620.25 | 1065807.73 | 69.31%
Oct 2021 | 0 | 1700000.02 | 0 | 1537671.0923 | 162328.9277 | 9.549% | 0 | 751658.48 | -46742.5 | 1019065.23 | 66.27%
Nov 2021 | 0 | 1700000.02 | 0 | 1537671.0923 | 162328.9277 | 9.549% | 0 | 751658.48 | 0 | 1019065.23 | 66.27%
Dec 2021 | 0 | 1700000.02 | 0 | 1537671.0923 | 162328.9277 | 9.549% | 0 | 751658.48 | 32651.5909 | 1051716.8209 | 68.4%
Jan 2022 | 0 | 1700000.02 | 0 | 1537671.0923 | 162328.9277 | 9.549% | 0 | 751658.48 | 0 | 1051716.8209 | 68.4%
Feb 2022 | 0 | 1700000.02 | 30000 | 1567671.0923 | 132328.9277 | 7.784% | 0 | 751658.48 | 0 | 1051716.8209 | 67.09%
Mar 2022 | 0 | 1700000.02 | 30000 | 1597671.0923 | 102328.9277 | 6.019% | 0 | 751658.48 | 1000 | 1052716.8209 | 65.89%
Apr 2022 | 0 | 1700000.02 | 60000 | 1657671.0923 | 42328.9277 | 2.49% | 0 | 751658.48 | 0 | 1052716.8209 | 63.51%
May 2022 | 0 | 1700000.02 | 60000 | 1717671.0923 | -17671.0723 | -1.039% | 0 | 751658.48 | 0 | 1052716.8209 | 61.29%
Jun 2022 | 0 | 1700000.02 | 80000 | 1797671.0923 | -97671.0723 | -5.745% | 0 | 751658.48 | 115 | 1052831.8209 | 58.57%
Jul 2022 | 0 | 1700000.02 | 0 | 1797671.0923 | -97671.0723 | -5.745% | 0 | 751658.48 | 0 | 1052831.8209 | 58.57%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2020 | 0 | 0 | 0 | 0
Sep 2020 | 0 | 0 | 0 | 0
Oct 2020 | 0 | 0 | 0 | 0
Nov 2020 | 0 | 0 | 0 | 0
Dec 2020 | 0 | 0 | 0 | 0
Jan 2021 | 0 | 0 | 0 | 0
Feb 2021 | 1897.223 | 0 | 1897.223 | 1570.98
Mar 2021 | 191104.3841 | 120000 | 71104.3841 | 58877.4029
Apr 2021 | 551557.1978 | 255428 | 296129.1978 | 245207.3567
May 2021 | 817475.0265 | 617330.92 | 200144.1065 | 165727.6881
Jun 2021 | 1262289.809 | 725684.21 | 536605.599 | 444331.8711
Jul 2021 | 1279957.4709 | 653980.31 | 625977.1609 | 518335.2609
Aug 2021 | 1179008.6947 | 752686.31 | 426322.3847 | 385613.8819
Sep 2021 | 1178322.9661 | 751658.48 | 426664.4861 | 385923.3168
Oct 2021 | 1126645.9518 | 751658.48 | 374987.4718 | 339180.8168
Nov 2021 | 1126645.9518 | 751658.48 | 374987.4718 | 339180.8168
Dec 2021 | 1162744.5073 | 751658.48 | 411086.0273 | 371832.4077
Jan 2022 | 1162744.5073 | 751658.48 | 411086.0273 | 371832.4077
Feb 2022 | 1140493.4526 | 751658.48 | 388834.9726 | 358567.8465
Mar 2022 | 1120142.0776 | 751658.48 | 368483.5976 | 346303.2852
Apr 2022 | 1079598.1331 | 751658.48 | 327939.6531 | 319774.1627
May 2022 | 1041886.6712 | 751658.48 | 290228.1912 | 293245.0402
Jun 2022 | 995629.3586 | 751658.48 | 243970.8786 | 257987.8769
Jul 2022 | 995629.3586 | 751658.48 | 243970.8786 | 257987.8769
Job Profitability Summary
| Beginning | Aug 2020 | Sep 2020 | Oct 2020 | Nov 2020 | Dec 2020 | Jan 2021 | Feb 2021 | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 135428 | 361902.92 | 108353.29 | -71703.9 | 98706 | -1027.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570.98 | 58877.4029 | 245207.3567 | 165727.6881 | 444331.8711 | 518335.2609 | 385613.8819 | 385923.3168 | 339180.8168 | 339180.8168 | 371832.4077 | 371832.4077 | 358567.8465 | 346303.2852 | 319774.1627 | 293245.0402 | 257987.8769 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570.98 | 156671.44 | 298470 | 220191.08 | 368325.2373 | 14629.5627 | 6569.68 | -620.25 | -46742.5 | 0 | 32651.5909 | 0 | 0 | 1000 | 0 | 0 | 115 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 1570.98 | 58877.4029 | 245207.3567 | 165727.6881 | 444331.8711 | 518335.2609 | 385613.8819 | 385923.3168 | 339180.8168 | 339180.8168 | 371832.4077 | 371832.4077 | 358567.8465 | 346303.2852 | 319774.1627 | 293245.0402 | 257987.8769 | 257987.8769 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99365.0171 | 112140.0461 | 299670.7487 | 89721.0543 | -59373.8271 | 139291.059 | -929.685 | 0 | 0 | 0 | 0 | 13264.5613 | 13264.5613 | 26529.1225 | 26529.1225 | 35372.1633 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0.1116% | 11.24% | 32.44% | 48.09% | 74.25% | 75.29% | 69.35% | 69.31% | 66.27% | 66.27% | 68.4% | 68.4% | 67.09% | 65.89% | 63.51% | 61.29% | 58.57% | 58.57% | 58.57%

## J-1085
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Hadi Hayek |  |  |  |  | Steel | 61317.9278 | 0 | 6965.37 | 0
Estimate Code |  | E00009967 |  |  |  |  | Bolts | 1848.0525 | 0 | 526.13 | 500
Contract Code |  | J-1085 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 5 Brympton Avenue, Park Orchards |  |  |  |  | Labour | 16936.6954 | 0 | 25458.5755 | 5000
Customer |  | Hadi Hayek |  |  |  |  | Processing | 9108.2588 | 0 | 19076.58 | 0
Start Date |  | 26 Oct 2021 |  |  |  |  | Rigging | 1000 | 0 | 11045 | 0
Completion Date |  | 29 Apr 2021 |  |  |  |  | Freight | 500 | 0 | 2585 | 0
Budgeted Revenue |  | 188000.01 |  |  |  |  | Shop Drawings | 5808.165 | 0 | 5808 | 0
Budgeted Job Expenditure |  | 131231.1498 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 30.2% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 29.0408 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 630
Actual Weight |  | 24.0041 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 30.2% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 2397.92 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 726.0206 | 0 | 696.7 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 13254.8804 | 0 | 0 | 0
[7 empty] | Total | 112897.9205 | 0 | 72791.3555 | 5500
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 188000 | 188000 | 131231.1498 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
May 2021 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Jun 2021 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Jul 2021 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Aug 2021 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Sep 2021 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Oct 2021 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Nov 2021 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Dec 2021 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Jan 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Feb 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Mar 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 0 | 0%
Apr 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 3742.22 | 3742.22 | 2.852%
May 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 22273.4955 | 26015.7155 | 19.82%
Jun 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 26015.7155 | 19.82%
Jul 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 26015.7155 | 19.82%
Aug 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 10053.92 | 36069.6355 | 27.49%
Sep 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 20217.62 | 56287.2555 | 42.89%
Oct 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 1152.5 | 57439.7555 | 43.77%
Nov 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 1970 | 59409.7555 | 45.27%
Dec 2022 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 210 | 59619.7555 | 45.43%
Jan 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 70 | 59689.7555 | 45.48%
Feb 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
Mar 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
Apr 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
May 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
Jun 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
Jul 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
Aug 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
Sep 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
Oct 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
Nov 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
Dec 2023 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 59689.7555 | 45.48%
Jan 2024 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 2047 | 61736.7555 | 47.04%
Feb 2024 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 862.5 | 62599.2555 | 47.7%
Mar 2024 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 0 | 62599.2555 | 47.7%
Apr 2024 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 12731.25 | 75330.5055 | 57.4%
May 2024 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 2460.8533 | 77791.3588 | 59.28%
Jun 2024 | 0 | 188000 | 0 | 131231.1498 | 56768.8502 | 30.2% | 0 | 0 | 500 | 78291.3588 | 59.66%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
May 2021 | 0 | 0 | 0 | 0
Jun 2021 | 0 | 0 | 0 | 0
Jul 2021 | 0 | 0 | 0 | 0
Aug 2021 | 0 | 0 | 0 | 0
Sep 2021 | 0 | 0 | 0 | 0
Oct 2021 | 0 | 0 | 0 | 0
Nov 2021 | 0 | 0 | 0 | 0
Dec 2021 | 0 | 0 | 0 | 0
Jan 2022 | 0 | 0 | 0 | 0
Feb 2022 | 0 | 0 | 0 | 0
Mar 2022 | 0 | 0 | 0 | 0
Apr 2022 | 5361.0546 | 0 | 5361.0546 | 3742.22
May 2022 | 37269.768 | 0 | 37269.768 | 26015.7155
Jun 2022 | 37269.768 | 0 | 37269.768 | 26015.7155
Jul 2022 | 37269.768 | 0 | 37269.768 | 26015.7155
Aug 2022 | 51672.8801 | 0 | 51672.8801 | 36069.6355
Sep 2022 | 80636.3736 | 0 | 80636.3736 | 56287.2555
Oct 2022 | 82287.4298 | 0 | 82287.4298 | 57439.7555
Nov 2022 | 85109.6256 | 0 | 85109.6256 | 59409.7555
Dec 2022 | 85410.4688 | 0 | 85410.4688 | 59619.7555
Jan 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Feb 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Mar 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Apr 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
May 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Jun 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Jul 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Aug 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Sep 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Oct 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Nov 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Dec 2023 | 85510.7499 | 0 | 85510.7499 | 59689.7555
Jan 2024 | 88443.2549 | 0 | 88443.2549 | 61736.7555
Feb 2024 | 89678.8609 | 0 | 89678.8609 | 62599.2555
Mar 2024 | 89678.8609 | 0 | 89678.8609 | 62599.2555
Apr 2024 | 107917.4803 | 0 | 107917.4803 | 75330.5055
May 2024 | 111442.8661 | 0 | 111442.8661 | 77791.3588
Jun 2024 | 112159.1594 | 0 | 112159.1594 | 78291.3588
Job Profitability Summary
| Beginning | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3742.22 | 26015.7155 | 26015.7155 | 26015.7155 | 36069.6355 | 56287.2555 | 57439.7555 | 59409.7555 | 59619.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 61736.7555 | 62599.2555 | 62599.2555 | 75330.5055 | 77791.3588 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3742.22 | 22273.4955 | 0 | 0 | 10053.92 | 20217.62 | 1152.5 | 1970 | 210 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2047 | 862.5 | 0 | 12731.25 | 2460.8533 | 500 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3742.22 | 26015.7155 | 26015.7155 | 26015.7155 | 36069.6355 | 56287.2555 | 57439.7555 | 59409.7555 | 59619.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 59689.7555 | 61736.7555 | 62599.2555 | 62599.2555 | 75330.5055 | 77791.3588 | 78291.3588 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.852% | 19.82% | 19.82% | 19.82% | 27.49% | 42.89% | 43.77% | 45.27% | 45.43% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 47.04% | 47.7% | 47.7% | 57.4% | 59.28% | 59.66% | 59.66%

## J-1328
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Alchemy Construct |  |  |  |  | Steel | 162068.2525 | 8000 | 188676.5291 | 0
Estimate Code |  | E00010737 |  |  |  |  | Bolts | 7873.2251 | 5000 | 12335.4582 | 0
Contract Code |  | J-1328 |  |  |  |  | Purlin | 25879.7199 | 13000 | 37089.4091 | 0
Contract Name |  | 8 Langs Road, Ascot Vale |  |  |  |  | Labour | 60208.5962 | 40000 | 84582.0027 | 14584
Customer |  | Alchemy Construct |  |  |  |  | Processing | 30587.9434 | 12000 | 42955.1627 | 0
Start Date |  | 1 May 2022 |  |  |  |  | Rigging | 112456.7734 | 35000 | 11757.5 | 0
Completion Date |  | 19 Nov 2021 |  |  |  |  | Freight | 4837.956 | 0 | 12429.8955 | 0
Budgeted Revenue |  | 584123.99 |  |  |  |  | Shop Drawings | 13414.624 | 5000 | 16800 | 0
Budgeted Job Expenditure |  | 462293.2788 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.86% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 66.4495 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 81.1003 |  |  |  |  | Stairs | 28000 | 0 | 0 | 0
Current GP% |  | 20.74% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 2262.55 | 0 | 3607.4982 | 0
[7 empty] | Grates | 0 | 0 | 11160 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 13011.2292 | 0 | 3020 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1692.4021 | 0 | 0 | 0
[7 empty] | OH & Profit | 121830.7278 | 30000 | 0 | 0
[7 empty] | Total | 584123.9998 | 148000 | 424413.4555 | 14584
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 584124.01 | 584124.01 | 462293.2788 | 462293.2788 | 121830.7312 | 20.86% | 0 | 0 | 0 | 0 | 0%
Feb 2022 | 0 | 584124.01 | 0 | 462293.2788 | 121830.7312 | 20.86% | 0 | 0 | 0 | 0 | 0%
Mar 2022 | 0 | 584124.01 | 0 | 462293.2788 | 121830.7312 | 20.86% | 0 | 0 | 108 | 108 | 0.02336%
Apr 2022 | 0 | 584124.01 | 0 | 462293.2788 | 121830.7312 | 20.86% | 0 | 0 | 5368.85 | 5476.85 | 1.185%
May 2022 | 0 | 584124.01 | 0 | 462293.2788 | 121830.7312 | 20.86% | 6400 | 6400 | 23739.68 | 29216.53 | 6.32%
Jun 2022 | 0 | 584124.01 | 0 | 462293.2788 | 121830.7312 | 20.86% | -704 | 5696 | 125505.7909 | 154722.3209 | 33.47%
Jul 2022 | 0 | 584124.01 | 0 | 462293.2788 | 121830.7312 | 20.86% | 0 | 5696 | 4056.92 | 158779.2409 | 34.35%
Aug 2022 | 0 | 584124.01 | 0 | 462293.2788 | 121830.7312 | 20.86% | 40000 | 45696 | 15079.2445 | 173858.4855 | 37.61%
Sep 2022 | 0 | 584124.01 | 0 | 462293.2788 | 121830.7312 | 20.86% | -4400 | 41296 | 3875.59 | 177734.0755 | 38.45%
Oct 2022 | 0 | 584124.01 | 0 | 462293.2788 | 121830.7312 | 20.86% | 0 | 41296 | 16878.39 | 194612.4655 | 42.1%
Nov 2022 | 0 | 584124.01 | 0 | 462293.2788 | 121830.7312 | 20.86% | 309124 | 350420 | 99091.2782 | 293703.7436 | 63.53%
Dec 2022 | 148000 | 732124.01 | 118000 | 580293.2788 | 151830.7312 | 20.74% | 18275.19 | 368695.19 | 168266.2109 | 461969.9545 | 79.61%
Jan 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 121399.2 | 490094.39 | -8322.33 | 453647.6245 | 78.18%
Feb 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 100000 | 590094.39 | 5262.0009 | 458909.6255 | 79.08%
Mar 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 58015.27 | 648109.66 | 1866.7903 | 460776.4158 | 79.4%
Apr 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 0 | 648109.66 | -37705.2518 | 423071.1639 | 72.91%
May 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 16876 | 664985.66 | 1907.7764 | 424978.9403 | 73.24%
Jun 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 0 | 664985.66 | 611.3127 | 425590.253 | 73.34%
Jul 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 0 | 664985.66 | 13266.6479 | 438856.9009 | 75.63%
Aug 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 16850 | 681835.66 | 140.5645 | 438997.4655 | 75.65%
Sep 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 0 | 681835.66 | 0 | 438997.4655 | 75.65%
Oct 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 0 | 681835.66 | 0 | 438997.4655 | 75.65%
Nov 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | -66 | 681769.66 | 0 | 438997.4655 | 75.65%
Dec 2023 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 0 | 681769.66 | 0 | 438997.4655 | 75.65%
Jan 2024 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 0 | 681769.66 | 0 | 438997.4655 | 75.65%
Feb 2024 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | 0 | 681769.66 | 0 | 438997.4655 | 75.65%
Mar 2024 | 0 | 732124.01 | 0 | 580293.2788 | 151830.7312 | 20.74% | -860.75 | 680908.91 | 0 | 438997.4655 | 75.65%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2022 | 0 | 0 | 0 | 0
Mar 2022 | 136.4618 | 0 | 136.4618 | 108
Apr 2022 | 6920.1949 | 0 | 6920.1949 | 5476.85
May 2022 | 36916.1254 | 6400 | 30516.1254 | 24151.3779
Jun 2022 | 195497.1588 | 5696 | 189801.1588 | 150214.3355
Jul 2022 | 200623.2216 | 5696 | 194927.2216 | 154271.2555
Aug 2022 | 219676.3837 | 45696 | 173980.3837 | 137693.2991
Sep 2022 | 224573.3296 | 41296 | 183277.3296 | 145051.1812
Oct 2022 | 245899.776 | 41296 | 204603.776 | 161929.5712
Nov 2022 | 371105.1325 | 350420 | 20685.1325 | 16370.8349
Dec 2022 | 582842.0007 | 368695.19 | 214146.8107 | 169736.2103
Jan 2023 | 572342.1762 | 490094.39 | 82247.7862 | 65190.9196
Feb 2023 | 578980.9524 | 590094.39 | -11113.4376 | -8808.6896
Mar 2023 | 581336.1787 | 648109.66 | -66773.4813 | -52925.7365
Apr 2023 | 533765.543 | 648109.66 | -114344.117 | -90630.9883
May 2023 | 536172.4792 | 664985.66 | -128813.1808 | -102099.4013
Jun 2023 | 536943.7387 | 664985.66 | -128041.9213 | -101488.0885
Jul 2023 | 553681.5363 | 664985.66 | -111304.1237 | -88221.4406
Aug 2023 | 553858.8788 | 681835.66 | -127976.7812 | -101436.4574
Sep 2023 | 553858.8788 | 681835.66 | -127976.7812 | -101436.4574
Oct 2023 | 553858.8788 | 681835.66 | -127976.7812 | -101436.4574
Nov 2023 | 553858.8788 | 681769.66 | -127910.7812 | -101384.1448
Dec 2023 | 553858.8788 | 681769.66 | -127910.7812 | -101384.1448
Jan 2024 | 553858.8788 | 681769.66 | -127910.7812 | -101384.1448
Feb 2024 | 553858.8788 | 681769.66 | -127910.7812 | -101384.1448
Mar 2024 | 553858.8788 | 680908.91 | -127050.0312 | -100701.9004
Job Profitability Summary
| Beginning | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Total
Sales | 0 | 0 | 0 | 0 | 6400 | -704 | 0 | 40000 | -4400 | 0 | 309124 | 18275.19 | 121399.2 | 100000 | 58015.27 | 0 | 16876 | 0 | 0 | 16850 | 0 | 0 | -66 | 0 | 0 | 0 | -860.75 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11113.4376 | -66773.4813 | -114344.117 | -128813.1808 | -128041.9213 | -111304.1237 | -127976.7812 | -127976.7812 | -127976.7812 | -127910.7812 | -127910.7812 | -127910.7812 | -127910.7812 | -127050.0312 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11113.4376 | 66773.4813 | 114344.117 | 128813.1808 | 128041.9213 | 111304.1237 | 127976.7812 | 127976.7812 | 127976.7812 | 127910.7812 | 127910.7812 | 127910.7812 | 127910.7812
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 108 | 5476.85 | 24151.3779 | 150214.3355 | 154271.2555 | 137693.2991 | 145051.1812 | 161929.5712 | 16370.8349 | 169736.2103 | 65190.9196 | -8808.6896 | -52925.7365 | -90630.9883 | -102099.4013 | -101488.0885 | -88221.4406 | -101436.4574 | -101436.4574 | -101436.4574 | -101384.1448 | -101384.1448 | -101384.1448 | -101384.1448 | 0
Construction Costs | 0 | 0 | 108 | 5368.85 | 23739.68 | 125505.7909 | 4056.92 | 15079.2445 | 3875.59 | 16878.39 | 99091.2782 | 168266.2109 | -8322.33 | 5262.0009 | 1866.7903 | -37705.2518 | 1907.7764 | 611.3127 | 13266.6479 | 140.5645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 108 | 5476.85 | 24151.3779 | 150214.3355 | 154271.2555 | 137693.2991 | 145051.1812 | 161929.5712 | 16370.8349 | 169736.2103 | 65190.9196 | -8808.6896 | -52925.7365 | -90630.9883 | -102099.4013 | -101488.0885 | -88221.4406 | -101436.4574 | -101436.4574 | -101436.4574 | -101384.1448 | -101384.1448 | -101384.1448 | -101384.1448 | -100701.9004 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 5065.1521 | -557.1667 | 0 | 31657.2009 | -3482.2921 | 0 | 244650.0145 | 14900.8355 | 96222.9607 | 79261.6102 | 45983.8371 | 0 | 13376.1893 | 0 | 0 | 13355.5813 | 0 | 0 | -52.3127 | 0 | 0 | 0 | -682.2443 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.02336% | 1.185% | 6.32% | 33.47% | 34.35% | 37.61% | 38.45% | 42.1% | 63.53% | 79.61% | 78.18% | 79.08% | 79.4% | 72.91% | 73.24% | 73.34% | 75.63% | 75.65% | 75.65% | 75.65% | 75.65% | 75.65% | 75.65% | 75.65% | 75.65% | 75.65%

## J-1373
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Empire Property Builders Pty Ltd |  |  |  |  | Steel | 80232.0955 | 0 | 80185.8464 | 0
Estimate Code |  | E00010958 |  |  |  |  | Bolts | 3129.1929 | 0 | 3404.7909 | 0
Contract Code |  | J-1373 |  |  |  |  | Purlin | 8847.59 | 0 | 8816.1727 | 0
Contract Name |  | 50 Mainview Boulevard, Truganina- LOT D |  |  |  |  | Labour | 36573.8772 | 0 | 3169.37 | 0
Customer |  | Empire Property Builders Pty Ltd |  |  |  |  | Processing | 30443.2246 | 0 | 26490.3418 | 0
Start Date |  | 28 Jun 2022 |  |  |  |  | Rigging | 95013.0391 | 0 | 98475 | 0
Completion Date |  | 18 Feb 2022 |  |  |  |  | Freight | 6538.0637 | 0 | 7622.1818 | 0
Budgeted Revenue |  | 364900 |  |  |  |  | Shop Drawings | 6246.2393 | 0 | 6230 | 0
Budgeted Job Expenditure |  | 301263.7933 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.44% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 43.8508 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 35.49 |  |  |  |  | Stairs | 0 | 0 | 40000 | 0
Current GP% |  | 17.44% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 32624.9461 | 0 | 32562.8818 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 300 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1315.5239 | 0 | 0 | 0
[7 empty] | OH & Profit | 63636.2015 | 0 | 0 | 0
[7 empty] | Total | 364899.9937 | 0 | 306956.5855 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 364900 | 364900 | 301263.7933 | 301263.7933 | 63636.2067 | 17.44% | 0 | 0 | 0 | 0 | 0%
Mar 2022 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 109470 | 109470 | 0 | 0 | 0%
Apr 2022 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 0 | 0%
May 2022 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 0 | 0%
Jun 2022 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 0 | 0%
Jul 2022 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 115 | 115 | 0.03817%
Aug 2022 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 115 | 0.03817%
Sep 2022 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 490 | 605 | 0.2008%
Oct 2022 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Nov 2022 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Dec 2022 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Jan 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Feb 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Mar 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Apr 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
May 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Jun 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Jul 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Aug 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Sep 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 605 | 0.2008%
Oct 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 70 | 675 | 0.2241%
Nov 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 675 | 0.2241%
Dec 2023 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 675 | 0.2241%
Jan 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 675 | 0.2241%
Feb 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 675 | 0.2241%
Mar 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 675 | 0.2241%
Apr 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 0 | 675 | 0.2241%
May 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 1291.5 | 1966.5 | 0.6528%
Jun 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 93945.5824 | 95912.0824 | 31.84%
Jul 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 15395.5942 | 111307.6767 | 36.95%
Aug 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 2990 | 114297.6767 | 37.94%
Sep 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 40951.5 | 155249.1767 | 51.53%
Oct 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 92033.0091 | 247282.1858 | 82.08%
Nov 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 45719.7173 | 293001.903 | 97.26%
Dec 2024 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 109470 | 1785.1073 | 294787.0103 | 97.85%
Jan 2025 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 84130 | 193600 | 540 | 295327.0103 | 98.03%
Feb 2025 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 193600 | 0 | 295327.0103 | 98.03%
Mar 2025 | 0 | 364900 | 0 | 301263.7933 | 63636.2067 | 17.44% | 0 | 193600 | 11629.5818 | 306956.5921 | 101.9%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2022 | 0 | 109470 | -109470 | -90379.138
Apr 2022 | 0 | 109470 | -109470 | -90379.138
May 2022 | 0 | 109470 | -109470 | -90379.138
Jun 2022 | 0 | 109470 | -109470 | -90379.138
Jul 2022 | 139.2915 | 109470 | -109330.7085 | -90264.138
Aug 2022 | 139.2915 | 109470 | -109330.7085 | -90264.138
Sep 2022 | 732.7947 | 109470 | -108737.2053 | -89774.138
Oct 2022 | 732.7947 | 109470 | -108737.2053 | -89774.138
Nov 2022 | 732.7947 | 109470 | -108737.2053 | -89774.138
Dec 2022 | 732.7947 | 109470 | -108737.2053 | -89774.138
Jan 2023 | 732.7947 | 109470 | -108737.2053 | -89774.138
Feb 2023 | 732.7947 | 109470 | -108737.2053 | -89774.138
Mar 2023 | 732.7947 | 109470 | -108737.2053 | -89774.138
Apr 2023 | 732.7947 | 109470 | -108737.2053 | -89774.138
May 2023 | 732.7947 | 109470 | -108737.2053 | -89774.138
Jun 2023 | 732.7947 | 109470 | -108737.2053 | -89774.138
Jul 2023 | 732.7947 | 109470 | -108737.2053 | -89774.138
Aug 2023 | 732.7947 | 109470 | -108737.2053 | -89774.138
Sep 2023 | 732.7947 | 109470 | -108737.2053 | -89774.138
Oct 2023 | 817.5808 | 109470 | -108652.4192 | -89704.138
Nov 2023 | 817.5808 | 109470 | -108652.4192 | -89704.138
Dec 2023 | 817.5808 | 109470 | -108652.4192 | -89704.138
Jan 2024 | 817.5808 | 109470 | -108652.4192 | -89704.138
Feb 2024 | 817.5808 | 109470 | -108652.4192 | -89704.138
Mar 2024 | 817.5808 | 109470 | -108652.4192 | -89704.138
Apr 2024 | 817.5808 | 109470 | -108652.4192 | -89704.138
May 2024 | 2381.8855 | 109470 | -107088.1145 | -88412.638
Jun 2024 | 116171.673 | 109470 | 6701.673 | 5532.9444
Jul 2024 | 134819.2916 | 109470 | 25349.2916 | 20928.5387
Aug 2024 | 138440.8719 | 109470 | 28970.8719 | 23918.5387
Sep 2024 | 188042.592 | 109470 | 78572.592 | 64870.0387
Oct 2024 | 299515.8117 | 109470 | 190045.8117 | 156903.0478
Nov 2024 | 354892.9436 | 109470 | 245422.9436 | 202622.765
Dec 2024 | 357055.1206 | 109470 | 247585.1206 | 204407.8723
Jan 2025 | 357709.1853 | 193600 | 164109.1853 | 135489.6017
Feb 2025 | 357709.1853 | 193600 | 164109.1853 | 135489.6017
Mar 2025 | 371795.2935 | 193600 | 178195.2935 | 147119.1835
Job Profitability Summary
| Beginning | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 109470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84130 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | -109470 | -109470 | -109470 | -109470 | -109330.7085 | -109330.7085 | -108737.2053 | -108737.2053 | -108737.2053 | -108737.2053 | -108737.2053 | -108737.2053 | -108737.2053 | -108737.2053 | -108737.2053 | -108737.2053 | -108737.2053 | -108737.2053 | -108737.2053 | -108652.4192 | -108652.4192 | -108652.4192 | -108652.4192 | -108652.4192 | -108652.4192 | -108652.4192 | -107088.1145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 109470 | 109470 | 109470 | 109470 | 109330.7085 | 109330.7085 | 108737.2053 | 108737.2053 | 108737.2053 | 108737.2053 | 108737.2053 | 108737.2053 | 108737.2053 | 108737.2053 | 108737.2053 | 108737.2053 | 108737.2053 | 108737.2053 | 108737.2053 | 108652.4192 | 108652.4192 | 108652.4192 | 108652.4192 | 108652.4192 | 108652.4192 | 108652.4192 | 107088.1145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | -90379.138 | -90379.138 | -90379.138 | -90379.138 | -90264.138 | -90264.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89704.138 | -89704.138 | -89704.138 | -89704.138 | -89704.138 | -89704.138 | -89704.138 | -88412.638 | 5532.9444 | 20928.5387 | 23918.5387 | 64870.0387 | 156903.0478 | 202622.765 | 204407.8723 | 135489.6017 | 135489.6017 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 115 | 0 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 1291.5 | 93945.5824 | 15395.5942 | 2990 | 40951.5 | 92033.0091 | 45719.7173 | 1785.1073 | 540 | 0 | 11629.5818 | #VALUE!
Closing WIP | Difference (GP Exc) | -90379.138 | -90379.138 | -90379.138 | -90379.138 | -90264.138 | -90264.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89774.138 | -89704.138 | -89704.138 | -89704.138 | -89704.138 | -89704.138 | -89704.138 | -89704.138 | -88412.638 | 5532.9444 | 20928.5387 | 23918.5387 | 64870.0387 | 156903.0478 | 202622.765 | 204407.8723 | 135489.6017 | 135489.6017 | 147119.1835 | 0
Total Costruction Cost | #VALUE! | 90379.138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69458.2706 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0.03817% | 0.03817% | 0.2008% | 0.2008% | 0.2008% | 0.2008% | 0.2008% | 0.2008% | 0.2008% | 0.2008% | 0.2008% | 0.2008% | 0.2008% | 0.2008% | 0.2008% | 0.2241% | 0.2241% | 0.2241% | 0.2241% | 0.2241% | 0.2241% | 0.2241% | 0.6528% | 31.84% | 36.95% | 37.94% | 51.53% | 82.08% | 97.26% | 97.85% | 98.03% | 98.03% | 101.9% | 101.9%

## J-1407
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1407 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Maddox Road, Altona- Newport |  |  |  |  | Labour | 0 | 0 | 662.5 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 0 | 0 | 57.5 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 175 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 895 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-1408
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1408 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Mountain Highway, Bayswater |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-1410
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1410 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Ozco Trucks, Colardo Drive |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-1411
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1411 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Palmers Road, Truganina |  |  |  |  | Labour | 0 | 0 | 60 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 280 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 340 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-1413
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1413 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Servo |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 0 | 0 | 1322.5 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 1322.5 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-1414
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1414 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Galleghars Road, Epping- S. A |  |  |  |  | Labour | 0 | 0 | 123 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 123 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-1431
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Vaughan Constructions Pty Ltd |  |  |  |  | Steel | 1227000.2923 | 242000 | 113494.6727 | 0
Estimate Code |  | E00010748 |  |  |  |  | Bolts | 84000 | 0 | 83917.0273 | 0
Contract Code |  | J-1431 |  |  |  |  | Purlin | 450000.0302 | 80000 | 524846.9727 | 0
Contract Name |  | 30-68 Taras Avenue, Altona North - Nascap |  |  |  |  | Labour | 279803.0605 | 50000 | 307722.9 | 107230.92
Customer |  | Vaughan Constructions Pty Ltd |  |  |  |  | Processing | 219999.6133 | 30000 | 227915.7591 | 0
Start Date |  | 19 May 2022 |  |  |  |  | Rigging | 637999.6875 | 344515 | 970534.4 | 0
Completion Date |  | 24 Nov 2021 |  |  |  |  | Freight | 64742.6113 | 0 | 42340.1264 | 0
Budgeted Revenue |  | 3795000.03 |  |  |  |  | Shop Drawings | 59999.8398 | 0 | 51700 | 0
Budgeted Job Expenditure |  | 3175045.1616 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.34% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 537.7776 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 613.1704 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 44.99% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 128500 | 0 | 128017.6273 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 17000 | 0 | 16632.8636 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 5999.9839 | 0 | 1827.5 | 0
[7 empty] | OH & Profit | 619954.8697 | 140000 | 0 | 1346244
[7 empty] | Total | 3794999.9886 | 886515 | 2468949.8491 | 1453474.92
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 3795000.04 | 3795000.04 | 3175045.1616 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 0 | 0 | 0%
Apr 2022 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 0 | 0 | 0%
May 2022 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 0 | 0 | 0%
Jun 2022 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 0 | 0 | 0%
Jul 2022 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 0 | 0 | 0%
Aug 2022 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 0 | 0 | 0%
Sep 2022 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 0 | 0 | 0%
Oct 2022 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 864.38 | 864.38 | 0.02722%
Nov 2022 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 0 | 864.38 | 0.02722%
Dec 2022 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 12230.5 | 13094.88 | 0.4124%
Jan 2023 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 12218.4236 | 25313.3036 | 0.7973%
Feb 2023 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 0 | 0 | 94380.8545 | 119694.1582 | 3.77%
Mar 2023 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 750000 | 750000 | 603639.3921 | 723333.5503 | 22.78%
Apr 2023 | 0 | 3795000.04 | 0 | 3175045.1616 | 619954.8784 | 16.34% | 785175 | 1535175 | 256696.1386 | 980029.6889 | 30.87%
May 2023 | 105175 | 3900175.04 | 55175 | 3230220.1616 | 669954.8784 | 17.18% | 255000 | 1790175 | 250880.0515 | 1230909.7405 | 38.11%
Jun 2023 | 0 | 3900175.04 | 0 | 3230220.1616 | 669954.8784 | 17.18% | 470070 | 2260245 | 259275.7897 | 1490185.5302 | 46.13%
Jul 2023 | 0 | 3900175.04 | 0 | 3230220.1616 | 669954.8784 | 17.18% | 300000 | 2560245 | 524663.1861 | 2014848.7162 | 62.37%
Aug 2023 | 675000 | 4575175.04 | 585000 | 3815220.1616 | 759954.8784 | 16.61% | 100000 | 2660245 | 47668.0291 | 2062516.7453 | 54.06%
Sep 2023 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 17655 | 2677900 | 7438.1455 | 2069954.8908 | 54.26%
Oct 2023 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 0 | 2677900 | 39429.2427 | 2109384.1335 | 55.29%
Nov 2023 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 2700 | 2680600 | 44984.4373 | 2154368.5708 | 56.47%
Dec 2023 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 71000 | 2751600 | 21681.2909 | 2176049.8617 | 57.04%
Jan 2024 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 20511.5 | 2772111.5 | 9632.48 | 2185682.3417 | 57.29%
Feb 2024 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 18400 | 2790511.5 | 9004.25 | 2194686.5917 | 57.52%
Mar 2024 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 0 | 2790511.5 | 29013.6645 | 2223700.2562 | 58.28%
Apr 2024 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 0 | 2790511.5 | 99131.2579 | 2322831.5141 | 60.88%
May 2024 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 200000 | 2990511.5 | 106055.5973 | 2428887.1114 | 63.66%
Jun 2024 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 2825 | 2993336.5 | 36378.5636 | 2465265.675 | 64.62%
Jul 2024 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 40300 | 3033636.5 | 7290.2591 | 2472555.9341 | 64.81%
Aug 2024 | 0 | 4575175.04 | 0 | 3815220.1616 | 759954.8784 | 16.61% | 0 | 3033636.5 | 3092.18 | 2475648.1141 | 64.89%
Sep 2024 | 14340 | 4589515.04 | 14340 | 3829560.1616 | 759954.8784 | 16.56% | 14340 | 3047976.5 | 8229.25 | 2483877.3641 | 64.86%
Oct 2024 | 0 | 4589515.04 | 0 | 3829560.1616 | 759954.8784 | 16.56% | 3375 | 3051351.5 | 24444.7 | 2508322.0641 | 65.5%
Nov 2024 | 92000 | 4681515.04 | 92000 | 3921560.1616 | 759954.8784 | 16.23% | 92000 | 3143351.5 | 66543.1745 | 2574865.2386 | 65.66%
Dec 2024 | 0 | 4681515.04 | 0 | 3921560.1616 | 759954.8784 | 16.23% | 0 | 3143351.5 | 450 | 2575315.2386 | 65.67%
Jan 2025 | 0 | 4681515.04 | -1346244 | 2575316.1616 | 2106198.8784 | 44.99% | 8890 | 3152241.5 | 0 | 2575315.2386 | 100%
Feb 2025 | 0 | 4681515.04 | 0 | 2575316.1616 | 2106198.8784 | 44.99% | 0 | 3152241.5 | 0 | 2575315.2386 | 100%
Mar 2025 | 0 | 4681515.04 | 0 | 2575316.1616 | 2106198.8784 | 44.99% | 0 | 3152241.5 | 865.5455 | 2576180.7841 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2022 | 0 | 0 | 0 | 0
May 2022 | 0 | 0 | 0 | 0
Jun 2022 | 0 | 0 | 0 | 0
Jul 2022 | 0 | 0 | 0 | 0
Aug 2022 | 0 | 0 | 0 | 0
Sep 2022 | 0 | 0 | 0 | 0
Oct 2022 | 1033.1576 | 0 | 1033.1576 | 864.38
Nov 2022 | 1033.1576 | 0 | 1033.1576 | 864.38
Dec 2022 | 15651.768 | 0 | 15651.768 | 13094.88
Jan 2023 | 30255.9439 | 0 | 30255.9439 | 25313.3036
Feb 2023 | 143065.4721 | 0 | 143065.4721 | 119694.1582
Mar 2023 | 864570.6478 | 750000 | 114570.6478 | 95854.276
Apr 2023 | 1171388.9156 | 1535175 | -363786.0844 | -304357.6377
May 2023 | 1486203.1707 | 1790175 | -303971.8293 | -251756.8882
Jun 2023 | 1799253.3384 | 2260245 | -460991.6616 | -381804.5458
Jul 2023 | 2432732.8415 | 2560245 | -127512.1585 | -105608.6819
Aug 2023 | 2473350.0907 | 2660245 | -186894.9093 | -155850.9172
Sep 2023 | 2482269.8426 | 2677900 | -195630.1574 | -163135.2056
Oct 2023 | 2529553.0083 | 2677900 | -148346.9917 | -123705.9628
Nov 2023 | 2583497.9095 | 2680600 | -97102.0905 | -80973.0448
Dec 2023 | 2609497.9034 | 2751600 | -142102.0966 | -118498.3698
Jan 2024 | 2621049.0801 | 2772111.5 | -151062.4199 | -125970.3476
Feb 2024 | 2631846.8894 | 2790511.5 | -158664.6106 | -132309.784
Mar 2024 | 2666639.7947 | 2790511.5 | -123871.7053 | -103296.1194
Apr 2024 | 2785517.0384 | 2790511.5 | -4994.4616 | -4164.8616
May 2024 | 2912697.8827 | 2990511.5 | -77813.6173 | -64888.4641
Jun 2024 | 2956322.7037 | 2993336.5 | -37013.7963 | -30865.6567
Jul 2024 | 2965065.1117 | 3033636.5 | -68571.3883 | -57181.4064
Aug 2024 | 2968773.224 | 3033636.5 | -64863.276 | -54089.2264
Sep 2024 | 2976788.9885 | 3047976.5 | -71187.5115 | -59399.9269
Oct 2024 | 3006084.6031 | 3051351.5 | -45266.8969 | -37771.3775
Nov 2024 | 3073845.5726 | 3143351.5 | -69505.9274 | -58222.9627
Dec 2024 | 3074382.7777 | 3143351.5 | -68968.7223 | -57772.9627
Jan 2025 | 4681513.3622 | 3152241.5 | 1529271.8622 | 841257.2658
Feb 2025 | 4681513.3622 | 3152241.5 | 1529271.8622 | 841257.2658
Mar 2025 | 4683086.7861 | 3152241.5 | 1530845.2861 | 842122.8112
Job Profitability Summary
| Beginning | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 785175 | 255000 | 470070 | 300000 | 100000 | 17655 | 0 | 2700 | 71000 | 20511.5 | 18400 | 0 | 0 | 200000 | 2825 | 40300 | 0 | 14340 | 3375 | 92000 | 0 | 8890 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -363786.0844 | -303971.8293 | -460991.6616 | -127512.1585 | -186894.9093 | -195630.1574 | -148346.9917 | -97102.0905 | -142102.0966 | -151062.4199 | -158664.6106 | -123871.7053 | -4994.4616 | -77813.6173 | -37013.7963 | -68571.3883 | -64863.276 | -71187.5115 | -45266.8969 | -69505.9274 | -68968.7223 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363786.0844 | 303971.8293 | 460991.6616 | 127512.1585 | 186894.9093 | 195630.1574 | 148346.9917 | 97102.0905 | 142102.0966 | 151062.4199 | 158664.6106 | 123871.7053 | 4994.4616 | 77813.6173 | 37013.7963 | 68571.3883 | 64863.276 | 71187.5115 | 45266.8969 | 69505.9274 | 68968.7223 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 864.38 | 864.38 | 13094.88 | 25313.3036 | 119694.1582 | 95854.276 | -304357.6377 | -251756.8882 | -381804.5458 | -105608.6819 | -155850.9172 | -163135.2056 | -123705.9628 | -80973.0448 | -118498.3698 | -125970.3476 | -132309.784 | -103296.1194 | -4164.8616 | -64888.4641 | -30865.6567 | -57181.4064 | -54089.2264 | -59399.9269 | -37771.3775 | -58222.9627 | -57772.9627 | 841257.2658 | 841257.2658 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 864.38 | 0 | 12230.5 | 12218.4236 | 94380.8545 | 603639.3921 | 256696.1386 | 250880.0515 | 259275.7897 | 524663.1861 | 47668.0291 | 7438.1455 | 39429.2427 | 44984.4373 | 21681.2909 | 9632.48 | 9004.25 | 29013.6645 | 99131.2579 | 106055.5973 | 36378.5636 | 7290.2591 | 3092.18 | 8229.25 | 24444.7 | 66543.1745 | 450 | 0 | 0 | 865.5455 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 864.38 | 864.38 | 13094.88 | 25313.3036 | 119694.1582 | 95854.276 | -304357.6377 | -251756.8882 | -381804.5458 | -105608.6819 | -155850.9172 | -163135.2056 | -123705.9628 | -80973.0448 | -118498.3698 | -125970.3476 | -132309.784 | -103296.1194 | -4164.8616 | -64888.4641 | -30865.6567 | -57181.4064 | -54089.2264 | -59399.9269 | -37771.3775 | -58222.9627 | -57772.9627 | 841257.2658 | 841257.2658 | 842122.8112 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627479.2743 | 656908.0523 | 198279.302 | 389323.4472 | 248467.3222 | 97910.2643 | 14722.4339 | 0 | 2251.5192 | 59206.6159 | 17104.4578 | 15343.6864 | 0 | -4.2655e-10 | 166779.1998 | 2355.7562 | 33606.0088 | -3.5652e-10 | 13539.9505 | 2816.1506 | 86994.7598 | -2.9831e-10 | -899030.2285 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0.02722% | 0.02722% | 0.4124% | 0.7973% | 3.77% | 22.78% | 30.87% | 38.11% | 46.13% | 62.37% | 54.06% | 54.26% | 55.29% | 56.47% | 57.04% | 57.29% | 57.52% | 58.28% | 60.88% | 63.66% | 64.62% | 64.81% | 64.89% | 64.86% | 65.5% | 65.66% | 65.67% | 100% | 100% | 100% | 100%

## J-1444
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Forte Group Pty Ltd |  |  |  |  | Steel | 40889.2136 | 35204.0298 | 53637.9 | 0
Estimate Code |  | E00010294 |  |  |  |  | Bolts | 2299.968 | 0 | 939.3818 | 0
Contract Code |  | J-1444 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 240 High Street, Thomastown- Level 5 |  |  |  |  | Labour | 17356.8715 | 0 | 11248.84 | 977.76
Customer |  | Forte Group Pty Ltd |  |  |  |  | Processing | 7578.9875 | 0 | 19878.6591 | 0
Start Date |  | 26 Jan 2022 |  |  |  |  | Rigging | 32999.582 | 9555 | 23075 | 0
Completion Date |  | 27 Jul 2021 |  |  |  |  | Freight | 4339.9866 | 0 | 1794.4 | 0
Budgeted Revenue |  | 130000 |  |  |  |  | Shop Drawings | 3003.5957 | 0 | 3000 | 0
Budgeted Job Expenditure |  | 109520.8714 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.75% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 18.6117 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 15.6174 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 13.46% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 198.22 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 465.2928 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 389.1523 | 0 | 0 | 0
[7 empty] | OH & Profit | 20479.1303 | 3520.97 | 0 | 0
[7 empty] | Total | 130000.0005 | 48279.9998 | 113574.1809 | 977.76
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 130000 | 130000 | 109520.8713 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Jan 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Feb 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Mar 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Apr 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
May 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Jun 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Jul 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Aug 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Sep 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Oct 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Nov 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Dec 2022 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Jan 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Feb 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Mar 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 130000 | 0 | 109520.8713 | 20479.1287 | 15.75% | 0 | 0 | 13447.3 | 13447.3 | 12.28%
Sep 2024 | 7600 | 137600 | 6642 | 116162.8713 | 21437.1287 | 15.58% | 7600 | 7600 | 31257.0091 | 44704.3091 | 38.48%
Oct 2024 | 565 | 138165 | 565 | 116727.8713 | 21437.1287 | 15.52% | 565 | 8165 | 19598.5736 | 64302.8827 | 55.09%
Nov 2024 | 13130 | 151295 | 12780 | 129507.8713 | 21787.1287 | 14.4% | 78130 | 86295 | 18733.3855 | 83036.2682 | 64.12%
Dec 2024 | 15485 | 166780 | 13517.0298 | 143024.9011 | 23755.0989 | 14.24% | 15485 | 101780 | 23162.0182 | 106198.2864 | 74.25%
Jan 2025 | 11500 | 178280 | 11255 | 154279.9011 | 24000.0989 | 13.46% | 11500 | 113280 | 3413.6545 | 109611.9409 | 71.05%
Feb 2025 | 0 | 178280 | 0 | 154279.9011 | 24000.0989 | 13.46% | 0 | 113280 | 526.75 | 110138.6909 | 71.39%
Mar 2025 | 0 | 178280 | 0 | 154279.9011 | 24000.0989 | 13.46% | 1000 | 114280 | 4413.25 | 114551.9409 | 74.25%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2022 | 0 | 0 | 0 | 0
Feb 2022 | 0 | 0 | 0 | 0
Mar 2022 | 0 | 0 | 0 | 0
Apr 2022 | 0 | 0 | 0 | 0
May 2022 | 0 | 0 | 0 | 0
Jun 2022 | 0 | 0 | 0 | 0
Jul 2022 | 0 | 0 | 0 | 0
Aug 2022 | 0 | 0 | 0 | 0
Sep 2022 | 0 | 0 | 0 | 0
Oct 2022 | 0 | 0 | 0 | 0
Nov 2022 | 0 | 0 | 0 | 0
Dec 2022 | 0 | 0 | 0 | 0
Jan 2023 | 0 | 0 | 0 | 0
Feb 2023 | 0 | 0 | 0 | 0
Mar 2023 | 0 | 0 | 0 | 0
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 15961.7886 | 0 | 15961.7886 | 13447.3
Sep 2024 | 52954.2087 | 7600 | 45354.2087 | 38288.3365
Oct 2024 | 76112.1375 | 8165 | 67947.1375 | 57404.7315
Nov 2024 | 97005.4721 | 86295 | 10710.4721 | 9168.1182
Dec 2024 | 123836.8288 | 101780 | 22056.8288 | 18915.1922
Jan 2025 | 126663.4 | 113280 | 13383.4 | 11581.7233
Feb 2025 | 127272.0923 | 113280 | 13992.0923 | 12108.4733
Mar 2025 | 132371.8765 | 114280 | 18091.8765 | 15656.3435
Job Profitability Summary
| Beginning | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7600 | 565 | 78130 | 15485 | 11500 | 0 | 1000 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13447.3 | 38288.3365 | 57404.7315 | 9168.1182 | 18915.1922 | 11581.7233 | 12108.4733 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13447.3 | 31257.0091 | 19598.5736 | 18733.3855 | 23162.0182 | 3413.6545 | 526.75 | 4413.25 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13447.3 | 38288.3365 | 57404.7315 | 9168.1182 | 18915.1922 | 11581.7233 | 12108.4733 | 15656.3435 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6415.9725 | 482.1787 | 66969.9988 | 13414.9441 | 10747.1235 | 0 | 865.3797 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.28% | 38.48% | 55.09% | 64.12% | 74.25% | 71.05% | 71.39% | 74.25% | 74.25%

## J-1460
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Tilt Construct Pty Ltd |  |  |  |  | Steel | 161152.6316 | 0 | 138835.2891 | 0
Estimate Code |  | E00010453 |  |  |  |  | Bolts | 4441.7783 | 0 | 7286.3909 | 0
Contract Code |  | J-1460 |  |  |  |  | Purlin | 117052.9849 | 0 | 72680.5091 | 0
Contract Name |  | Lot 6 & 7, 36-40 Taryn Drive, Epping |  |  |  |  | Labour | 26528.3785 | 0 | 24015.43 | 11866
Customer |  | Tilt Construct Pty Ltd |  |  |  |  | Processing | 25306.0928 | 0 | 24126.3191 | 0
Start Date |  | 7 Mar 2022 |  |  |  |  | Rigging | 73833.0723 | 0 | 91470.3636 | 0
Completion Date |  | 6 Sep 2021 |  |  |  |  | Freight | 3364.0776 | 0 | 772.7636 | 0
Budgeted Revenue |  | 499999.98 |  |  |  |  | Shop Drawings | 9160.0508 | 0 | 6300 | 0
Budgeted Job Expenditure |  | 420839.0597 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.83% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 69.7994 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 67.5745 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 24.53% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 79160.9341 | 0 | 0 | 43485.99
[7 empty] | Total | 500000.001 | 0 | 365487.0655 | 55351.99
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 499999.99 | 499999.99 | 420839.0597 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Mar 2022 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Apr 2022 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
May 2022 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Jun 2022 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Jul 2022 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Aug 2022 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Sep 2022 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Oct 2022 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Nov 2022 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Dec 2022 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Jan 2023 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Feb 2023 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Mar 2023 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 7238.8 | 7238.8 | 1.72%
Jun 2023 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 0 | 103676.5924 | 110915.3924 | 26.36%
Jul 2023 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 100000 | 100000 | 48626.7236 | 159542.1161 | 37.91%
Aug 2023 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 100000 | 75819.2627 | 235361.3788 | 55.93%
Sep 2023 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 100000 | 25349.9897 | 260711.3685 | 61.95%
Oct 2023 | 0 | 499999.99 | 0 | 420839.0597 | 79160.9303 | 15.83% | 0 | 100000 | 64862.6745 | 325574.043 | 77.36%
Nov 2023 | 0 | 499999.99 | -125000 | 295839.0597 | 204160.9303 | 40.83% | 50000 | 150000 | -29378.88 | 296195.163 | 100.1%
Dec 2023 | 0 | 499999.99 | 30121.23 | 325960.2897 | 174039.7003 | 34.81% | 0 | 150000 | 30853.1273 | 327048.2903 | 100.3%
Jan 2024 | 0 | 499999.99 | 0 | 325960.2897 | 174039.7003 | 34.81% | 150000 | 300000 | 0 | 327048.2903 | 100.3%
Feb 2024 | 0 | 499999.99 | 19122.77 | 345083.0597 | 154916.9303 | 30.98% | 0 | 300000 | 0 | 327048.2903 | 94.77%
Mar 2024 | 0 | 499999.99 | 16353.87 | 361436.9297 | 138563.0603 | 27.71% | 110000 | 410000 | 34388.6364 | 361436.9267 | 100%
Apr 2024 | 0 | 499999.99 | 0 | 361436.9297 | 138563.0603 | 27.71% | 0 | 410000 | 0 | 361436.9267 | 100%
May 2024 | 0 | 499999.99 | 0 | 361436.9297 | 138563.0603 | 27.71% | 0 | 410000 | 0 | 361436.9267 | 100%
Jun 2024 | 0 | 499999.99 | 0 | 361436.9297 | 138563.0603 | 27.71% | 0 | 410000 | 4863.1182 | 366300.0448 | 101.3%
Jul 2024 | 0 | 499999.99 | 0 | 361436.9297 | 138563.0603 | 27.71% | 0 | 410000 | 6726.6636 | 373026.7085 | 103.2%
Aug 2024 | 0 | 499999.99 | 0 | 361436.9297 | 138563.0603 | 27.71% | 0 | 410000 | 0 | 373026.7085 | 103.2%
Sep 2024 | 0 | 499999.99 | 0 | 361436.9297 | 138563.0603 | 27.71% | 0 | 410000 | 4190 | 377216.7085 | 104.4%
Oct 2024 | 0 | 499999.99 | 0 | 361436.9297 | 138563.0603 | 27.71% | 0 | 410000 | 136.3636 | 377353.0721 | 104.4%
Nov 2024 | 0 | 499999.99 | 0 | 361436.9297 | 138563.0603 | 27.71% | 0 | 410000 | 0 | 377353.0721 | 104.4%
Dec 2024 | 0 | 499999.99 | 15916.14 | 377353.0697 | 122646.9203 | 24.53% | 0 | 410000 | 0 | 377353.0721 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2022 | 0 | 0 | 0 | 0
Apr 2022 | 0 | 0 | 0 | 0
May 2022 | 0 | 0 | 0 | 0
Jun 2022 | 0 | 0 | 0 | 0
Jul 2022 | 0 | 0 | 0 | 0
Aug 2022 | 0 | 0 | 0 | 0
Sep 2022 | 0 | 0 | 0 | 0
Oct 2022 | 0 | 0 | 0 | 0
Nov 2022 | 0 | 0 | 0 | 0
Dec 2022 | 0 | 0 | 0 | 0
Jan 2023 | 0 | 0 | 0 | 0
Feb 2023 | 0 | 0 | 0 | 0
Mar 2023 | 0 | 0 | 0 | 0
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 8600.4373 | 0 | 8600.4373 | 7238.8
Jun 2023 | 131778.8685 | 0 | 131778.8685 | 110915.3924
Jul 2023 | 189552.4063 | 100000 | 89552.4063 | 75374.3024
Aug 2023 | 279633.4711 | 100000 | 179633.4711 | 151193.5652
Sep 2023 | 309751.8603 | 100000 | 209751.8603 | 176543.5549
Oct 2023 | 386815.374 | 100000 | 286815.374 | 241406.2294
Nov 2023 | 500601.8431 | 150000 | 350601.8431 | 207443.4433
Dec 2023 | 501668.9059 | 150000 | 351668.9059 | 229260.2014
Jan 2024 | 501668.9059 | 300000 | 201668.9059 | 131472.1126
Feb 2024 | 473868.9347 | 300000 | 173868.9347 | 119998.4503
Mar 2024 | 499999.9858 | 410000 | 89999.9858 | 65058.6384
Apr 2024 | 499999.9858 | 410000 | 89999.9858 | 65058.6384
May 2024 | 499999.9858 | 410000 | 89999.9858 | 65058.6384
Jun 2024 | 506727.464 | 410000 | 96727.464 | 69921.7566
Jul 2024 | 516032.9097 | 410000 | 106032.9097 | 76648.4202
Aug 2024 | 516032.9097 | 410000 | 106032.9097 | 76648.4202
Sep 2024 | 521829.2183 | 410000 | 111829.2183 | 80838.4202
Oct 2024 | 522017.8592 | 410000 | 112017.8592 | 80974.7838
Nov 2024 | 522017.8592 | 410000 | 112017.8592 | 80974.7838
Dec 2024 | 499999.9932 | 410000 | 89999.9932 | 67923.5488
Job Profitability Summary
| Beginning | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 50000 | 0 | 150000 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7238.8 | 110915.3924 | 75374.3024 | 151193.5652 | 176543.5549 | 241406.2294 | 207443.4433 | 229260.2014 | 131472.1126 | 119998.4503 | 65058.6384 | 65058.6384 | 65058.6384 | 69921.7566 | 76648.4202 | 76648.4202 | 80838.4202 | 80974.7838 | 80974.7838 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7238.8 | 103676.5924 | 48626.7236 | 75819.2627 | 25349.9897 | 64862.6745 | -29378.88 | 30853.1273 | 0 | 0 | 34388.6364 | 0 | 0 | 4863.1182 | 6726.6636 | 0 | 4190 | 136.3636 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7238.8 | 110915.3924 | 75374.3024 | 151193.5652 | 176543.5549 | 241406.2294 | 207443.4433 | 229260.2014 | 131472.1126 | 119998.4503 | 65058.6384 | 65058.6384 | 65058.6384 | 69921.7566 | 76648.4202 | 76648.4202 | 80838.4202 | 80974.7838 | 80974.7838 | 67923.5488 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84167.8136 | 0 | 0 | 0 | 4583.9061 | 9036.3692 | 97788.0889 | 11473.6622 | 89328.4483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13051.2351 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.72% | 26.36% | 37.91% | 55.93% | 61.95% | 77.36% | 100.1% | 100.3% | 100.3% | 94.77% | 100% | 100% | 100% | 101.3% | 103.2% | 103.2% | 104.4% | 104.4% | 104.4% | 100% | 100%

## J-1544
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Maddox 27 to 28 Pty Ltd |  |  |  |  | Steel | 74764.5817 | 0 | 0 | 0
Estimate Code |  | E00011339 |  |  |  |  | Bolts | 3945.1946 | 0 | 0 | 0
Contract Code |  | J-1544 |  |  |  |  | Purlin | 53215.0034 | 0 | 0 | 0
Contract Name |  | 42-44 Robbins Circuit, Williamstown |  |  |  |  | Labour | 28721.7615 | 0 | 0 | 0
Customer |  | Maddox 27 to 28 Pty Ltd |  |  |  |  | Processing | 13321.8828 | 0 | 86.25 | 0
Start Date |  | 4 Oct 2022 |  |  |  |  | Rigging | 40415.4141 | 0 | 0 | 0
Completion Date |  | 8 Jun 2022 |  |  |  |  | Freight | 2979.8367 | 0 | 0 | 0
Budgeted Revenue |  | 295000.01 |  |  |  |  | Shop Drawings | 4498.9815 | 0 | 0 | 0
Budgeted Job Expenditure |  | 232031.4404 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 21.35% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 30.998 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 3435 | 0 | 0 | 0
Current GP% |  | 21.35% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1387.7925 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 1241.1 | 0 | 0 | 0
[7 empty] | Other Materials | 3174.9489 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 929.9387 | 0 | 0 | 0
[7 empty] | OH & Profit | 62968.5644 | 0 | 0 | 0
[7 empty] | Total | 295000.0006 | 0 | 86.25 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 295000 | 295000 | 232031.4404 | 232031.4404 | 62968.5596 | 21.35% | 0 | 0 | 0 | 0 | 0%
Sep 2022 | 0 | 295000 | 0 | 232031.4404 | 62968.5596 | 21.35% | 0 | 0 | 86.25 | 86.25 | 0.03717%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2022 | 109.6565 | 0 | 109.6565 | 86.25
Job Profitability Summary
| Beginning | Sep 2022 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 86.25 | #VALUE!
Closing WIP | Difference (GP Exc) | 86.25 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0.03717% | 0.03717%

## J-1609
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Zonzo |  |  |  |  | Steel | 23634.5212 | 0 | 0 | 0
Estimate Code |  | E00011809 |  |  |  |  | Bolts | 1571.4342 | 0 | 0 | 0
Contract Code |  | J-1609 |  |  |  |  | Purlin | 3069.2791 | 0 | 0 | 0
Contract Name |  | 997 Healesville- Yarra Glen Road, Yarra Glen |  |  |  |  | Labour | 11451.6294 | 0 | 0 | 0
Customer |  | Zonzo |  |  |  |  | Processing | 4481.4461 | 0 | 0 | 0
Start Date |  | 9 Feb 2023 |  |  |  |  | Rigging | 15135.5273 | 0 | 0 | 0
Completion Date |  | 19 Oct 2022 |  |  |  |  | Freight | 1173.3347 | 0 | 0 | 0
Budgeted Revenue |  | 87999.99 |  |  |  |  | Shop Drawings | 2525.0049 | 0 | 0 | 0
Budgeted Job Expenditure |  | 65467.2637 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 25.61% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 8.4167 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 25.61% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1662.17 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 510.4171 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 252.5005 | 0 | 0 | 0
[7 empty] | OH & Profit | 22532.736 | 0 | 0 | 0
[7 empty] | Total | 88000.0005 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 88000 | 88000 | 65467.2637 | 65467.2637 | 22532.7363 | 25.61% | 0 | 0 | 0 | 0 | 0%
Nov 2022 | 0 | 88000 | 0 | 65467.2637 | 22532.7363 | 25.61% | 17600 | 17600 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2022 | 0 | 17600 | -17600 | -13093.4528
Job Profitability Summary
| Beginning | Nov 2022 | Total
Sales | 0 | 17600 | #VALUE!
Less Current Period Overbills | 0 | -17600 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | -13093.4528 | 0
Total Costruction Cost | #VALUE! | 13093.4528 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-1613
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Grow Constructions |  |  |  |  | Steel | 8000 | 0 | 0 | 0
Estimate Code |  | E00011909 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1613 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Steel |  |  |  |  | Labour | 4000 | 0 | 0 | 4000
Customer |  | Grow Constructions |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 4300 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 15000 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 12000 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 20% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 3000 | 0 | 0 | 0
[7 empty] | Total | 15000 | 0 | 4300 | 4000
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 15000 | 15000 | 12000 | 12000 | 3000 | 20% | 0 | 0 | 0 | 0 | 0%
Nov 2022 | 0 | 15000 | 0 | 12000 | 3000 | 20% | 0 | 0 | 0 | 0 | 0%
Dec 2022 | 0 | 15000 | 0 | 12000 | 3000 | 20% | 0 | 0 | 8300 | 8300 | 69.17%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2022 | 0 | 0 | 0 | 0
Dec 2022 | 10375 | 0 | 10375 | 8300
Job Profitability Summary
| Beginning | Nov 2022 | Dec 2022 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 8300 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 8300 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 69.17% | 69.17%

## J-1700
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Kiel & Co |  |  |  |  | Steel | 54267.3116 | 0 | 39600.9909 | 0
Estimate Code |  | E00012152 |  |  |  |  | Bolts | 7173.1709 | 0 | 4325.5091 | 0
Contract Code |  | J-1700 |  |  |  |  | Purlin | 56061.8612 | 0 | 55915.1455 | 0
Contract Name |  | Lot 425, 501-502 (18-22) Castle Drive, Torquay |  |  |  |  | Labour | 24452.2779 | 0 | 13463.69 | 11392
Customer |  | Kiel & Co |  |  |  |  | Processing | 13062.4287 | 0 | 12886.25 | 0
Start Date |  | 1 May 2023 |  |  |  |  | Rigging | 96704.3281 | 0 | 95117.5 | 0
Completion Date |  | 16 Feb 2023 |  |  |  |  | Freight | 3123.0476 | 0 | 2195.7 | 0
Budgeted Revenue |  | 324999.99 |  |  |  |  | Shop Drawings | 13536.5 | 0 | 11000 | 0
Budgeted Job Expenditure |  | 268580.9234 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.36% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 32.7881 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 29.7692 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 24.34% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 200 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 56419.0721 | 0 | 0 | 22684.14
[7 empty] | Total | 324999.9982 | 0 | 234504.7855 | 34076.14
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 325000 | 325000 | 268580.9234 | 268580.9234 | 56419.0766 | 17.36% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 65000 | 65000 | 4200 | 4200 | 1.564%
Sep 2023 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 65000 | 0 | 4200 | 1.564%
Oct 2023 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 195000 | 260000 | 124970.6273 | 129170.6273 | 48.09%
Nov 2023 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 42038.53 | 171209.1573 | 63.75%
Dec 2023 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 42915.7 | 214124.8573 | 79.72%
Jan 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 0 | 214124.8573 | 79.72%
Feb 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 0 | 214124.8573 | 79.72%
Mar 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 500 | 214624.8573 | 79.91%
Apr 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 6095 | 220719.8573 | 82.18%
May 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 969.2427 | 221689.1 | 82.54%
Jun 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 0 | 221689.1 | 82.54%
Jul 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 690 | 222379.1 | 82.8%
Aug 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 0 | 222379.1 | 82.8%
Sep 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 0 | 222379.1 | 82.8%
Oct 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 9345.1855 | 231724.2855 | 86.28%
Nov 2024 | 0 | 325000 | 0 | 268580.9234 | 56419.0766 | 17.36% | 0 | 260000 | 14000 | 245724.2855 | 91.49%
Dec 2024 | 0 | 325000 | -22684.14 | 245896.7834 | 79103.2166 | 24.34% | 0 | 260000 | 0 | 245724.2855 | 99.93%
Jan 2025 | 0 | 325000 | 0 | 245896.7834 | 79103.2166 | 24.34% | 0 | 260000 | 172.5 | 245896.7855 | 100%
Feb 2025 | 0 | 325000 | 0 | 245896.7834 | 79103.2166 | 24.34% | 65000 | 325000 | 0 | 245896.7855 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 5082.2671 | 65000 | -59917.7329 | -49516.1847
Sep 2023 | 5082.2671 | 65000 | -59917.7329 | -49516.1847
Oct 2023 | 156304.6747 | 260000 | -103695.3253 | -85694.1115
Nov 2023 | 207173.9698 | 260000 | -52826.0302 | -43655.5815
Dec 2023 | 259104.6964 | 260000 | -895.3036 | -739.8815
Jan 2024 | 259104.6964 | 260000 | -895.3036 | -739.8815
Feb 2024 | 259104.6964 | 260000 | -895.3036 | -739.8815
Mar 2024 | 259709.7282 | 260000 | -290.2718 | -239.8815
Apr 2024 | 267085.0658 | 260000 | 7085.0658 | 5855.1185
May 2024 | 268257.9112 | 260000 | 8257.9112 | 6824.3613
Jun 2024 | 268257.9112 | 260000 | 8257.9112 | 6824.3613
Jul 2024 | 269092.8551 | 260000 | 9092.8551 | 7514.3613
Aug 2024 | 269092.8551 | 260000 | 9092.8551 | 7514.3613
Sep 2024 | 269092.8551 | 260000 | 9092.8551 | 7514.3613
Oct 2024 | 280401.1238 | 260000 | 20401.1238 | 16859.5467
Nov 2024 | 297342.0143 | 260000 | 37342.0143 | 30859.5467
Dec 2024 | 324772.0107 | 260000 | 64772.0107 | 49006.8587
Jan 2025 | 325000.0027 | 260000 | 65000.0027 | 49179.3587
Feb 2025 | 325000.0027 | 325000 | 0.0026758 | 0.0020245
Job Profitability Summary
| Beginning | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 65000 | 0 | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | -59917.7329 | -59917.7329 | -103695.3253 | -52826.0302 | -895.3036 | -895.3036 | -895.3036 | -290.2718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 59917.7329 | 59917.7329 | 103695.3253 | 52826.0302 | 895.3036 | 895.3036 | 895.3036 | 290.2718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | -49516.1847 | -49516.1847 | -85694.1115 | -43655.5815 | -739.8815 | -739.8815 | -739.8815 | -239.8815 | 5855.1185 | 6824.3613 | 6824.3613 | 7514.3613 | 7514.3613 | 7514.3613 | 16859.5467 | 30859.5467 | 49006.8587 | 49179.3587 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 124970.6273 | 42038.53 | 42915.7 | 0 | 0 | 500 | 6095 | 969.2427 | 0 | 690 | 0 | 0 | 9345.1855 | 14000 | 0 | 172.5 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | -49516.1847 | -49516.1847 | -85694.1115 | -43655.5815 | -739.8815 | -739.8815 | -739.8815 | -239.8815 | 5855.1185 | 6824.3613 | 6824.3613 | 7514.3613 | 7514.3613 | 7514.3613 | 16859.5467 | 30859.5467 | 49006.8587 | 49179.3587 | 0.0020245 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 53716.1847 | 0 | 161148.5541 | 0 | -3.1832e-12 | 0 | 0 | 2.0975e-11 | 0 | -3.3651e-11 | 0 | 0 | 0 | 0 | 0 | 0 | -18147.312 | 0 | 49179.3567 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 1.564% | 1.564% | 48.09% | 63.75% | 79.72% | 79.72% | 79.72% | 79.91% | 82.18% | 82.54% | 82.54% | 82.8% | 82.8% | 82.8% | 86.28% | 91.49% | 99.93% | 100% | 100% | 100%

## J-1718
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Monde Construction & Refrigeration PtyLtd |  |  |  |  | Steel | 154064.2651 | 0 | 52.1364 | 0
Estimate Code |  | E00011537 |  |  |  |  | Bolts | 6938.1572 | 0 | 0 | 0
Contract Code |  | J-1718 |  |  |  |  | Purlin | 14325.0219 | 0 | 1427.4 | 0
Contract Name |  | 572 Stockinbingal Road, Coottamudra- Link Building |  |  |  |  | Labour | 87071.6278 | 0 | 0 | 0
Customer |  | Monde Construction & Refrigeration PtyLtd |  |  |  |  | Processing | 24049.0107 | 0 | 690 | 0
Start Date |  | 16 Nov 2022 |  |  |  |  | Rigging | 111605.9062 | 21600 | 68100 | 0
Completion Date |  | 5 Aug 2022 |  |  |  |  | Freight | 4861.1274 | 0 | 0 | 0
Budgeted Revenue |  | 568000.03 |  |  |  |  | Shop Drawings | 16354.2275 | 0 | 0 | 0
Budgeted Job Expenditure |  | 429640.3862 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 24.36% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 54.5141 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 23.47% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 7372.766 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1362.8523 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1635.4227 | 0 | 0 | 0
[7 empty] | OH & Profit | 138359.6199 | 0 | 0 | 0
[7 empty] | Total | 568000.0049 | 21600 | 70269.5364 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 568000.01 | 568000.01 | 429640.3862 | 429640.3862 | 138359.6238 | 24.36% | 0 | 0 | 0 | 0 | 0%
Nov 2022 | 0 | 568000.01 | 0 | 429640.3862 | 138359.6238 | 24.36% | 0 | 0 | 0 | 0 | 0%
Dec 2022 | 0 | 568000.01 | 0 | 429640.3862 | 138359.6238 | 24.36% | 0 | 0 | 0 | 0 | 0%
Jan 2023 | 0 | 568000.01 | 0 | 429640.3862 | 138359.6238 | 24.36% | 0 | 0 | 0 | 0 | 0%
Feb 2023 | 0 | 568000.01 | 0 | 429640.3862 | 138359.6238 | 24.36% | 0 | 0 | 0 | 0 | 0%
Mar 2023 | 0 | 568000.01 | 0 | 429640.3862 | 138359.6238 | 24.36% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 568000.01 | 0 | 429640.3862 | 138359.6238 | 24.36% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 568000.01 | 0 | 429640.3862 | 138359.6238 | 24.36% | 46500 | 46500 | 47927.4 | 47927.4 | 11.16%
Jun 2023 | 0 | 568000.01 | 0 | 429640.3862 | 138359.6238 | 24.36% | 0 | 46500 | 0 | 47927.4 | 11.16%
Jul 2023 | 21600 | 589600.01 | 21600 | 451240.3862 | 138359.6238 | 23.47% | 21600 | 68100 | 21600 | 69527.4 | 15.41%
Aug 2023 | 0 | 589600.01 | 0 | 451240.3862 | 138359.6238 | 23.47% | 0 | 68100 | 0 | 69527.4 | 15.41%
Sep 2023 | 0 | 589600.01 | 0 | 451240.3862 | 138359.6238 | 23.47% | 0 | 68100 | 0 | 69527.4 | 15.41%
Oct 2023 | 0 | 589600.01 | 0 | 451240.3862 | 138359.6238 | 23.47% | 0 | 68100 | 52.1364 | 69579.5364 | 15.42%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2022 | 0 | 0 | 0 | 0
Dec 2022 | 0 | 0 | 0 | 0
Jan 2023 | 0 | 0 | 0 | 0
Feb 2023 | 0 | 0 | 0 | 0
Mar 2023 | 0 | 0 | 0 | 0
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 63361.7429 | 46500 | 16861.7429 | 12754.376
Jun 2023 | 63361.7429 | 46500 | 16861.7429 | 12754.376
Jul 2023 | 90845.9371 | 68100 | 22745.9371 | 17408.2179
Aug 2023 | 90845.9371 | 68100 | 22745.9371 | 17408.2179
Sep 2023 | 90845.9371 | 68100 | 22745.9371 | 17408.2179
Oct 2023 | 90914.0595 | 68100 | 22814.0595 | 17460.3542
Job Profitability Summary
| Beginning | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46500 | 0 | 21600 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12754.376 | 12754.376 | 17408.2179 | 17408.2179 | 17408.2179 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47927.4 | 0 | 21600 | 0 | 0 | 52.1364 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 12754.376 | 12754.376 | 17408.2179 | 17408.2179 | 17408.2179 | 17460.3542 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 35173.024 | 0 | 16946.1582 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 11.16% | 11.16% | 15.41% | 15.41% | 15.41% | 15.42% | 15.42%

## J-1749
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Geelong |  |  |  |  | Steel | 0 | 0 | 26546.5818 | 0
Estimate Code |  | E00012570 |  |  |  |  | Bolts | 0 | 0 | 5398.2727 | 0
Contract Code |  | J-1749 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Geelong |  |  |  |  | Labour | 0 | 0 | 162991.17 | 0
Customer |  | Geelong |  |  |  |  | Processing | 0 | 0 | 6526.25 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 5165.5 | 0
Completion Date |  | 14 Jun 2023 |  |  |  |  | Freight | 0 | 0 | 4670.93 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 104399.01 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 318 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 316015.7145 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 55212.74 | 55212.74 | #DIV/0!
Jul 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 39643.63 | 94856.37 | #DIV/0!
Aug 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 31228.9745 | 126085.3445 | #DIV/0!
Sep 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 31804.2 | 157889.5445 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 1441.7182 | 159331.2627 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 11488.8909 | 170820.1536 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 11181.2645 | 182001.4182 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 13007.4782 | 195008.8964 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 23090.1736 | 218099.07 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 32115.7864 | 250214.8564 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 12846.1582 | 263061.0145 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 5744.3 | 268805.3145 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 3359.5091 | 272164.8236 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 4055.0518 | 276219.8755 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 5218.7845 | 281438.66 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 2328.8709 | 283767.5309 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 6350.3218 | 290117.8527 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 947.6545 | 291065.5073 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 8237.47 | 299302.9773 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 8938.9255 | 308241.9027 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 7466.0618 | 315707.9645 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jun 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 55212.74 | 39643.63 | 31228.9745 | 31804.2 | 1441.7182 | 11488.8909 | 11181.2645 | 13007.4782 | 23090.1736 | 32115.7864 | 12846.1582 | 5744.3 | 3359.5091 | 4055.0518 | 5218.7845 | 2328.8709 | 6350.3218 | 947.6545 | 8237.47 | 8938.9255 | 7466.0618 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-1751
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Design Electrical Pty Ltd |  |  |  |  | Steel | 2917.8556 | 0 | 0 | 0
Estimate Code |  | E00010535 |  |  |  |  | Bolts | 515.6517 | 0 | 0 | 0
Contract Code |  | J-1751 |  |  |  |  | Purlin | 2061.5026 | 0 | 0 | 0
Contract Name |  | 3 Dyson Court, Breakwater- Mezzanine @ Factory 8 |  |  |  |  | Labour | 1747.2575 | 0 | 0 | 0
Customer |  | Design Electrical Pty Ltd |  |  |  |  | Processing | 1013.7607 | 0 | 57.5 | 0
Start Date |  | 23 Mar 2022 |  |  |  |  | Rigging | 2007.2117 | 0 | 0 | 0
Completion Date |  | 29 Sep 2021 |  |  |  |  | Freight | 500.88 | 0 | 0 | 0
Budgeted Revenue |  | 24999.99 |  |  |  |  | Shop Drawings | 543.3153 | 0 | 0 | 0
Budgeted Job Expenditure |  | 19853.6952 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.59% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 1.8111 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 8167.95 | 0 | 0 | 0
Current GP% |  | 20.59% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 42.48 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 245.2763 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 90.5525 | 0 | 0 | 0
[7 empty] | OH & Profit | 5146.306 | 0 | 0 | 0
[7 empty] | Total | 24999.9999 | 0 | 57.5 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 25000 | 25000 | 19853.6952 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Mar 2022 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Apr 2022 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
May 2022 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Jun 2022 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Jul 2022 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Aug 2022 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Sep 2022 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Oct 2022 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Nov 2022 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Dec 2022 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Jan 2023 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Feb 2023 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Mar 2023 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 25000 | 0 | 19853.6952 | 5146.3048 | 20.59% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2022 | 0 | 0 | 0 | 0
Apr 2022 | 0 | 0 | 0 | 0
May 2022 | 0 | 0 | 0 | 0
Jun 2022 | 0 | 0 | 0 | 0
Jul 2022 | 0 | 0 | 0 | 0
Aug 2022 | 0 | 0 | 0 | 0
Sep 2022 | 0 | 0 | 0 | 0
Oct 2022 | 0 | 0 | 0 | 0
Nov 2022 | 0 | 0 | 0 | 0
Dec 2022 | 0 | 0 | 0 | 0
Jan 2023 | 0 | 0 | 0 | 0
Feb 2023 | 0 | 0 | 0 | 0
Mar 2023 | 0 | 0 | 0 | 0
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## J-1763
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Malibu Properties |  |  |  |  | Steel | 8205.1013 | 0 | 8185.0691 | 0
Estimate Code |  | E00012606 |  |  |  |  | Bolts | 388.997 | 0 | 399.0091 | 0
Contract Code |  | J-1763 |  |  |  |  | Purlin | 6696.2539 | 0 | 6601.1 | 0
Contract Name |  | 25 Carrick Drive, Tullamarine- Mezzanine |  |  |  |  | Labour | 1829.1253 | 0 | 1315.62 | 300
Customer |  | Malibu Properties |  |  |  |  | Processing | 1864.2403 | 0 | 1753.75 | 0
Start Date |  | 16 Aug 2023 |  |  |  |  | Rigging | 4201.1209 | 0 | 4000 | 0
Completion Date |  | 20 Jun 2023 |  |  |  |  | Freight | 802.2998 | 0 | 35 | 0
Budgeted Revenue |  | 29999.99 |  |  |  |  | Shop Drawings | 617.0026 | 0 | 700 | 0
Budgeted Job Expenditure |  | 24772.2431 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.43% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 3.0564 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 3.1034 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 22.37% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 76.4101 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 91.6921 | 0 | 0 | 0
[7 empty] | OH & Profit | 5227.757 | 0 | 0 | 1482.69
[7 empty] | Total | 30000.0002 | 0 | 22989.5482 | 1782.69
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 30000 | 30000 | 24772.2432 | 24772.2432 | 5227.7568 | 17.43% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 6000 | 6000 | 0 | 0 | 0%
Jul 2023 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 9421.0691 | 9421.0691 | 38.03%
Aug 2023 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 9494.7291 | 18915.7982 | 76.36%
Sep 2023 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 4373.75 | 23289.5482 | 94.01%
Oct 2023 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Nov 2023 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Dec 2023 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Jan 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Feb 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Mar 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Apr 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
May 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Jun 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Jul 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Aug 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Sep 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Oct 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Nov 2024 | 0 | 30000 | 0 | 24772.2432 | 5227.7568 | 17.43% | 0 | 6000 | 0 | 23289.5482 | 94.01%
Dec 2024 | 0 | 30000 | -4082.69 | 20689.5532 | 9310.4468 | 31.03% | 0 | 6000 | 0 | 23289.5482 | 112.6%
Jan 2025 | 0 | 30000 | 0 | 20689.5532 | 9310.4468 | 31.03% | 0 | 6000 | 0 | 23289.5482 | 112.6%
Feb 2025 | 0 | 30000 | 2600 | 23289.5532 | 6710.4468 | 22.37% | 24000 | 30000 | 0 | 23289.5482 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jun 2023 | 0 | 6000 | -6000 | -4954.4486
Jul 2023 | 11409.2241 | 6000 | 5409.2241 | 4466.6205
Aug 2023 | 22907.6528 | 6000 | 16907.6528 | 13961.3495
Sep 2023 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Oct 2023 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Nov 2023 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Dec 2023 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Jan 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Feb 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Mar 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Apr 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
May 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Jun 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Jul 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Aug 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Sep 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Oct 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Nov 2024 | 28204.4077 | 6000 | 22204.4077 | 18335.0995
Dec 2024 | 33770.0114 | 6000 | 27770.0114 | 19151.6375
Jan 2025 | 33770.0114 | 6000 | 27770.0114 | 19151.6375
Feb 2025 | 29999.9936 | 30000 | -0.0064126 | -0.0049782
Job Profitability Summary
| Beginning | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | #VALUE!
Less Current Period Overbills | 0 | -6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.0064126 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | -4954.4486 | 4466.6205 | 13961.3495 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 19151.6375 | 19151.6375 | 0
Construction Costs | 0 | 0 | 9421.0691 | 9494.7291 | 4373.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | -4954.4486 | 4466.6205 | 13961.3495 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 18335.0995 | 19151.6375 | 19151.6375 | -0.0049782 | 0
Total Costruction Cost | #VALUE! | 4954.4486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -816.538 | 0 | 19151.6425 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 38.03% | 76.36% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 112.6% | 112.6% | 100% | 100%

## J-1791
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | John Brincat JB Rigging |  |  |  |  | Steel | 0 | 0 | 39158.0391 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 1792.3727 | 0
Contract Code |  | J-1791 |  |  |  |  | Purlin | 0 | 0 | 21174.9182 | 0
Contract Name |  | 18 Hampden Road, Cranbourne West |  |  |  |  | Labour | 0 | 0 | 11508.81 | 1383
Customer |  | John Brincat JB Rigging |  |  |  |  | Processing | 0 | 0 | 8799.41 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 780.08 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 16.5535 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 612 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 83825.63 | 1383
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 48207.6758 | 48207.6758 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 18878.0309 | 67085.7067 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 2974.18 | 70059.8867 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 70059.8867 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 2399.6864 | 72459.573 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 72459.573 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 8549.8 | 81009.373 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 166.2636 | 81175.6367 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 3803 | 84978.6367 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 230 | 85208.6367 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 85208.6367 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 85208.6367 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 85208.6367 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 85208.6367 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 85208.6367 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 48207.6758 | 18878.0309 | 2974.18 | 0 | 2399.6864 | 0 | 8549.8 | 166.2636 | 3803 | 230 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-1800
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00014853 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1800 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Verandah Beams (Dominic Cullia) |  |  |  |  | Labour | 0 | 0 | 2728.06 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 0 | 0 | 2472.5 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 16 Dec 2024 |  |  |  |  | Freight | 0 | 0 | 348 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 5548.56 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 1265 | 1265 | #DIV/0!
Sep 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1265 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 2902.06 | 4167.06 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 174 | 4341.06 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 4341.06 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 4341.06 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 4341.06 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 1207.5 | 5548.56 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5548.56 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5548.56 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5548.56 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5548.56 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5548.56 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5548.56 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5548.56 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5548.56 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5548.56 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 1265 | 0 | 2902.06 | 174 | 0 | 0 | 0 | 1207.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-1804
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Bellafia Homes |  |  |  |  | Steel | 35528.7079 | 3000 | 38927.7927 | 0
Estimate Code |  | E00012492 |  |  |  |  | Bolts | 2101.6172 | 350 | 3148.4727 | 0
Contract Code |  | J-1804 |  |  |  |  | Purlin | 22931.0215 | 0 | 22924.1909 | 0
Contract Name |  | Lot 77 Literary Way (15 Robbins Court) Williamspoi |  |  |  |  | Labour | 14148.0049 | 1800 | 13338.12 | 5846
Customer |  | Bellafia Homes |  |  |  |  | Processing | 8130.4727 | 800 | 10077.83 | 0
Start Date |  | 18 Jul 2023 |  |  |  |  | Rigging | 28995.1895 | 5000 | 35900 | 0
Completion Date |  | 22 May 2023 |  |  |  |  | Freight | 621.0216 | 0 | 998.6636 | 0
Budgeted Revenue |  | 140000.01 |  |  |  |  | Shop Drawings | 2000.7291 | 1800 | 3800 | 0
Budgeted Job Expenditure |  | 114756.764 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 18.03% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 16.5127 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 18.3269 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 14.63% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 300 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 25243.2353 | 5250 | 0 | -7373.31
[7 empty] | Total | 139999.9997 | 18000 | 129115.07 | -1527.31
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 140000 | 140000 | 114756.764 | 114756.764 | 25243.236 | 18.03% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 0 | 0 | 1904.0833 | 1904.0833 | 1.659%
Sep 2023 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 0 | 0 | 594.5 | 2498.5833 | 2.177%
Oct 2023 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 0 | 0 | 5940 | 8438.5833 | 7.353%
Nov 2023 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 0 | 0 | 2671.0909 | 11109.6742 | 9.681%
Dec 2023 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 0 | 0 | 402.5 | 11512.1742 | 10.03%
Jan 2024 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 0 | 0 | 39541.9427 | 51054.117 | 44.49%
Feb 2024 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 64555 | 64555 | 2925.25 | 53979.367 | 47.04%
Mar 2024 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 64555 | 129110 | 51090.96 | 105070.327 | 91.56%
Apr 2024 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 0 | 129110 | 528.0182 | 105598.3452 | 92.02%
May 2024 | 0 | 140000 | 0 | 114756.764 | 25243.236 | 18.03% | 18000 | 147110 | 13155.3636 | 118753.7088 | 103.5%
Jun 2024 | 18000 | 158000 | 12750 | 127506.764 | 30493.236 | 19.3% | 0 | 147110 | 5210.36 | 123964.0688 | 97.22%
Jul 2024 | 0 | 158000 | 0 | 127506.764 | 30493.236 | 19.3% | 0 | 147110 | 100 | 124064.0688 | 97.3%
Aug 2024 | 0 | 158000 | 0 | 127506.764 | 30493.236 | 19.3% | 0 | 147110 | 10576.0045 | 134640.0733 | 105.6%
Sep 2024 | 0 | 158000 | 0 | 127506.764 | 30493.236 | 19.3% | 0 | 147110 | 240 | 134880.0733 | 105.8%
Oct 2024 | 0 | 158000 | 0 | 127506.764 | 30493.236 | 19.3% | 0 | 147110 | 0 | 134880.0733 | 105.8%
Nov 2024 | 0 | 158000 | 0 | 127506.764 | 30493.236 | 19.3% | 0 | 147110 | 0 | 134880.0733 | 105.8%
Dec 2024 | 0 | 158000 | 7373.31 | 134880.074 | 23119.926 | 14.63% | 0 | 147110 | 0 | 134880.0733 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 2322.9277 | 0 | 2322.9277 | 1904.0833
Sep 2023 | 3048.2009 | 0 | 3048.2009 | 2498.5833
Oct 2023 | 10294.8325 | 0 | 10294.8325 | 8438.5833
Nov 2023 | 13553.4877 | 0 | 13553.4877 | 11109.6742
Dec 2023 | 14044.5263 | 0 | 14044.5263 | 11512.1742
Jan 2024 | 62284.5759 | 0 | 62284.5759 | 51054.117
Feb 2024 | 65853.298 | 64555 | 1298.298 | 1064.2034
Mar 2024 | 128182.8213 | 129110 | -927.1787 | -760.0002
Apr 2024 | 128826.9886 | 129110 | -283.0114 | -231.982
May 2024 | 144876.1594 | 147110 | -2233.8406 | -1831.0594
Jun 2024 | 153610.0694 | 147110 | 6500.0694 | 5245.5875
Jul 2024 | 153733.9844 | 147110 | 6623.9844 | 5345.5875
Aug 2024 | 166839.2399 | 147110 | 19729.2399 | 15921.592
Sep 2024 | 167136.6359 | 147110 | 20026.6359 | 16161.592
Oct 2024 | 167136.6359 | 147110 | 20026.6359 | 16161.592
Nov 2024 | 167136.6359 | 147110 | 20026.6359 | 16161.592
Dec 2024 | 157999.9992 | 147110 | 10889.9992 | 9296.4804
Job Profitability Summary
| Beginning | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64555 | 64555 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -927.1787 | -283.0114 | -2233.8406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927.1787 | 283.0114 | 2233.8406 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 1904.0833 | 2498.5833 | 8438.5833 | 11109.6742 | 11512.1742 | 51054.117 | 1064.2034 | -760.0002 | -231.982 | -1831.0594 | 5245.5875 | 5345.5875 | 15921.592 | 16161.592 | 16161.592 | 16161.592 | 0
Construction Costs | 0 | 0 | 1904.0833 | 594.5 | 5940 | 2671.0909 | 402.5 | 39541.9427 | 2925.25 | 51090.96 | 528.0182 | 13155.3636 | 5210.36 | 100 | 10576.0045 | 240 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 1904.0833 | 2498.5833 | 8438.5833 | 11109.6742 | 11512.1742 | 51054.117 | 1064.2034 | -760.0002 | -231.982 | -1831.0594 | 5245.5875 | 5345.5875 | 15921.592 | 16161.592 | 16161.592 | 16161.592 | 9296.4804 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52915.1636 | 52915.1636 | 1.3017e-11 | 14754.4411 | -1866.2869 | 0 | 0 | 0 | 0 | 0 | 6865.1116 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 1.659% | 2.177% | 7.353% | 9.681% | 10.03% | 44.49% | 47.04% | 91.56% | 92.02% | 103.5% | 97.22% | 97.3% | 105.6% | 105.8% | 105.8% | 105.8% | 100% | 100%

## J-1829
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | The Ci Group |  |  |  |  | Steel | 40367.7912 | 3920 | 28146.4536 | 0
Estimate Code |  | E00012771 |  |  |  |  | Bolts | 1995.2954 | 0 | 396.3636 | 0
Contract Code |  | J-1829 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 210-216 Jumping Creek Road, Wonga Park |  |  |  |  | Labour | 16698.1378 | 0 | 10162.85 | 1000
Customer |  | The Ci Group |  |  |  |  | Processing | 8052.442 | 0 | 4384.08 | 0
Start Date |  | 18 Sep 2023 |  |  |  |  | Rigging | 26000 | 0 | 14509 | 0
Completion Date |  | 2 Aug 2023 |  |  |  |  | Freight | 1000 | 0 | 250 | 0
Budgeted Revenue |  | 132000.01 |  |  |  |  | Shop Drawings | 5487.0625 | 0 | 5451 | 0
Budgeted Job Expenditure |  | 102369.3531 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 22.45% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 15.6773 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 11.1488 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 22.36% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 2376.69 | 0 | 497.2545 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 391.933 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 29630.6533 | 980 | 0 | 0
[7 empty] | Total | 132000.0052 | 4900 | 63797.0018 | 1000
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 132000.01 | 132000.01 | 102369.3531 | 102369.3531 | 29630.6569 | 22.45% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 132000.01 | 0 | 102369.3531 | 29630.6569 | 22.45% | 26400 | 26400 | 0 | 0 | 0%
Sep 2023 | 0 | 132000.01 | 0 | 102369.3531 | 29630.6569 | 22.45% | 0 | 26400 | 17198.6509 | 17198.6509 | 16.8%
Oct 2023 | 0 | 132000.01 | 0 | 102369.3531 | 29630.6569 | 22.45% | 0 | 26400 | 4482.7845 | 21681.4355 | 21.18%
Nov 2023 | 0 | 132000.01 | 0 | 102369.3531 | 29630.6569 | 22.45% | 0 | 26400 | 0 | 21681.4355 | 21.18%
Dec 2023 | 0 | 132000.01 | 0 | 102369.3531 | 29630.6569 | 22.45% | 0 | 26400 | 0 | 21681.4355 | 21.18%
Jan 2024 | 0 | 132000.01 | 0 | 102369.3531 | 29630.6569 | 22.45% | 0 | 26400 | 460 | 22141.4355 | 21.63%
Feb 2024 | 0 | 132000.01 | 0 | 102369.3531 | 29630.6569 | 22.45% | 15000 | 41400 | 1778.79 | 23920.2255 | 23.37%
Mar 2024 | 0 | 132000.01 | 0 | 102369.3531 | 29630.6569 | 22.45% | 0 | 41400 | 2485 | 26405.2255 | 25.79%
Apr 2024 | 0 | 132000.01 | 0 | 102369.3531 | 29630.6569 | 22.45% | 0 | 41400 | 1338.5 | 27743.7255 | 27.1%
May 2024 | 0 | 132000.01 | 0 | 102369.3531 | 29630.6569 | 22.45% | 27500 | 68900 | 21372.4997 | 49116.2252 | 47.98%
Jun 2024 | 4900 | 136900.01 | 3920 | 106289.3531 | 30610.6569 | 22.36% | 4900 | 73800 | 15680.775 | 64797.0002 | 60.96%
Jul 2024 | 0 | 136900.01 | 0 | 106289.3531 | 30610.6569 | 22.36% | 0 | 73800 | 0 | 64797.0002 | 60.96%
Aug 2024 | 0 | 136900.01 | 0 | 106289.3531 | 30610.6569 | 22.36% | 0 | 73800 | 0 | 64797.0002 | 60.96%
Sep 2024 | 0 | 136900.01 | 0 | 106289.3531 | 30610.6569 | 22.36% | 27500 | 101300 | 0 | 64797.0002 | 60.96%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2023 | 0 | 26400 | -26400 | -20473.8691
Sep 2023 | 22176.7748 | 26400 | -4223.2252 | -3275.2182
Oct 2023 | 27957.0947 | 26400 | 1557.0947 | 1207.5664
Nov 2023 | 27957.0947 | 26400 | 1557.0947 | 1207.5664
Dec 2023 | 27957.0947 | 26400 | 1557.0947 | 1207.5664
Jan 2024 | 28550.241 | 26400 | 2150.241 | 1667.5664
Feb 2024 | 30843.8991 | 41400 | -10556.1009 | -8186.5238
Mar 2024 | 34048.1787 | 41400 | -7351.8213 | -5701.5238
Apr 2024 | 35774.1055 | 41400 | -5625.8945 | -4363.0238
May 2024 | 63332.8434 | 68900 | -5567.1566 | -4317.471
Jun 2024 | 83458.1236 | 73800 | 9658.1236 | 7498.5802
Jul 2024 | 83458.1236 | 73800 | 9658.1236 | 7498.5802
Aug 2024 | 83458.1236 | 73800 | 9658.1236 | 7498.5802
Sep 2024 | 83458.1236 | 101300 | -17841.8764 | -13852.457
Job Profitability Summary
| Beginning | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Total
Sales | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 27500 | 4900 | 0 | 0 | 27500 | #VALUE!
Less Current Period Overbills | 0 | -26400 | -4223.2252 | 0 | 0 | 0 | 0 | -10556.1009 | -7351.8213 | -5625.8945 | -5567.1566 | 0 | 0 | 0 | -17841.8764 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 26400 | 4223.2252 | 0 | 0 | 0 | 0 | 10556.1009 | 7351.8213 | 5625.8945 | 5567.1566 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | -20473.8691 | -3275.2182 | 1207.5664 | 1207.5664 | 1207.5664 | 1667.5664 | -8186.5238 | -5701.5238 | -4363.0238 | -4317.471 | 7498.5802 | 7498.5802 | 7498.5802 | 0
Construction Costs | 0 | 0 | 17198.6509 | 4482.7845 | 0 | 0 | 460 | 1778.79 | 2485 | 1338.5 | 21372.4997 | 15680.775 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | -20473.8691 | -3275.2182 | 1207.5664 | 1207.5664 | 1207.5664 | 1667.5664 | -8186.5238 | -5701.5238 | -4363.0238 | -4317.471 | 7498.5802 | 7498.5802 | 7498.5802 | -13852.457 | 0
Total Costruction Cost | #VALUE! | 20473.8691 | 0 | 0 | 0 | 0 | 0 | 11632.8802 | 0 | 0 | 21326.947 | 3864.7237 | 0 | 0 | 21351.0372 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 16.8% | 21.18% | 21.18% | 21.18% | 21.63% | 23.37% | 25.79% | 27.1% | 47.98% | 60.96% | 60.96% | 60.96% | 60.96% | 60.96%

## J-1847
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Albert Infelice |  |  |  |  | Steel | 17139.3725 | 0 | 13220.5018 | 1600
Estimate Code |  | E00012900 |  |  |  |  | Bolts | 824.166 | 0 | 244.6364 | 0
Contract Code |  | J-1847 |  |  |  |  | Purlin | 396.981 | 0 | 699.5909 | 0
Contract Name |  | 13 Yarra Braes Road Eltham |  |  |  |  | Labour | 5957.5294 | 0 | 7105.7191 | 0
Customer |  | Albert Infelice |  |  |  |  | Processing | 3326.0986 | 0 | 2012.5 | 0
Start Date |  | 1 Dec 2023 |  |  |  |  | Rigging | 10000 | 0 | 7455.9909 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 800 | 0 | 600 | 0
Budgeted Revenue |  | 54200.01 |  |  |  |  | Shop Drawings | 2266.4565 | 0 | 2266 | 0
Budgeted Job Expenditure |  | 41378.2444 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 23.66% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 6.6283 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 6.1796 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 23.66% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 505.75 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 161.8898 | 0 | 201.63 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 12821.7556 | 0 | 0 | 0
[7 empty] | Total | 54199.9994 | 0 | 33806.5691 | 1600
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 54200 | 54200 | 41378.2444 | 41378.2444 | 12821.7556 | 23.66% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 54200 | 0 | 41378.2444 | 12821.7556 | 23.66% | 10840 | 10840 | 0 | 0 | 0%
Oct 2023 | 0 | 54200 | 0 | 41378.2444 | 12821.7556 | 23.66% | 0 | 10840 | 0 | 0 | 0%
Nov 2023 | 0 | 54200 | 0 | 41378.2444 | 12821.7556 | 23.66% | 0 | 10840 | 0 | 0 | 0%
Dec 2023 | 0 | 54200 | 0 | 41378.2444 | 12821.7556 | 23.66% | 0 | 10840 | 3010.6 | 3010.6 | 7.276%
Jan 2024 | 0 | 54200 | 0 | 41378.2444 | 12821.7556 | 23.66% | 32520 | 43360 | 23739.54 | 26750.14 | 64.65%
Feb 2024 | 0 | 54200 | 0 | 41378.2444 | 12821.7556 | 23.66% | 0 | 43360 | 5632.3091 | 32382.4491 | 78.26%
Mar 2024 | 0 | 54200 | 0 | 41378.2444 | 12821.7556 | 23.66% | 0 | 43360 | 1424.12 | 33806.5691 | 81.7%
Apr 2024 | 0 | 54200 | 0 | 41378.2444 | 12821.7556 | 23.66% | 0 | 43360 | 1600 | 35406.5691 | 85.57%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2023 | 0 | 10840 | -10840 | -8275.6489
Oct 2023 | 0 | 10840 | -10840 | -8275.6489
Nov 2023 | 0 | 10840 | -10840 | -8275.6489
Dec 2023 | 3943.4858 | 10840 | -6896.5142 | -5265.0489
Jan 2024 | 35039.1277 | 43360 | -8320.8723 | -6352.4555
Feb 2024 | 42416.7039 | 43360 | -943.2961 | -720.1464
Mar 2024 | 44282.1118 | 43360 | 922.1118 | 703.9736
Apr 2024 | 46377.8991 | 43360 | 3017.8991 | 2303.9736
Job Profitability Summary
| Beginning | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | Total
Sales | 0 | 10840 | 0 | 0 | 0 | 32520 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | -10840 | -10840 | -10840 | -6896.5142 | -8320.8723 | -943.2961 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 10840 | 10840 | 10840 | 6896.5142 | 8320.8723 | 943.2961 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | -8275.6489 | -8275.6489 | -8275.6489 | -5265.0489 | -6352.4555 | -720.1464 | 703.9736 | 0
Construction Costs | 0 | 0 | 0 | 0 | 3010.6 | 23739.54 | 5632.3091 | 1424.12 | 1600 | #VALUE!
Closing WIP | Difference (GP Exc) | -8275.6489 | -8275.6489 | -8275.6489 | -5265.0489 | -6352.4555 | -720.1464 | 703.9736 | 2303.9736 | 0
Total Costruction Cost | #VALUE! | 8275.6489 | 0 | 0 | 0 | 24826.9466 | -5.2296e-12 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 7.276% | 64.65% | 78.26% | 81.7% | 85.57% | 85.57%

## J-1863
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Texco Construction Pty Ltd |  |  |  |  | Steel | 1440000.1866 | 12000 | 1375834.1682 | 0
Estimate Code |  | E00012952 |  |  |  |  | Bolts | 70000.3047 | 0 | 68708.1818 | 0
Contract Code |  | J-1863 |  |  |  |  | Purlin | 709999.9987 | 0 | 687295.9555 | 0
Contract Name |  | 15-33 Macedon Way, Melbourne Airport- WH 1 & 4 |  |  |  |  | Labour | 399414.3209 | 1000 | 290330.05 | 95199
Customer |  | Texco Construction Pty Ltd |  |  |  |  | Processing | 200000.0166 | 5000 | 227623.4373 | 0
Start Date |  | 7 Nov 2023 |  |  |  |  | Rigging | 840000 | 26000 | 782350.7727 | 0
Completion Date |  | 19 Sep 2023 |  |  |  |  | Freight | 25000 | 0 | 26968.2791 | 0
Budgeted Revenue |  | 4750000.02 |  |  |  |  | Shop Drawings | 80000 | 0 | 80000 | 0
Budgeted Job Expenditure |  | 3900414.8669 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.89% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 703.1245 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 508.6429 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 20.32% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 119999.984 | 0 | 101477.9364 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 10000 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 6000 | 0 | 3149 | 0
[7 empty] | OH & Profit | 849585.1787 | 31000 | 0 | 100000
[7 empty] | Total | 4749999.9902 | 75000 | 3643737.7809 | 195199
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 4750000.05 | 4750000.05 | 3900414.8669 | 3900414.8669 | 849585.1831 | 17.89% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 4750000.05 | 0 | 3900414.8669 | 849585.1831 | 17.89% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 4750000.05 | 0 | 3900414.8669 | 849585.1831 | 17.89% | 0 | 0 | 9946.07 | 9946.07 | 0.255%
Dec 2023 | 0 | 4750000.05 | 0 | 3900414.8669 | 849585.1831 | 17.89% | 0 | 0 | 223290.6218 | 233236.6918 | 5.98%
Jan 2024 | 0 | 4750000.05 | 0 | 3900414.8669 | 849585.1831 | 17.89% | 0 | 0 | 570297.7455 | 803534.4373 | 20.6%
Feb 2024 | 0 | 4750000.05 | 0 | 3900414.8669 | 849585.1831 | 17.89% | 1197000 | 1197000 | 687717.7794 | 1491252.2167 | 38.23%
Mar 2024 | 0 | 4750000.05 | 0 | 3900414.8669 | 849585.1831 | 17.89% | 1000000 | 2197000 | 395919.5836 | 1887171.8003 | 48.38%
Apr 2024 | 0 | 4750000.05 | 0 | 3900414.8669 | 849585.1831 | 17.89% | 0 | 2197000 | 54311.8218 | 1941483.6221 | 49.78%
May 2024 | 0 | 4750000.05 | 0 | 3900414.8669 | 849585.1831 | 17.89% | 15750 | 2212750 | 3695.9455 | 1945179.5676 | 49.87%
Jun 2024 | 0 | 4750000.05 | 0 | 3900414.8669 | 849585.1831 | 17.89% | 0 | 2212750 | 2005 | 1947184.5676 | 49.92%
Jul 2024 | 75000 | 4825000.05 | 44000 | 3944414.8669 | 880585.1831 | 18.25% | 12250 | 2225000 | 12552.5118 | 1959737.0794 | 49.68%
Aug 2024 | 0 | 4825000.05 | 0 | 3944414.8669 | 880585.1831 | 18.25% | 0 | 2225000 | 4902.2364 | 1964639.3158 | 49.81%
Sep 2024 | 0 | 4825000.05 | 0 | 3944414.8669 | 880585.1831 | 18.25% | 0 | 2225000 | 21730.71 | 1986370.0258 | 50.36%
Oct 2024 | 0 | 4825000.05 | 0 | 3944414.8669 | 880585.1831 | 18.25% | 0 | 2225000 | 85408.7 | 2071778.7258 | 52.52%
Nov 2024 | 0 | 4825000.05 | 0 | 3944414.8669 | 880585.1831 | 18.25% | 800000 | 3025000 | 890963.6273 | 2962742.353 | 75.11%
Dec 2024 | 0 | 4825000.05 | -100000 | 3844414.8669 | 980585.1831 | 20.32% | 1392000 | 4417000 | 583803.3464 | 3546545.6994 | 92.25%
Jan 2025 | 0 | 4825000.05 | 0 | 3844414.8669 | 980585.1831 | 20.32% | 241000 | 4658000 | 135958.9894 | 3682504.6888 | 95.79%
Feb 2025 | 0 | 4825000.05 | 0 | 3844414.8669 | 980585.1831 | 20.32% | 209000 | 4867000 | 50379 | 3732883.6888 | 97.1%
Mar 2025 | 0 | 4825000.05 | 0 | 3844414.8669 | 980585.1831 | 20.32% | 0 | 4867000 | 6053.0955 | 3738936.7842 | 97.26%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 12112.5149 | 0 | 12112.5149 | 9946.07
Dec 2023 | 284040.1177 | 0 | 284040.1177 | 233236.6918
Jan 2024 | 978559.6526 | 0 | 978559.6526 | 803534.4373
Feb 2024 | 1816075.5574 | 1197000 | 619075.5574 | 508347.6805
Mar 2024 | 2298234.0217 | 2197000 | 101234.0217 | 83127.3008
Apr 2024 | 2364376.0002 | 2197000 | 167376.0002 | 137439.1227
May 2024 | 2368876.9935 | 2212750 | 156126.9935 | 128202.1137
Jun 2024 | 2371318.7209 | 2212750 | 158568.7209 | 130207.1137
Jul 2024 | 2397245.6816 | 2225000 | 172245.6816 | 140810.0352
Aug 2024 | 2403242.3354 | 2225000 | 178242.3354 | 145712.2716
Sep 2024 | 2429824.3965 | 2225000 | 204824.3965 | 167442.9816
Oct 2024 | 2534300.4711 | 2225000 | 309300.4711 | 252851.6816
Nov 2024 | 3624170.5002 | 3025000 | 599170.5002 | 489819.0683
Dec 2024 | 4451154.1468 | 4417000 | 34154.1468 | 27212.9965
Jan 2025 | 4621791.8519 | 4658000 | -36208.1481 | -28849.563
Feb 2025 | 4685020.8961 | 4867000 | -181979.1039 | -144995.4746
Mar 2025 | 4692617.9394 | 4867000 | -174382.0606 | -138942.3792
Job Profitability Summary
| Beginning | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 1197000 | 1000000 | 0 | 15750 | 0 | 12250 | 0 | 0 | 0 | 800000 | 1392000 | 241000 | 209000 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36208.1481 | -181979.1039 | -174382.0606 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36208.1481 | 181979.1039
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 9946.07 | 233236.6918 | 803534.4373 | 508347.6805 | 83127.3008 | 137439.1227 | 128202.1137 | 130207.1137 | 140810.0352 | 145712.2716 | 167442.9816 | 252851.6816 | 489819.0683 | 27212.9965 | -28849.563 | -144995.4746 | 0
Construction Costs | 0 | 0 | 9946.07 | 223290.6218 | 570297.7455 | 687717.7794 | 395919.5836 | 54311.8218 | 3695.9455 | 2005 | 12552.5118 | 4902.2364 | 21730.71 | 85408.7 | 890963.6273 | 583803.3464 | 135958.9894 | 50379 | 6053.0955 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 9946.07 | 233236.6918 | 803534.4373 | 508347.6805 | 83127.3008 | 137439.1227 | 128202.1137 | 130207.1137 | 140810.0352 | 145712.2716 | 167442.9816 | 252851.6816 | 489819.0683 | 27212.9965 | -28849.563 | -144995.4746 | -138942.3792 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 982904.5361 | 821139.9633 | 0 | 12932.9544 | 0 | 1949.5903 | 0 | 0 | 0 | 653996.2406 | 1046409.4181 | 192021.5489 | 166524.9117 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.255% | 5.98% | 20.6% | 38.23% | 48.38% | 49.78% | 49.87% | 49.92% | 49.68% | 49.81% | 50.36% | 52.52% | 75.11% | 92.25% | 95.79% | 97.1% | 97.26% | 97.26%

## J-1864
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 380122.3462 | 48906.5 | 359201.3945 | 0
Estimate Code |  | E00012050 |  |  |  |  | Bolts | 32931.332 | 2200 | 34948 | 0
Contract Code |  | J-1864 |  |  |  |  | Purlin | 340335.2175 | 300 | 339920.6545 | 0
Contract Name |  | 17-31 Franklyn Street, Huntingdale |  |  |  |  | Labour | 148396.9502 | 0 | 95857.99 | 29592.46
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 84976.8398 | 0 | 87536.7318 | 0
Start Date |  | 13 Apr 2023 |  |  |  |  | Rigging | 314293.9375 | 129590 | 394200 | 0
Completion Date |  | 25 Jan 2023 |  |  |  |  | Freight | 14914.04 | 0 | 14788.75 | 0
Budgeted Revenue |  | 1924999.98 |  |  |  |  | Shop Drawings | 23107.1484 | 0 | 22500 | 0
Budgeted Job Expenditure |  | 1608050.698 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.46% |  |  |  |  | Box Frame | 240000 | 0 | 0 | 0
Estimated Weight |  | 180.1755 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 179.5985 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.17% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 900 | 1016.5545 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 28035.7881 | 0 | 1982.2818 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 937.0928 | 0 | 0 | 0
[7 empty] | OH & Profit | 316949.2947 | 3097 | 0 | 0
[7 empty] | Total | 1924999.9874 | 184993.5 | 1351952.3573 | 29592.46
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1924999.99 | 1924999.99 | 1608050.698 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 0 | 11281.1318 | 11281.1318 | 0.7015%
Feb 2024 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 76972 | 76972 | 124882.1403 | 136163.2721 | 8.468%
Mar 2024 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 200127.78 | 277099.78 | 141467.0045 | 277630.2767 | 17.27%
Apr 2024 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 140926.67 | 418026.45 | 119544.8509 | 397175.1276 | 24.7%
May 2024 | 0 | 1924999.99 | 0 | 1608050.698 | 316949.292 | 16.46% | 0 | 418026.45 | 120579.9197 | 517755.0473 | 32.2%
Jun 2024 | 81881.5 | 2006881.49 | 81881.5 | 1689932.198 | 316949.292 | 15.79% | 183487.78 | 601514.23 | 37921.4652 | 555676.5124 | 32.88%
Jul 2024 | 3200 | 2010081.49 | 2400 | 1692332.198 | 317749.292 | 15.81% | 3200 | 604714.23 | 56362.9336 | 612039.4461 | 36.17%
Aug 2024 | 0 | 2010081.49 | 0 | 1692332.198 | 317749.292 | 15.81% | 0 | 604714.23 | 56787.3579 | 668826.8039 | 39.52%
Sep 2024 | 630 | 2010711.49 | 630 | 1692962.198 | 317749.292 | 15.8% | 1800 | 606514.23 | 61037.7573 | 729864.5612 | 43.11%
Oct 2024 | 12592 | 2023303.49 | 11200 | 1704162.198 | 319141.292 | 15.77% | 177886.07 | 784400.3 | 208677.6018 | 938542.163 | 55.07%
Nov 2024 | 7700 | 2031003.49 | 7500 | 1711662.198 | 319341.292 | 15.72% | 110638.89 | 895039.19 | 115190.61 | 1053732.773 | 61.56%
Dec 2024 | 0 | 2031003.49 | 0 | 1711662.198 | 319341.292 | 15.72% | 26430 | 921469.19 | 43390.7482 | 1097123.5212 | 64.1%
Jan 2025 | 0 | 2031003.49 | 0 | 1711662.198 | 319341.292 | 15.72% | 350780 | 1272249.19 | 63948.9864 | 1161072.5076 | 67.83%
Feb 2025 | 8990 | 2039993.49 | 8285 | 1719947.198 | 320046.292 | 15.69% | 379965.92 | 1652215.11 | 93927.39 | 1254999.8976 | 72.97%
Mar 2025 | 70000 | 2109993.49 | 70000 | 1789947.198 | 320046.292 | 15.17% | 0 | 1652215.11 | 126544.9364 | 1381544.8339 | 77.18%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 13504.6604 | 0 | 13504.6604 | 11281.1318
Feb 2024 | 163001.2647 | 76972 | 86029.2647 | 71864.6337
Mar 2024 | 332351.6357 | 277099.78 | 55251.8557 | 46154.6938
Apr 2024 | 475458.9626 | 418026.45 | 57432.5126 | 47976.3077
May 2024 | 619805.3718 | 418026.45 | 201778.9218 | 168556.2274
Jun 2024 | 659894.4671 | 601514.23 | 58380.2371 | 49160.1736
Jul 2024 | 726954.8869 | 604714.23 | 122240.6569 | 102917.1209
Aug 2024 | 794404.5384 | 604714.23 | 189690.3084 | 159704.4787
Sep 2024 | 866851.6409 | 606514.23 | 260337.4109 | 219196.7359
Oct 2024 | 1114304.5164 | 784400.3 | 329904.2164 | 277867.506
Nov 2024 | 1250325.5269 | 895039.19 | 355286.3369 | 299423.5093
Dec 2024 | 1301811.5976 | 921469.19 | 380342.4076 | 320539.9324
Jan 2025 | 1377691.4147 | 1272249.19 | 105442.2247 | 88863.2004
Feb 2025 | 1488529.1967 | 1652215.11 | -163685.9133 | -138005.8953
Mar 2025 | 1628567.9315 | 1652215.11 | -23647.1785 | -20060.3467
Job Profitability Summary
| Beginning | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76972 | 200127.78 | 140926.67 | 0 | 183487.78 | 3200 | 0 | 1800 | 177886.07 | 110638.89 | 26430 | 350780 | 379965.92 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -163685.9133 | -23647.1785 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163685.9133
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11281.1318 | 71864.6337 | 46154.6938 | 47976.3077 | 168556.2274 | 49160.1736 | 102917.1209 | 159704.4787 | 219196.7359 | 277867.506 | 299423.5093 | 320539.9324 | 88863.2004 | -138005.8953 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11281.1318 | 124882.1403 | 141467.0045 | 119544.8509 | 120579.9197 | 37921.4652 | 56362.9336 | 56787.3579 | 61037.7573 | 208677.6018 | 115190.61 | 43390.7482 | 63948.9864 | 93927.39 | 126544.9364 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11281.1318 | 71864.6337 | 46154.6938 | 47976.3077 | 168556.2274 | 49160.1736 | 102917.1209 | 159704.4787 | 219196.7359 | 277867.506 | 299423.5093 | 320539.9324 | 88863.2004 | -138005.8953 | -20060.3467 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64298.6384 | 167176.9444 | 117723.237 | 0 | 157317.519 | 2605.9863 | 0 | 1545.5001 | 150006.8317 | 93634.6067 | 22274.325 | 295625.7184 | 320796.4856 | 8599.3878 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7015% | 8.468% | 17.27% | 24.7% | 32.2% | 32.88% | 36.17% | 39.52% | 43.11% | 55.07% | 61.56% | 64.1% | 67.83% | 72.97% | 77.18% | 77.18%

## J-1873
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Shark Screens Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1873 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Brackets |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Shark Screens Pty Ltd |  |  |  |  | Processing | 0 | 0 | 230 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 158.9727 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 388.9727 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 230 | 230 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 158.9727 | 388.9727 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Oct 2023 | Nov 2023 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | 0
Construction Costs | 0 | 230 | 158.9727 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-1877
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Chick Constructions Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00013061 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1877 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | AGPC CCTV Temporary Forklift Sleeves |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Chick Constructions Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 27 Oct 2023 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Oct 2023 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-1898
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Texco Construction Pty Ltd |  |  |  |  | Steel | 522353.1828 | 0 | 0 | 0
Estimate Code |  | E00012982 |  |  |  |  | Bolts | 28836.1738 | 0 | 0 | 0
Contract Code |  | J-1898 |  |  |  |  | Purlin | 274135.2897 | 0 | 0 | 0
Contract Name |  | 285 Palmers Road, Truganina |  |  |  |  | Labour | 155725.904 | 0 | 0 | 0
Customer |  | Texco Construction Pty Ltd |  |  |  |  | Processing | 84471.6152 | 0 | 0 | 0
Start Date |  | 16 Nov 2023 |  |  |  |  | Rigging | 214557.9531 | 0 | 0 | 0
Completion Date |  | 28 Sep 2023 |  |  |  |  | Freight | 10441.1289 | 0 | 0 | 0
Budgeted Revenue |  | 1615599.99 |  |  |  |  | Shop Drawings | 18061.9277 | 0 | 0 | 0
Budgeted Job Expenditure |  | 1330453.6283 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.65% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 226.5699 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 3455.1899 | 0 | 0 | 0
Current GP% |  | 17.65% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 13207.0719 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2499.999 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2708.1904 | 0 | 0 | 0
[7 empty] | OH & Profit | 285146.3699 | 0 | 0 | 0
[7 empty] | Total | 1615599.9965 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1615599.99 | 1615599.99 | 1330453.6283 | 1330453.6283 | 285146.3617 | 17.65% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 1615599.99 | 0 | 1330453.6283 | 285146.3617 | 17.65% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2023 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Nov 2023 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-1900
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Qanstruct (Aust) Pty Ltd |  |  |  |  | Steel | 2595271.9805 | 12700 | 2578740.4009 | 0
Estimate Code |  | E00012997 |  |  |  |  | Bolts | 146847.3438 | 0 | 104917.6545 | 0
Contract Code |  | J-1900 |  |  |  |  | Purlin | 1282026.7946 | 1500 | 1286327.8364 | 0
Contract Name |  | 131-149 Somerton Road, Campbellfield- WH 1.1-1.3 & |  |  |  |  | Labour | 775843.1172 | 4320 | 589837.76 | 183345
Customer |  | Qanstruct (Aust) Pty Ltd |  |  |  |  | Processing | 446873.6172 | 1600 | 334831.6209 | 0
Start Date |  | 19 Nov 2023 |  |  |  |  | Rigging | 1253014.3125 | 19156 | 1255447.5 | 0
Completion Date |  | 10 Oct 2023 |  |  |  |  | Freight | 50795.4102 | 0 | 42180.09 | 0
Budgeted Revenue |  | 8350000.01 |  |  |  |  | Shop Drawings | 81551.7969 | 0 | 79500 | 0
Budgeted Job Expenditure |  | 6901468.5596 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.35% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 1222.959 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 1292.397 |  |  |  |  | Stairs | 29579.0417 | 0 | 0 | 0
Current GP% |  | 20.3% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 225437.5051 | 11000 | 245899.5636 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 4000 | 0 | 4761.9182 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 10227.6055 | 0 | 8755 | 0
[7 empty] | OH & Profit | 1448531.4605 | 8735.25 | 0 | 250000
[7 empty] | Total | 8349999.9855 | 59011.25 | 6531199.3445 | 433345
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 8350000 | 8350000 | 6901468.5596 | 6901468.5596 | 1448531.4404 | 17.35% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 8350000 | 0 | 6901468.5596 | 1448531.4404 | 17.35% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 8350000 | 0 | 6901468.5596 | 1448531.4404 | 17.35% | 128132.12 | 128132.12 | 0 | 0 | 0%
Jan 2024 | 0 | 8350000 | 0 | 6901468.5596 | 1448531.4404 | 17.35% | 0 | 128132.12 | 805 | 805 | 0.01166%
Feb 2024 | 0 | 8350000 | 0 | 6901468.5596 | 1448531.4404 | 17.35% | 0 | 128132.12 | 68278.33 | 69083.33 | 1.001%
Mar 2024 | 0 | 8350000 | 0 | 6901468.5596 | 1448531.4404 | 17.35% | 300000 | 428132.12 | 1180601.2327 | 1249684.5627 | 18.11%
Apr 2024 | 0 | 8350000 | 0 | 6901468.5596 | 1448531.4404 | 17.35% | 1575132 | 2003264.12 | 2361004.0245 | 3610688.5873 | 52.32%
May 2024 | 0 | 8350000 | 0 | 6901468.5596 | 1448531.4404 | 17.35% | 1715288.38 | 3718552.5 | 1185446.9667 | 4796135.5539 | 69.49%
Jun 2024 | 0 | 8350000 | 0 | 6901468.5596 | 1448531.4404 | 17.35% | 2042944.84 | 5761497.34 | 1062973.9288 | 5859109.4827 | 84.9%
Jul 2024 | 17384 | 8367384 | 13100 | 6914568.5596 | 1452815.4404 | 17.36% | 1012927.54 | 6774424.88 | 266290.2306 | 6125399.7133 | 88.59%
Aug 2024 | 0 | 8367384 | 0 | 6914568.5596 | 1452815.4404 | 17.36% | 380601 | 7155025.88 | 141986.617 | 6267386.3303 | 90.64%
Sep 2024 | 10856 | 8378240 | 8856 | 6923424.5596 | 1454815.4404 | 17.36% | 22760 | 7177785.88 | 9152.7173 | 6276539.0476 | 90.66%
Oct 2024 | 0 | 8378240 | -150000 | 6773424.5596 | 1604815.4404 | 19.15% | 541470.36 | 7719256.24 | 261732.1027 | 6538271.1503 | 96.53%
Nov 2024 | 14020 | 8392260 | 13020 | 6786444.5596 | 1605815.4404 | 19.13% | 0 | 7719256.24 | 57220.2545 | 6595491.4048 | 97.19%
Dec 2024 | 11126.25 | 8403386.25 | 9675 | 6796119.5596 | 1607266.6904 | 19.13% | 75140.38 | 7794396.62 | 49419.8955 | 6644911.3003 | 97.78%
Jan 2025 | 5625 | 8409011.25 | -94375 | 6701744.5596 | 1707266.6904 | 20.3% | 62289 | 7856685.62 | 37778.0891 | 6682689.3894 | 99.72%
Feb 2025 | 0 | 8409011.25 | 0 | 6701744.5596 | 1707266.6904 | 20.3% | 0 | 7856685.62 | 20979.5536 | 6703668.943 | 100%
Mar 2025 | 0 | 8409011.25 | 0 | 6701744.5596 | 1707266.6904 | 20.3% | 0 | 7856685.62 | 10875.4182 | 6714544.3612 | 100.2%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 128132.12 | -128132.12 | -105904.1674
Jan 2024 | 973.9594 | 128132.12 | -127158.1606 | -105099.1674
Feb 2024 | 83583.052 | 128132.12 | -44549.068 | -36820.8374
Mar 2024 | 1511977.6333 | 428132.12 | 1083845.5133 | 895823.4411
Apr 2024 | 4368526.7046 | 2003264.12 | 2365262.5846 | 1954944.3549
May 2024 | 5802784.0784 | 3718552.5 | 2084231.5784 | 1722665.7137
Jun 2024 | 7088862.8643 | 5761497.34 | 1327365.5243 | 1097098.3752
Jul 2024 | 7412403.4079 | 6774424.88 | 637978.5279 | 527207.3411
Aug 2024 | 7584222.7393 | 7155025.88 | 429196.8593 | 354676.0982
Sep 2024 | 7595424.7869 | 7177785.88 | 417638.9069 | 345119.1975
Oct 2024 | 8087372.1115 | 7719256.24 | 368115.8715 | 297604.877
Nov 2024 | 8156123.3149 | 7719256.24 | 436867.0749 | 353274.8251
Dec 2024 | 8216417.5842 | 7794396.62 | 422020.9642 | 341303.475
Jan 2025 | 8385101.783 | 7856685.62 | 528416.163 | 421132.7634
Feb 2025 | 8411425.8694 | 7856685.62 | 554740.2494 | 442112.3171
Mar 2025 | 8425071.7959 | 7856685.62 | 568386.1759 | 452987.7353
Job Profitability Summary
| Beginning | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 128132.12 | 0 | 0 | 300000 | 1575132 | 1715288.38 | 2042944.84 | 1012927.54 | 380601 | 22760 | 541470.36 | 0 | 75140.38 | 62289 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | -128132.12 | -127158.1606 | -44549.068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 128132.12 | 127158.1606 | 44549.068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | -105904.1674 | -105099.1674 | -36820.8374 | 895823.4411 | 1954944.3549 | 1722665.7137 | 1097098.3752 | 527207.3411 | 354676.0982 | 345119.1975 | 297604.877 | 353274.8251 | 341303.475 | 421132.7634 | 442112.3171 | 0
Construction Costs | 0 | 0 | 0 | 805 | 68278.33 | 1180601.2327 | 2361004.0245 | 1185446.9667 | 1062973.9288 | 266290.2306 | 141986.617 | 9152.7173 | 261732.1027 | 57220.2545 | 49419.8955 | 37778.0891 | 20979.5536 | 10875.4182 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | -105904.1674 | -105099.1674 | -36820.8374 | 895823.4411 | 1954944.3549 | 1722665.7137 | 1097098.3752 | 527207.3411 | 354676.0982 | 345119.1975 | 297604.877 | 353274.8251 | 341303.475 | 421132.7634 | 442112.3171 | 452987.7353 | 0
Total Costruction Cost | #VALUE! | 0 | 105904.1674 | 0 | 0 | 247956.9542 | 1301883.1108 | 1417725.6078 | 1688541.2673 | 836181.2647 | 314517.8599 | 18709.618 | 309246.4232 | 1550.3065 | 61391.2455 | -42051.1993 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0.01166% | 1.001% | 18.11% | 52.32% | 69.49% | 84.9% | 88.59% | 90.64% | 90.66% | 96.53% | 97.19% | 97.78% | 99.72% | 100% | 100.2% | 100.2%

## J-1905
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Erilyan |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00013162 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1905 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Roof Louvre Works |  |  |  |  | Labour | 0 | 0 | 200 | 0
Customer |  | Erilyan |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 28 Nov 2023 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 200 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-1911
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Mainbrace Constructions (Victoria) |  |  |  |  | Steel | 479999.9453 | 6900 | 287258.9009 | 0
Estimate Code |  | E00012841 |  |  |  |  | Bolts | 25000.0352 | 0 | 15116.2182 | 0
Contract Code |  | J-1911 |  |  |  |  | Purlin | 129999.9837 | 0 | 66647.7 | 0
Contract Name |  | 144 Northcorp Boulevard, Broadmeadows |  |  |  |  | Labour | 360001.0049 | 0 | 66832.69 | 17838
Customer |  | Mainbrace Constructions (Victoria) |  |  |  |  | Processing | 110000.0078 | 0 | 66372.7727 | 0
Start Date | [6 empty] | Rigging | 500000.125 | 2435 | 188406.6536 | 0
Completion Date |  | 16 Aug 2023 |  |  |  |  | Freight | 19999.9414 | 0 | 8370.1909 | 0
Budgeted Revenue |  | 2344999.98 |  |  |  |  | Shop Drawings | 137000 | 0 | 136200 | 0
Budgeted Job Expenditure |  | 1837850.98 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 21.63% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 225.412 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 143.1774 |  |  |  |  | Stairs | 0 | 0 | 75000 | 0
Current GP% |  | 21.54% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 39999.9725 | 0 | 6122.8273 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 29849.958 | 0 | 28324.3818 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 6000.0166 | 0 | 1683 | 0
[7 empty] | OH & Profit | 507149.0085 | 0 | 0 | 0
[7 empty] | Total | 2344999.9989 | 9335 | 946335.3355 | 17838
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 2344999.98 | 2344999.98 | 1837850.98 | 1837850.98 | 507149 | 21.63% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 2344999.98 | 0 | 1837850.98 | 507149 | 21.63% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 2344999.98 | 0 | 1837850.98 | 507149 | 21.63% | 30000 | 30000 | 0 | 0 | 0%
Feb 2024 | 0 | 2344999.98 | 0 | 1837850.98 | 507149 | 21.63% | 0 | 30000 | 30968.5091 | 30968.5091 | 1.685%
Mar 2024 | 0 | 2344999.98 | 0 | 1837850.98 | 507149 | 21.63% | 0 | 30000 | 7355.8727 | 38324.3818 | 2.085%
Apr 2024 | 0 | 2344999.98 | 0 | 1837850.98 | 507149 | 21.63% | -3300 | 26700 | 0 | 38324.3818 | 2.085%
May 2024 | 0 | 2344999.98 | 0 | 1837850.98 | 507149 | 21.63% | 0 | 26700 | 0 | 38324.3818 | 2.085%
Jun 2024 | 0 | 2344999.98 | 0 | 1837850.98 | 507149 | 21.63% | 0 | 26700 | 0 | 38324.3818 | 2.085%
Jul 2024 | 2435 | 2347434.98 | 2435 | 1840285.98 | 507149 | 21.6% | 13300 | 40000 | 24153.4273 | 62477.8091 | 3.395%
Aug 2024 | 0 | 2347434.98 | 0 | 1840285.98 | 507149 | 21.6% | 0 | 40000 | 43783.7055 | 106261.5145 | 5.774%
Sep 2024 | 0 | 2347434.98 | 0 | 1840285.98 | 507149 | 21.6% | 0 | 40000 | 5481.6273 | 111743.1418 | 6.072%
Oct 2024 | 6900 | 2354334.98 | 6900 | 1847185.98 | 507149 | 21.54% | 6900 | 46900 | 238381.9718 | 350125.1136 | 18.95%
Nov 2024 | 0 | 2354334.98 | 0 | 1847185.98 | 507149 | 21.54% | 650080 | 696980 | 61795.9527 | 411921.0664 | 22.3%
Dec 2024 | 0 | 2354334.98 | 0 | 1847185.98 | 507149 | 21.54% | -1463 | 695517 | 57174.0955 | 469095.1618 | 25.4%
Jan 2025 | 0 | 2354334.98 | 0 | 1847185.98 | 507149 | 21.54% | 117106 | 812623 | 103634.6 | 572729.7618 | 31.01%
Feb 2025 | 0 | 2354334.98 | 0 | 1847185.98 | 507149 | 21.54% | 83160 | 895783 | 267060.9782 | 839790.74 | 45.46%
Mar 2025 | 0 | 2354334.98 | 0 | 1847185.98 | 507149 | 21.54% | -21181.6 | 874601.4 | 124382.5955 | 964173.3355 | 52.2%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 30000 | -30000 | -23511.953
Feb 2024 | 39514.1684 | 30000 | 9514.1684 | 7456.5561
Mar 2024 | 48899.8703 | 30000 | 18899.8703 | 14812.4288
Apr 2024 | 48899.8703 | 26700 | 22199.8703 | 17398.7436
May 2024 | 48899.8703 | 26700 | 22199.8703 | 17398.7436
Jun 2024 | 48899.8703 | 26700 | 22199.8703 | 17398.7436
Jul 2024 | 79695.5452 | 40000 | 39695.5452 | 31119.565
Aug 2024 | 135545.2354 | 40000 | 95545.2354 | 74903.2704
Sep 2024 | 142537.4984 | 40000 | 102537.4984 | 80384.8977
Oct 2024 | 446252.7387 | 46900 | 399352.7387 | 313327.8765
Nov 2024 | 525014.907 | 696980 | -171965.093 | -134921.968
Dec 2024 | 597886.277 | 695517 | -97630.723 | -76600.0184
Jan 2025 | 729973.9858 | 812623 | -82649.0142 | -64845.5303
Feb 2025 | 1070357.1468 | 895783 | 174574.1468 | 136969.0036
Mar 2025 | 1228889.2591 | 874601.4 | 354287.8591 | 277970.4553
Job Profitability Summary
| Beginning | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 30000 | 0 | 0 | -3300 | 0 | 0 | 13300 | 0 | 0 | 6900 | 650080 | -1463 | 117106 | 83160 | -21181.6 | #VALUE!
Less Current Period Overbills | 0 | 0 | -30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -171965.093 | -97630.723 | -82649.0142 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171965.093 | 97630.723 | 82649.0142 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | -23511.953 | 7456.5561 | 14812.4288 | 17398.7436 | 17398.7436 | 17398.7436 | 31119.565 | 74903.2704 | 80384.8977 | 313327.8765 | -134921.968 | -76600.0184 | -64845.5303 | 136969.0036 | 0
Construction Costs | 0 | 0 | 0 | 30968.5091 | 7355.8727 | 0 | 0 | 0 | 24153.4273 | 43783.7055 | 5481.6273 | 238381.9718 | 61795.9527 | 57174.0955 | 103634.6 | 267060.9782 | 124382.5955 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | -23511.953 | 7456.5561 | 14812.4288 | 17398.7436 | 17398.7436 | 17398.7436 | 31119.565 | 74903.2704 | 80384.8977 | 313327.8765 | -134921.968 | -76600.0184 | -64845.5303 | 136969.0036 | 277970.4553 | 0
Total Costruction Cost | #VALUE! | 0 | 23511.953 | 0 | 0 | -2586.3148 | 0 | 0 | 10432.6059 | 0 | 0 | 5438.993 | 510045.7972 | -1147.8541 | 91880.1119 | 65246.4443 | -16618.8562 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 1.685% | 2.085% | 2.085% | 2.085% | 2.085% | 3.395% | 5.774% | 6.072% | 18.95% | 22.3% | 25.4% | 31.01% | 45.46% | 52.2% | 52.2%

## J-1915
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Valiant Framing |  |  |  |  | Steel | 2021.6206 | 0 | 33646.3055 | 0
Estimate Code |  | E00013252 |  |  |  |  | Bolts | 2264.2151 | 0 | 591.3 | 0
Contract Code |  | J-1915 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 43 Danaher Drive, South Morang |  |  |  |  | Labour | 25262.1705 | 0 | 9119.17 | 297
Customer |  | Valiant Framing |  |  |  |  | Processing | 7858.6987 | 0 | 3823.75 | 0
Start Date | [6 empty] | Rigging | 29353.9297 | 0 | 26500 | 0
Completion Date |  | 16 Jan 2024 |  |  |  |  | Freight | 1211.6104 | 0 | 800 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 5337.0781 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 17.7903 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 15.1837 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 444.7565 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 533.7078 | 0 | 0 | 0
[7 empty] | OH & Profit | 23814.3779 | 0 | 0 | 0
[7 empty] | Total | 98102.1655 | 0 | 74480.5255 | 297
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 37539.0555 | 37539.0555 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 10738.47 | 48277.5255 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 26500 | 74777.5255 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Jan 2024 | Feb 2024 | Mar 2024 | Total
Sales | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 37539.0555 | 10738.47 | 26500 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-1944
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Qanstruct (Aust) Pty Ltd |  |  |  |  | Steel | 1849999.7582 | 272305.1299 | 2112702.6809 | 0
Estimate Code |  | E00013164 |  |  |  |  | Bolts | 95000.2109 | 14000 | 106562.6091 | 0
Contract Code |  | J-1944 |  |  |  |  | Purlin | 950000 | 600 | 950369.8273 | 0
Contract Name |  | Lot 3B Oakdale West Estate, Horsley Park - Precinc |  |  |  |  | Labour | 579999.9336 | 64300 | 450362.3836 | 133441.71
Customer |  | Qanstruct (Aust) Pty Ltd |  |  |  |  | Processing | 349999.875 | 48200 | 416526.1218 | 0
Start Date |  | 31 Jan 2024 |  |  |  |  | Rigging | 1600000.5 | 401780 | 2082619.6364 | 0
Completion Date |  | 28 Nov 2023 |  |  |  |  | Freight | 300000 | 68500 | 368803.0282 | 0
Budgeted Revenue |  | 7022000.06 |  |  |  |  | Shop Drawings | 85000.2656 | 9000 | 85000 | 0
Budgeted Job Expenditure |  | 5893000.4438 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.08% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 854.4372 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 1129.2099 |  |  |  |  | Stairs | 0 | 277000 | 219000 | 0
Current GP% |  | 17.55% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 60000.0039 | 133700 | 151997.0273 | 0
[7 empty] | Grates | 0 | 19000 | 12003.9455 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 17000 | 0 | 20921.3818 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 5999.8579 | 0 | 1791 | 0
[7 empty] | OH & Profit | 1128999.614 | 205400 | 0 | 163306.76
[7 empty] | Total | 7022000.0191 | 1513785.1299 | 6978659.6418 | 296748.47
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 7022000.07 | 7022000.07 | 5893000.4439 | 5893000.4439 | 1128999.6261 | 16.08% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 7022000.07 | 0 | 5893000.4439 | 1128999.6261 | 16.08% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 7022000.07 | 0 | 5893000.4439 | 1128999.6261 | 16.08% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 7022000.07 | 0 | 5893000.4439 | 1128999.6261 | 16.08% | 0 | 0 | 5460 | 5460 | 0.09265%
Apr 2024 | 0 | 7022000.07 | 0 | 5893000.4439 | 1128999.6261 | 16.08% | 0 | 0 | 22753.4455 | 28213.4455 | 0.4788%
May 2024 | 0 | 7022000.07 | 0 | 5893000.4439 | 1128999.6261 | 16.08% | 900750 | 900750 | 899037.8342 | 927251.2797 | 15.73%
Jun 2024 | 0 | 7022000.07 | 0 | 5893000.4439 | 1128999.6261 | 16.08% | 2182867.5 | 3083617.5 | 1832284.2015 | 2759535.4812 | 46.83%
Jul 2024 | 3360 | 7025360.07 | 3360 | 5896360.4439 | 1128999.6261 | 16.07% | 2356915.6 | 5440533.1 | 1193740.5336 | 3953276.0148 | 67.05%
Aug 2024 | 0 | 7025360.07 | -500000 | 5396360.4439 | 1628999.6261 | 23.19% | 587807 | 6028340.1 | 825064.6724 | 4778340.6873 | 88.55%
Sep 2024 | 1380400 | 8405760.07 | 1175000 | 6571360.4439 | 1834399.6261 | 21.82% | 633000 | 6661340.1 | 1082486.8264 | 5860827.5136 | 89.19%
Oct 2024 | 0 | 8405760.07 | 0 | 6571360.4439 | 1834399.6261 | 21.82% | 1178600 | 7839940.1 | 691522.3609 | 6552349.8745 | 99.71%
Nov 2024 | 0 | 8405760.07 | 0 | 6571360.4439 | 1834399.6261 | 21.82% | 0 | 7839940.1 | 294581.9736 | 6846931.8482 | 104.2%
Dec 2024 | 126020 | 8531780.07 | 375092.47 | 6946452.9139 | 1585327.1561 | 18.58% | 226140 | 8066080.1 | 99191.9255 | 6946123.7736 | 100%
Jan 2025 | 0 | 8531780.07 | 87620.77 | 7034073.6838 | 1497706.3861 | 17.55% | 30290 | 8096370.1 | 54662.3955 | 7000786.1691 | 99.53%
Feb 2025 | 4005.13 | 8535785.2 | 4005.1299 | 7038078.8137 | 1497706.3863 | 17.55% | 172848.94 | 8269219.04 | 107529.6927 | 7108315.8618 | 101%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 6506.044 | 0 | 6506.044 | 5460
Apr 2024 | 33618.6664 | 0 | 33618.6664 | 28213.4455
May 2024 | 1104897.0067 | 900750 | 204147.0067 | 171324.1796
Jun 2024 | 3288215.9991 | 3083617.5 | 204598.4991 | 171703.0809
Jul 2024 | 4710225.5238 | 5440533.1 | -730307.5762 | -612944.6265
Aug 2024 | 6220778.6553 | 6028340.1 | 192438.5553 | 147817.0225
Sep 2024 | 7496881.4011 | 6661340.1 | 835541.3011 | 653200.0687
Oct 2024 | 8381442.6877 | 7839940.1 | 541502.5877 | 423329.7947
Nov 2024 | 8758257.4146 | 7839940.1 | 918317.3146 | 717911.7683
Dec 2024 | 8531375.813 | 8066080.1 | 465295.713 | 378837.0932
Jan 2025 | 8491404.9236 | 8096370.1 | 395034.8236 | 325688.6645
Feb 2025 | 8620968.724 | 8269219.04 | 351749.684 | 290030.9627
Job Profitability Summary
| Beginning | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 900750 | 2182867.5 | 2356915.6 | 587807 | 633000 | 1178600 | 0 | 226140 | 30290 | 172848.94 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -730307.5762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730307.5762 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 5460 | 28213.4455 | 171324.1796 | 171703.0809 | -612944.6265 | 147817.0225 | 653200.0687 | 423329.7947 | 717911.7683 | 378837.0932 | 325688.6645 | 0
Construction Costs | 0 | 0 | 0 | 5460 | 22753.4455 | 899037.8342 | 1832284.2015 | 1193740.5336 | 825064.6724 | 1082486.8264 | 691522.3609 | 294581.9736 | 99191.9255 | 54662.3955 | 107529.6927 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 5460 | 28213.4455 | 171324.1796 | 171703.0809 | -612944.6265 | 147817.0225 | 653200.0687 | 423329.7947 | 717911.7683 | 378837.0932 | 325688.6645 | 290030.9627 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 755927.1001 | 1831905.3002 | 1978388.241 | 64303.0235 | 577103.7802 | 921392.6349 | 0 | 438266.6006 | 107810.8242 | 143187.3945 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0.09265% | 0.4788% | 15.73% | 46.83% | 67.05% | 88.55% | 89.19% | 99.71% | 104.2% | 100% | 99.53% | 101% | 101%

## J-1949
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 140000.0091 | 41800 | 210376.3273 | 0
Estimate Code |  | E00012113 |  |  |  |  | Bolts | 10000.0166 | 10000 | 14041.3 | 0
Contract Code |  | J-1949 |  |  |  |  | Purlin | 79999.989 | 60000 | 154863.8818 | 0
Contract Name |  | 1076-1078 Centre Road, Oakleigh South |  |  |  |  | Labour | 49999.874 | 25900 | 21136.93 | 3426.7
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 29999.897 | 20000 | 109586.5727 | 0
Start Date |  | 21 Apr 2023 |  |  |  |  | Rigging | 119999.3281 | 158375 | 200560 | 0
Completion Date |  | 9 Feb 2023 |  |  |  |  | Freight | 14999.9951 | 400 | 14462.0791 | 0
Budgeted Revenue |  | 550000 |  |  |  |  | Shop Drawings | 19999.9082 | 10000 | 24455 | 0
Budgeted Job Expenditure |  | 465299.0215 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.4% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 71.8927 |  |  |  |  | Light Weight Frame Delivery | 200000 |  | 0
Actual Weight |  | 100.3648 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 14.24% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 725.9909 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 300 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 84700.983 | 80000 | 0 | 0
[7 empty] | Total | 750000.0001 | 406475 | 750208.0818 | 3426.7
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 550000.01 | 550000.01 | 465299.0215 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 0 | 0 | 15233.0227 | 15233.0227 | 3.274%
Jul 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 3000 | 3000 | 102704.2173 | 117937.24 | 25.35%
Aug 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 247500 | 250500 | 103635.5964 | 221572.8364 | 47.62%
Sep 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 68000 | 318500 | 137031.9964 | 358604.8327 | 77.07%
Oct 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 230000 | 548500 | 100034.8636 | 458639.6964 | 98.57%
Nov 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 52900 | 601400 | 58694.2818 | 517333.9782 | 111.2%
Dec 2024 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 112500 | 713900 | 4762.8127 | 522096.7909 | 112.2%
Jan 2025 | 0 | 550000.01 | 0 | 465299.0215 | 84700.9885 | 15.4% | 240000 | 953900 | 108681.8955 | 630778.6864 | 135.6%
Feb 2025 | 601800 | 1151800.01 | 521800 | 987099.0215 | 164700.9885 | 14.3% | 203800 | 1157700 | 121611.8818 | 752390.5682 | 76.22%
Mar 2025 | 4675 | 1156475.01 | 4675 | 991774.0215 | 164700.9885 | 14.24% | 4675 | 1162375 | 1244.2136 | 753634.7818 | 75.99%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 18005.9752 | 0 | 18005.9752 | 15233.0227
Jul 2024 | 139406.0167 | 3000 | 136406.0167 | 115399.2454
Aug 2024 | 261906.9815 | 250500 | 11406.9815 | 9650.2859
Sep 2024 | 423883.6801 | 318500 | 105383.6801 | 89154.4043
Oct 2024 | 542128.4506 | 548500 | -6371.5494 | -5390.3193
Nov 2024 | 611507.1815 | 601400 | 10107.1815 | 8550.6574
Dec 2024 | 617136.9957 | 713900 | -96763.0043 | -81861.328
Jan 2025 | 745602.8657 | 953900 | -208297.1343 | -176219.0019
Feb 2025 | 877929.6151 | 1157700 | -279770.3849 | -239764.7776
Mar 2025 | 878788.6887 | 1162375 | -283586.3113 | -243198.9744
Job Profitability Summary
| Beginning | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 247500 | 68000 | 230000 | 52900 | 112500 | 240000 | 203800 | 4675 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6371.5494 | 0 | -96763.0043 | -208297.1343 | -279770.3849 | -283586.3113 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6371.5494 | 0 | 96763.0043 | 208297.1343 | 279770.3849
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15233.0227 | 115399.2454 | 9650.2859 | 89154.4043 | -5390.3193 | 8550.6574 | -81861.328 | -176219.0019 | -239764.7776 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15233.0227 | 102704.2173 | 103635.5964 | 137031.9964 | 100034.8636 | 58694.2818 | 4762.8127 | 108681.8955 | 121611.8818 | 1244.2136 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15233.0227 | 115399.2454 | 9650.2859 | 89154.4043 | -5390.3193 | 8550.6574 | -81861.328 | -176219.0019 | -239764.7776 | -243198.9744 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2537.9946 | 209384.5559 | 57527.878 | 194579.5873 | 44753.3051 | 95174.7981 | 203039.5693 | 185157.6575 | 4678.4105 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.274% | 25.35% | 47.62% | 77.07% | 98.57% | 111.2% | 112.2% | 135.6% | 76.22% | 75.99% | 75.99%

## J-1951
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | FORTEK |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00013426 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1951 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 365-455 Melbourne Rd Norlane - Factory19 - Crane |  |  |  |  | Labour | 0 | 0 | 10346.81 | 0
Customer |  | FORTEK |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 10346.81 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 10168.06 | 10168.06 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Feb 2024 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 10168.06 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-1960
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Leone Constructions Pty Ltd |  |  |  |  | Steel | 61825.1562 | 29953.5996 | 38408.2009 | 0
Estimate Code |  | E00012595 |  |  |  |  | Bolts | 6179.7918 | 0 | 1653.0636 | 0
Contract Code |  | J-1960 |  |  |  |  | Purlin | 2028.5144 | 0 | 1807.2545 | 0
Contract Name |  | 1 & 2 Montrose Court, Toorak |  |  |  |  | Labour | 22290.1876 | 0 | 31579.36 | 0
Customer |  | Leone Constructions Pty Ltd |  |  |  |  | Processing | 12348.4451 | 0 | 14369.85 | 0
Start Date |  | 14 Aug 2023 |  |  |  |  | Rigging | 36000 | 0 | 33036.2545 | 0
Completion Date |  | 19 Jun 2023 |  |  |  |  | Freight | 2500 | 0 | 1160.8273 | 0
Budgeted Revenue |  | 176850.02 |  |  |  |  | Shop Drawings | 8414.4268 | 0 | 7923 | 0
Budgeted Job Expenditure |  | 157811.254 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 10.77% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 24.7528 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 12.5376 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 12.38% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 5623.7 | 0 | 5749.6545 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 601.0305 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 19038.768 | 7488.3999 | 0 | 0
[7 empty] | Total | 176850.0203 | 37441.9995 | 135687.4655 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 176850.02 | 176850.02 | 157811.254 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 948 | 948 | 0.6007%
Apr 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 2417.5 | 3365.5 | 2.133%
May 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 0 | 0 | 3365.5 | 2.133%
Jun 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 49200 | 49200 | 44912.2382 | 48277.7382 | 30.59%
Jul 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 49200 | 49006.2409 | 97283.9791 | 61.65%
Aug 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 90000 | 139200 | 31454.6964 | 128738.6755 | 81.58%
Sep 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 37650 | 176850 | 1926.89 | 130665.5655 | 82.8%
Oct 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 176850 | 2766.9 | 133432.4655 | 84.55%
Nov 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 176850 | 500 | 133932.4655 | 84.87%
Dec 2024 | 0 | 176850.02 | 0 | 157811.254 | 19038.766 | 10.77% | 0 | 176850 | 0 | 133932.4655 | 84.87%
Jan 2025 | 37442 | 214292.02 | 29953.5996 | 187764.8536 | 26527.1664 | 12.38% | 0 | 176850 | 0 | 133932.4655 | 71.33%
Feb 2025 | 0 | 214292.02 | 0 | 187764.8536 | 26527.1664 | 12.38% | 0 | 176850 | 0 | 133932.4655 | 71.33%
Mar 2025 | 0 | 214292.02 | 0 | 187764.8536 | 26527.1664 | 12.38% | 0 | 176850 | 1755 | 135687.4655 | 72.26%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 1062.3692 | 0 | 1062.3692 | 948
Apr 2024 | 3771.5228 | 0 | 3771.5228 | 3365.5
May 2024 | 3771.5228 | 0 | 3771.5228 | 3365.5
Jun 2024 | 54102.0919 | 49200 | 4902.0919 | 4374.3578
Jul 2024 | 109020.575 | 49200 | 59820.575 | 53380.5987
Aug 2024 | 144270.0489 | 139200 | 5070.0489 | 4524.2335
Sep 2024 | 146429.404 | 176850 | -30420.596 | -27145.6707
Oct 2024 | 149530.1101 | 176850 | -27319.8899 | -24378.7707
Nov 2024 | 150090.4314 | 176850 | -26759.5686 | -23878.7707
Dec 2024 | 150090.4314 | 176850 | -26759.5686 | -23878.7707
Jan 2025 | 152854.2644 | 176850 | -23995.7356 | -21025.3083
Feb 2025 | 152854.2644 | 176850 | -23995.7356 | -21025.3083
Mar 2025 | 154857.2084 | 176850 | -21992.7916 | -19270.3083
Job Profitability Summary
| Beginning | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49200 | 0 | 90000 | 37650 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30420.596 | -27319.8899 | -26759.5686 | -26759.5686 | -23995.7356 | -23995.7356 | -21992.7916 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30420.596 | 27319.8899 | 26759.5686 | 26759.5686 | 23995.7356 | 23995.7356
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 3365.5 | 3365.5 | 4374.3578 | 53380.5987 | 4524.2335 | -27145.6707 | -24378.7707 | -23878.7707 | -23878.7707 | -21025.3083 | -21025.3083 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 2417.5 | 0 | 44912.2382 | 49006.2409 | 31454.6964 | 1926.89 | 2766.9 | 500 | 0 | 0 | 0 | 1755 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 3365.5 | 3365.5 | 4374.3578 | 53380.5987 | 4524.2335 | -27145.6707 | -24378.7707 | -23878.7707 | -23878.7707 | -21025.3083 | -21025.3083 | -19270.3083 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43903.3804 | 0 | 80311.0616 | 33596.7941 | 0 | 0 | 0 | -2853.4624 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.6007% | 2.133% | 2.133% | 30.59% | 61.65% | 81.58% | 82.8% | 84.55% | 84.87% | 84.87% | 71.33% | 71.33% | 72.26% | 72.26%

## J-1962
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | FDC Construction & Fitout (Vic) Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00013182 |  |  |  |  | Bolts | 204930 | 0 | 0 | 0
Contract Code |  | J-1962 |  |  |  |  | Purlin | 1493200 | 0 | 0 | 0
Contract Name |  | Moorebank Intermodal Precinct South Warehouse |  |  |  |  | Labour | 0 | 0 | 7071.75 | 0
Customer |  | FDC Construction & Fitout (Vic) Pty Ltd |  |  |  |  | Processing | 0 | 0 | 3011.25 | 0
Start Date | [6 empty] | Rigging | 1640350 | 0 | 0 | 0
Completion Date |  | 5 Dec 2023 |  |  |  |  | Freight | 12000 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 123800 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 1238 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 37.0067 |  |  |  |  | Stairs | 99000 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 3111540 | 0 | 7045106.6809 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 68000 | 0 | 0 | 0
[7 empty] | OH & Profit | 1084180 | 0 | 0 | -100000
[7 empty] | Total | 7837000 | 0 | 7055189.6809 | -100000
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 156386.05 | 156386.05 | 545254.27 | 545254.27 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 230513.95 | 386900 | 10158.54 | 555412.81 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 320131.29 | 707031.29 | 625333.67 | 1180746.48 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 7674.44 | 714705.73 | 1143881.7636 | 2324628.2436 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 1500769.81 | 2215475.54 | 1030592.2164 | 3355220.46 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 1933958.28 | 4149433.82 | 1290829.6655 | 4646050.1255 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 2505145.5 | 6654579.32 | 1047931.6691 | 5693981.7945 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 394764.99 | 7049344.31 | 492965.5818 | 6186947.3764 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 489858.45 | 7539202.76 | 587101.0045 | 6774048.3809 | #DIV/0!
Dec 2024 | 0 | 0 | 100000 | 100000 | -100000 | #DIV/0! | 183403.46 | 7722606.22 | 280458.9 | 7054507.2809 | 7055%
Jan 2025 | 0 | 0 | 0 | 100000 | -100000 | #DIV/0! | -67606.63 | 7654999.59 | 682.4 | 7055189.6809 | 7055%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 156386.05 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 386900 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 707031.29 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 714705.73 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 2215475.54 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 4149433.82 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 6654579.32 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 7049344.31 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 7539202.76 | #DIV/0! | #DIV/0!
Dec 2024 | 0 | 7722606.22 | -7722606.22 | #DIV/0!
Jan 2025 | 0 | 7654999.59 | -7654999.59 | #DIV/0!
Job Profitability Summary
| Beginning | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Total
Sales | 0 | 0 | 156386.05 | 230513.95 | 320131.29 | 7674.44 | 1500769.81 | 1933958.28 | 2505145.5 | 394764.99 | 489858.45 | 183403.46 | -67606.63 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -7722606.22 | -7654999.59 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 7722606.22
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 545254.27 | 10158.54 | 625333.67 | 1143881.7636 | 1030592.2164 | 1290829.6655 | 1047931.6691 | 492965.5818 | 587101.0045 | 280458.9 | 682.4 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 7055% | 7055% | 7055%

## J-1968
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | GSR Cranes |  |  |  |  | Steel | 0 | 0 | 20811.91 | 0
Estimate Code |  | E00014854 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-1968 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Cranes |  |  |  |  | Labour | 0 | 0 | 14878.25 | 0
Customer |  | GSR Cranes |  |  |  |  | Processing | 0 | 0 | 5497.5 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 16 Dec 2024 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 51.0422 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 132280.1636 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 173467.8236 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 43390.5009 | 43390.5009 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 6688.5727 | 50079.0736 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 3910 | 53989.0736 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 5458.75 | 59447.8236 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 10135.5 | 69583.3236 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 1734.5 | 71317.8236 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 71317.8236 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 71317.8236 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 71317.8236 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 82800 | 154117.8236 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 19350 | 173467.8236 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 43390.5009 | 6688.5727 | 3910 | 5458.75 | 10135.5 | 1734.5 | 0 | 0 | 0 | 82800 | 19350 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-1970
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 77898.2794 | 0 | 81054.3773 | 0
Estimate Code |  | E00012992 |  |  |  |  | Bolts | 8580.0264 | 0 | 8338.0182 | 0
Contract Code |  | J-1970 |  |  |  |  | Purlin | 63673.0123 | 0 | 61790.9636 | 0
Contract Name |  | 144-150 Hall Street, Spotswood |  |  |  |  | Labour | 29959.1165 | 0 | 29958.7 | 11626.56
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 18925.8967 | 0 | 16175 | 0
Start Date |  | 17 Nov 2023 |  |  |  |  | Rigging | 67099.9102 | 0 | 62008.28 | 0
Completion Date |  | 9 Oct 2023 |  |  |  |  | Freight | 2750 | 0 | 2511.4 | 0
Budgeted Revenue |  | 313500 |  |  |  |  | Shop Drawings | 8726.3643 | 0 | 8600 | 0
Budgeted Job Expenditure |  | 277083.9916 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 11.62% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 48.3369 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 42.3275 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 9.739% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | -2704.52 | 0 | 268.5273 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 974.9805 | 0 | 0 | 0
[7 empty] | Other Materials | 500 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 700.9339 | 0 | 636 | 0
[7 empty] | OH & Profit | 36416.0032 | 0 | 0 | -5883.84
[7 empty] | Total | 313500.0033 | 0 | 271341.2664 | 5742.72
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 313500 | 313500 | 277083.9916 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 55.9545 | 55.9545 | 0.02019%
Jun 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 0 | 55.9545 | 0.02019%
Jul 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 7850 | 7905.9545 | 2.853%
Aug 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 17227.85 | 25133.8045 | 9.071%
Sep 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 12385.2045 | 37519.0091 | 13.54%
Oct 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 0 | 108713.4473 | 146232.4564 | 52.78%
Nov 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 252000 | 252000 | 120565.8609 | 266798.3173 | 96.29%
Dec 2024 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 252000 | 15741.4 | 282539.7173 | 102%
Jan 2025 | 0 | 313500 | 0 | 277083.9916 | 36416.0084 | 11.62% | 0 | 252000 | 0 | 282539.7173 | 102%
Feb 2025 | 0 | 313500 | 5883.84 | 282967.8316 | 30532.1684 | 9.739% | 61500 | 313500 | 0 | 282539.7173 | 99.85%
Mar 2025 | 0 | 313500 | 0 | 282967.8316 | 30532.1684 | 9.739% | 0 | 313500 | 428.1091 | 282967.8264 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 63.3084 | 0 | 63.3084 | 55.9545
Jun 2024 | 63.3084 | 0 | 63.3084 | 55.9545
Jul 2024 | 8945.0016 | 0 | 8945.0016 | 7905.9545
Aug 2024 | 28437.037 | 0 | 28437.037 | 25133.8045
Sep 2024 | 42449.978 | 0 | 42449.978 | 37519.0091
Oct 2024 | 165451.1861 | 0 | 165451.1861 | 146232.4564
Nov 2024 | 301862.5218 | 252000 | 49862.5218 | 44070.5154
Dec 2024 | 319672.7492 | 252000 | 67672.7492 | 59811.9154
Jan 2025 | 319672.7492 | 252000 | 67672.7492 | 59811.9154
Feb 2025 | 313025.6922 | 313500 | -474.3078 | -428.1144
Mar 2025 | 313499.9942 | 313500 | -0.0058457 | -0.0052764
Job Profitability Summary
| Beginning | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252000 | 0 | 0 | 61500 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -474.3078 | -0.0058457 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474.3078
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.9545 | 55.9545 | 7905.9545 | 25133.8045 | 37519.0091 | 146232.4564 | 44070.5154 | 59811.9154 | 59811.9154 | -428.1144 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.9545 | 0 | 7850 | 17227.85 | 12385.2045 | 108713.4473 | 120565.8609 | 15741.4 | 0 | 0 | 428.1091 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 55.9545 | 55.9545 | 7905.9545 | 25133.8045 | 37519.0091 | 146232.4564 | 44070.5154 | 59811.9154 | 59811.9154 | -428.1144 | -0.0052764 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222727.8019 | 0 | 0 | 60240.0297 | 1.6919e-11 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0.02019% | 0.02019% | 2.853% | 9.071% | 13.54% | 52.78% | 96.29% | 102% | 102% | 99.85% | 100% | 100%

## J-1978
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Juscot Construction & Management |  |  |  |  | Steel | 75974.6717 | 0 | 81216.4327 | 0
Estimate Code |  | E00012694 |  |  |  |  | Bolts | 4439.2163 | 0 | 3893.2 | 0
Contract Code |  | J-1978 |  |  |  |  | Purlin | 15061.1584 | 0 | 20676.2545 | 0
Contract Name |  | Lot 60, 188 Maddox Road, Williamstown North |  |  |  |  | Labour | 36807.1174 | 0 | 13316.96 | 0
Customer |  | Juscot Construction & Management |  |  |  |  | Processing | 16386.6348 | 0 | 36285 | 0
Start Date |  | 31 Aug 2023 |  |  |  |  | Rigging | 55624.332 | 202070 | 74550 | 0
Completion Date |  | 12 Jul 2023 |  |  |  |  | Freight | 3204.6265 | 0 | 4383.5455 | 0
Budgeted Revenue |  | 285000.02 |  |  |  |  | Shop Drawings | 4342.4258 | 0 | 4000 | 0
Budgeted Job Expenditure |  | 240804.4229 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.51% |  |  |  |  | Box Frame | 28000 | 0 | 28280 | 0
Estimated Weight |  | 38.808 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 40.0389 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.97% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 300 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 664.2384 | 0 | 0 | 0
[7 empty] | OH & Profit | 44195.5797 | 20000 | 0 | 16773.03
[7 empty] | Total | 285000.0011 | 222070 | 266601.3927 | 16773.03
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 285000 | 285000 | 240804.4229 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 57000 | 57000 | 0 | 0 | 0%
Jul 2024 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 57000 | 0 | 0 | 0%
Aug 2024 | 0 | 285000 | 0 | 240804.4229 | 44195.5771 | 15.51% | 0 | 57000 | 82834.6973 | 82834.6973 | 34.4%
Sep 2024 | 2070 | 287070 | 2070 | 242874.4229 | 44195.5771 | 15.4% | 93270 | 150270 | 70808.4564 | 153643.1536 | 63.26%
Oct 2024 | 0 | 287070 | 0 | 242874.4229 | 44195.5771 | 15.4% | 0 | 150270 | 39417.3155 | 193060.4691 | 79.49%
Nov 2024 | 0 | 287070 | 0 | 242874.4229 | 44195.5771 | 15.4% | 0 | 150270 | 14291.16 | 207351.6291 | 85.37%
Dec 2024 | 220000 | 507070 | 183226.97 | 426101.3929 | 80968.6071 | 15.97% | 179130 | 329400 | 59249.7636 | 266601.3927 | 62.57%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 57000 | -57000 | -48160.8846
Jul 2024 | 0 | 57000 | -57000 | -48160.8846
Aug 2024 | 98037.6043 | 57000 | 41037.6043 | 34673.8127
Sep 2024 | 181601.4201 | 150270 | 31331.4201 | 26507.8224
Oct 2024 | 228191.4588 | 150270 | 77921.4588 | 65925.1379
Nov 2024 | 245083.1646 | 150270 | 94813.1646 | 80216.2979
Dec 2024 | 317261.5027 | 329400 | -12138.4973 | -10200.23
Job Profitability Summary
| Beginning | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57000 | 0 | 0 | 93270 | 0 | 0 | 179130 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -57000 | -57000 | 0 | 0 | 0 | 0 | -12138.4973 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57000 | 57000 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48160.8846 | -48160.8846 | 34673.8127 | 26507.8224 | 65925.1379 | 80216.2979 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82834.6973 | 70808.4564 | 39417.3155 | 14291.16 | 59249.7636 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48160.8846 | -48160.8846 | 34673.8127 | 26507.8224 | 65925.1379 | 80216.2979 | -10200.23 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48160.8846 | 0 | 0 | 78974.4466 | 0 | 0 | 149666.2915 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 34.4% | 63.26% | 79.49% | 85.37% | 62.57% | 62.57%

## J-1981
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Qanstruct (Aust) Pty Ltd |  |  |  |  | Steel | 0 | 0 | 6004.1591 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 903.5091 | 0
Contract Code |  | J-1981 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 85-87 High Street, South Kew |  |  |  |  | Labour | 0 | 0 | 4149.32 | 2305
Customer |  | Qanstruct (Aust) Pty Ltd |  |  |  |  | Processing | 0 | 0 | 4987.83 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 7394.5273 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 1992.8545 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 3500 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 3.0272 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 195 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 29127.2 | 2305
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 11171.6618 | 11171.6618 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 13025.9655 | 24197.6273 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 7317.4727 | 31515.1 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 345.3333 | 31860.4333 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | -456.23 | 31404.2033 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 31404.2033 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 31404.2033 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 31404.2033 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 28 | 31432.2033 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 11171.6618 | 13025.9655 | 7317.4727 | 345.3333 | -456.23 | 0 | 0 | 0 | 28 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-1988
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Texco Construction Pty Ltd |  |  |  |  | Steel | 1319999.3261 | 0 | 1311145.6136 | 0
Estimate Code |  | E00012972 |  |  |  |  | Bolts | 69999.9297 | 0 | 65195.1364 | 0
Contract Code |  | J-1988 |  |  |  |  | Purlin | 540000.0228 | 0 | 529914.5364 | 0
Contract Name |  | 427-451 Somerville Road, Tottenham- Stage 3 Freeze |  |  |  |  | Labour | 280000.3047 | 0 | 228566.88 | 23641.92
Customer |  | Texco Construction Pty Ltd |  |  |  |  | Processing | 159999.8516 | 0 | 151340.22 | 0
Start Date |  | 12 Nov 2023 |  |  |  |  | Rigging | 1009999.3125 | 0 | 981394.6455 | 0
Completion Date |  | 25 Sep 2023 |  |  |  |  | Freight | 29999.6777 | 0 | 27288.2673 | 0
Budgeted Revenue |  | 4677999.96 |  |  |  |  | Shop Drawings | 46000.1484 | 0 | 42500 | 0
Budgeted Job Expenditure |  | 3864498.6304 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.39% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 618.5975 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 603.8374 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.39% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 369999.8584 | 0 | 367957.0364 | 0
[7 empty] | Grates | 0 | 0 | 12855 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2500 | 0 | 0 | 0
[7 empty] | Special Paint | 26000 | 0 | 23150 | 0
[7 empty] | Quality Assurance | 10000.2471 | 0 | 7447 | 0
[7 empty] | OH & Profit | 813501.3209 | 0 | 0 | 0
[7 empty] | Total | 4677999.9999 | 0 | 3748754.3355 | 23641.92
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 4677999.97 | 4677999.97 | 3864498.6304 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 0 | 747 | 747 | 0.01933%
May 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 0 | 103325.6864 | 104072.6864 | 2.693%
Jun 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 102500 | 102500 | 23183.25 | 127255.9364 | 3.293%
Jul 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 102500 | 887288.1467 | 1014544.083 | 26.25%
Aug 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 1442000 | 1544500 | 723115.3048 | 1737659.3879 | 44.96%
Sep 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 2077500 | 3622000 | 1279118.45 | 3016777.8379 | 78.06%
Oct 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 815440 | 4437440 | 497428.7473 | 3514206.5852 | 90.94%
Nov 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 4437440 | 122481.9864 | 3636688.5715 | 94.11%
Dec 2024 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 4437440 | 34068.6591 | 3670757.2306 | 94.99%
Jan 2025 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 4437440 | 22406.8712 | 3693164.1018 | 95.57%
Feb 2025 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 4437440 | 67907.6909 | 3761071.7927 | 97.32%
Mar 2025 | 0 | 4677999.97 | 0 | 3864498.6304 | 813501.3396 | 17.39% | 0 | 4437440 | 11324.4727 | 3772396.2655 | 97.62%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 904.2482 | 0 | 904.2482 | 747
May 2024 | 125980.6434 | 0 | 125980.6434 | 104072.6864
Jun 2024 | 154044.1137 | 102500 | 51544.1137 | 42580.6238
Jul 2024 | 1228112.0124 | 102500 | 1125612.0124 | 929868.7705
Aug 2024 | 2103447.6505 | 1544500 | 558947.6505 | 461746.9952
Sep 2024 | 3651828.6031 | 3622000 | 29828.6031 | 24641.4272
Oct 2024 | 4253969.2396 | 4437440 | -183470.7604 | -151565.3072
Nov 2024 | 4402234.4567 | 4437440 | -35205.5433 | -29083.3208
Dec 2024 | 4443474.7834 | 4437440 | 6034.7834 | 4985.3383
Jan 2025 | 4470598.4424 | 4437440 | 33158.4424 | 27392.2095
Feb 2025 | 4552801.1306 | 4437440 | 115361.1306 | 95299.9004
Mar 2025 | 4566509.4763 | 4437440 | 129069.4763 | 106624.3731
Job Profitability Summary
| Beginning | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102500 | 0 | 1442000 | 2077500 | 815440 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -183470.7604 | -35205.5433 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183470.7604 | 35205.5433 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747 | 104072.6864 | 42580.6238 | 929868.7705 | 461746.9952 | 24641.4272 | -151565.3072 | -29083.3208 | 4985.3383 | 27392.2095 | 95299.9004 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 747 | 103325.6864 | 23183.25 | 887288.1467 | 723115.3048 | 1279118.45 | 497428.7473 | 122481.9864 | 34068.6591 | 22406.8712 | 67907.6909 | 11324.4727 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 747 | 104072.6864 | 42580.6238 | 929868.7705 | 461746.9952 | 24641.4272 | -151565.3072 | -29083.3208 | 4985.3383 | 27392.2095 | 95299.9004 | 106624.3731 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84675.3126 | 0 | 1191237.0801 | 1716224.018 | 673635.4817 | -6.6939e-10 | 7.0031e-10 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0.01933% | 2.693% | 3.293% | 26.25% | 44.96% | 78.06% | 90.94% | 94.11% | 94.99% | 95.57% | 97.32% | 97.62% | 97.62%

## J-1989
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Mannfield Group |  |  |  |  | Steel | 4093.8175 | 0 | 0 | 0
Estimate Code |  | E00013601 |  |  |  |  | Bolts | 252.1764 | 0 | 0 | 0
Contract Code |  | J-1989 |  |  |  |  | Purlin | 2887.46 | 0 | 0 | 0
Contract Name |  | 1161 High Street Road, Wantirna South - Extra |  |  |  |  | Labour | 2063.2993 | 0 | 325.62 | 0
Customer |  | Mannfield Group |  |  |  |  | Processing | 621.4347 | 0 | 258.75 | 0
Start Date | [6 empty] | Rigging | 6000 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 1000 | 0 | 0 | 0
Budgeted Revenue |  | 22500.01 |  |  |  |  | Shop Drawings | 693.4851 | 0 | 180 | 0
Budgeted Job Expenditure |  | 17661.2069 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 21.51% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 2.9285 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 21.51% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 49.5346 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 4838.7946 | 0 | 0 | 0
[7 empty] | Total | 22500.0022 | 0 | 764.37 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 22500 | 22500 | 17661.2069 | 17661.2069 | 4838.7931 | 21.51% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 22500 | 0 | 17661.2069 | 4838.7931 | 21.51% | 0 | 0 | 143.75 | 143.75 | 0.8139%
May 2024 | 0 | 22500 | 0 | 17661.2069 | 4838.7931 | 21.51% | 0 | 0 | 0 | 143.75 | 0.8139%
Jun 2024 | 0 | 22500 | 0 | 17661.2069 | 4838.7931 | 21.51% | 0 | 0 | 0 | 143.75 | 0.8139%
Jul 2024 | 0 | 22500 | 0 | 17661.2069 | 4838.7931 | 21.51% | 0 | 0 | 120 | 263.75 | 1.493%
Aug 2024 | 0 | 22500 | 0 | 17661.2069 | 4838.7931 | 21.51% | 0 | 0 | 115 | 378.75 | 2.145%
Sep 2024 | 0 | 22500 | 0 | 17661.2069 | 4838.7931 | 21.51% | 0 | 0 | 205.62 | 584.37 | 3.309%
Oct 2024 | 0 | 22500 | 0 | 17661.2069 | 4838.7931 | 21.51% | 0 | 0 | 0 | 584.37 | 3.309%
Nov 2024 | 0 | 22500 | 0 | 17661.2069 | 4838.7931 | 21.51% | 0 | 0 | 180 | 764.37 | 4.328%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2024 | 183.1344 | 0 | 183.1344 | 143.75
May 2024 | 183.1344 | 0 | 183.1344 | 143.75
Jun 2024 | 183.1344 | 0 | 183.1344 | 143.75
Jul 2024 | 336.0119 | 0 | 336.0119 | 263.75
Aug 2024 | 482.5194 | 0 | 482.5194 | 378.75
Sep 2024 | 744.4749 | 0 | 744.4749 | 584.37
Oct 2024 | 744.4749 | 0 | 744.4749 | 584.37
Nov 2024 | 973.791 | 0 | 973.791 | 764.37
Job Profitability Summary
| Beginning | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 143.75 | 143.75 | 143.75 | 263.75 | 378.75 | 584.37 | 584.37 | 0
Construction Costs | 0 | 143.75 | 0 | 0 | 120 | 115 | 205.62 | 0 | 180 | #VALUE!
Closing WIP | Difference (GP Exc) | 143.75 | 143.75 | 143.75 | 263.75 | 378.75 | 584.37 | 584.37 | 764.37 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0.8139% | 0.8139% | 0.8139% | 1.493% | 2.145% | 3.309% | 3.309% | 4.328% | 4.328%

## J-1999
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Able Constructions & Management Pty Ltd |  |  |  |  | Steel | 173110.2043 | 0 | 53684.7636 | 0
Estimate Code |  | E00008172 |  |  |  |  | Bolts | 11985.8302 | 0 | 4779.7727 | 0
Contract Code |  | J-1999 |  |  |  |  | Purlin | 60929.0301 | 0 | 0 | 0
Contract Name |  | 35 Decco Drive, Campbellfield |  |  |  |  | Labour | 67387.9707 | 0 | 2359.29 | 0
Customer |  | Able Constructions & Management Pty Ltd |  |  |  |  | Processing | 32154.3398 | 0 | 9270.1227 | 0
Start Date |  | 30 Mar 2020 |  |  |  |  | Rigging | 75955.2812 | 0 | 0 | 0
Completion Date |  | 28 Oct 2019 |  |  |  |  | Freight | 6525.4546 | 0 | 750 | 0
Budgeted Revenue |  | 570000 |  |  |  |  | Shop Drawings | 11949.3809 | 0 | 8360 | 0
Budgeted Job Expenditure |  | 469292.7884 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.67% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 75.3182 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 57.9149 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.67% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 4067.091 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 7432.9546 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 17795.2468 | 0 | 0 | 0
[7 empty] | OH & Profit | 100707.2163 | 0 | 0 | 0
[7 empty] | Total | 570000.0005 | 0 | 79203.9491 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 570000 | 570000 | 469292.7884 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Mar 2020 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Apr 2020 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
May 2020 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jun 2020 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jul 2020 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Aug 2020 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Sep 2020 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Oct 2020 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Nov 2020 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Dec 2020 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jan 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Feb 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Mar 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Apr 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
May 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jun 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jul 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Aug 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Sep 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Oct 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Nov 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Dec 2021 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jan 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Feb 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Mar 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Apr 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
May 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jun 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jul 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Aug 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Sep 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Oct 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Nov 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Dec 2022 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jan 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Feb 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Mar 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 675.0455 | 675.0455 | 0.1438%
Jul 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 127.29 | 802.3355 | 0.171%
Aug 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 1537 | 2339.3355 | 0.4985%
Sep 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 8360 | 10699.3355 | 2.28%
Oct 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 745.5 | 11444.8355 | 2.439%
Nov 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 11444.8355 | 2.439%
Dec 2024 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 0 | 11444.8355 | 2.439%
Jan 2025 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 1240.25 | 12685.0855 | 2.703%
Feb 2025 | 0 | 570000 | 0 | 469292.7884 | 100707.2116 | 17.67% | 0 | 0 | 66434.8636 | 79119.9491 | 16.86%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2020 | 0 | 0 | 0 | 0
Apr 2020 | 0 | 0 | 0 | 0
May 2020 | 0 | 0 | 0 | 0
Jun 2020 | 0 | 0 | 0 | 0
Jul 2020 | 0 | 0 | 0 | 0
Aug 2020 | 0 | 0 | 0 | 0
Sep 2020 | 0 | 0 | 0 | 0
Oct 2020 | 0 | 0 | 0 | 0
Nov 2020 | 0 | 0 | 0 | 0
Dec 2020 | 0 | 0 | 0 | 0
Jan 2021 | 0 | 0 | 0 | 0
Feb 2021 | 0 | 0 | 0 | 0
Mar 2021 | 0 | 0 | 0 | 0
Apr 2021 | 0 | 0 | 0 | 0
May 2021 | 0 | 0 | 0 | 0
Jun 2021 | 0 | 0 | 0 | 0
Jul 2021 | 0 | 0 | 0 | 0
Aug 2021 | 0 | 0 | 0 | 0
Sep 2021 | 0 | 0 | 0 | 0
Oct 2021 | 0 | 0 | 0 | 0
Nov 2021 | 0 | 0 | 0 | 0
Dec 2021 | 0 | 0 | 0 | 0
Jan 2022 | 0 | 0 | 0 | 0
Feb 2022 | 0 | 0 | 0 | 0
Mar 2022 | 0 | 0 | 0 | 0
Apr 2022 | 0 | 0 | 0 | 0
May 2022 | 0 | 0 | 0 | 0
Jun 2022 | 0 | 0 | 0 | 0
Jul 2022 | 0 | 0 | 0 | 0
Aug 2022 | 0 | 0 | 0 | 0
Sep 2022 | 0 | 0 | 0 | 0
Oct 2022 | 0 | 0 | 0 | 0
Nov 2022 | 0 | 0 | 0 | 0
Dec 2022 | 0 | 0 | 0 | 0
Jan 2023 | 0 | 0 | 0 | 0
Feb 2023 | 0 | 0 | 0 | 0
Mar 2023 | 0 | 0 | 0 | 0
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 819.9059 | 0 | 819.9059 | 675.0455
Jul 2024 | 974.5115 | 0 | 974.5115 | 802.3355
Aug 2024 | 2841.3418 | 0 | 2841.3418 | 2339.3355
Sep 2024 | 12995.344 | 0 | 12995.344 | 10699.3355
Oct 2024 | 13900.8235 | 0 | 13900.8235 | 11444.8355
Nov 2024 | 13900.8235 | 0 | 13900.8235 | 11444.8355
Dec 2024 | 13900.8235 | 0 | 13900.8235 | 11444.8355
Jan 2025 | 15407.2231 | 0 | 15407.2231 | 12685.0855
Feb 2025 | 96098.5809 | 0 | 96098.5809 | 79119.9491
Job Profitability Summary
| Beginning | Mar 2020 | Apr 2020 | May 2020 | Jun 2020 | Jul 2020 | Aug 2020 | Sep 2020 | Oct 2020 | Nov 2020 | Dec 2020 | Jan 2021 | Feb 2021 | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675.0455 | 802.3355 | 2339.3355 | 10699.3355 | 11444.8355 | 11444.8355 | 11444.8355 | 12685.0855 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675.0455 | 127.29 | 1537 | 8360 | 745.5 | 0 | 0 | 1240.25 | 66434.8636 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675.0455 | 802.3355 | 2339.3355 | 10699.3355 | 11444.8355 | 11444.8355 | 11444.8355 | 12685.0855 | 79119.9491 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1438% | 0.171% | 0.4985% | 2.28% | 2.439% | 2.439% | 2.439% | 2.703% | 16.86% | 16.86%

## J-2012
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Michael Hill |  |  |  |  | Steel | 4887.1276 | 0 | 0 | 0
Estimate Code |  | E00013336 |  |  |  |  | Bolts | 199.43 | 0 | 142.2364 | 0
Contract Code |  | J-2012 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 220 Sunday Creek Road, Broadford |  |  |  |  | Labour | 2225.069 | 0 | 493 | 167
Customer |  | Michael Hill |  |  |  |  | Processing | 648.1475 | 0 | 1523.75 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 1 Feb 2024 |  |  |  |  | Freight | 1125.356 | 0 | 280 | 0
Budgeted Revenue |  | 14999.99 |  |  |  |  | Shop Drawings | 470.085 | 0 | 0 | 0
Budgeted Job Expenditure |  | 11155.8988 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 25.63% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 1.5669 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 25.63% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1514.5 | 0 | 1005.9727 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 39.1737 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 47.0085 | 0 | 0 | 0
[7 empty] | OH & Profit | 3844.1023 | 0 | 0 | 0
[7 empty] | Total | 14999.9996 | 0 | 3444.9591 | 167
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 15000 | 15000 | 11155.8988 | 11155.8988 | 3844.1011 | 25.63% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 15000 | 0 | 11155.8988 | 3844.1011 | 25.63% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 15000 | 0 | 11155.8988 | 3844.1011 | 25.63% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 15000 | 0 | 11155.8988 | 3844.1011 | 25.63% | 0 | 0 | 2173.9864 | 2173.9864 | 19.49%
Jul 2024 | 0 | 15000 | 0 | 11155.8988 | 3844.1011 | 25.63% | 0 | 0 | 1257.9727 | 3431.9591 | 30.76%
Aug 2024 | 0 | 15000 | 0 | 11155.8988 | 3844.1011 | 25.63% | 0 | 0 | 0 | 3431.9591 | 30.76%
Sep 2024 | 0 | 15000 | 0 | 11155.8988 | 3844.1011 | 25.63% | 0 | 0 | 90 | 3521.9591 | 31.57%
Oct 2024 | 0 | 15000 | 0 | 11155.8988 | 3844.1011 | 25.63% | 0 | 0 | 90 | 3611.9591 | 32.38%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 2923.0989 | 0 | 2923.0989 | 2173.9864
Jul 2024 | 4614.544 | 0 | 4614.544 | 3431.9591
Aug 2024 | 4614.544 | 0 | 4614.544 | 3431.9591
Sep 2024 | 4735.5562 | 0 | 4735.5562 | 3521.9591
Oct 2024 | 4856.5684 | 0 | 4856.5684 | 3611.9591
Job Profitability Summary
| Beginning | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 2173.9864 | 3431.9591 | 3431.9591 | 3521.9591 | 0
Construction Costs | 0 | 0 | 0 | 2173.9864 | 1257.9727 | 0 | 90 | 90 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 2173.9864 | 3431.9591 | 3431.9591 | 3521.9591 | 3611.9591 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 19.49% | 30.76% | 30.76% | 31.57% | 32.38% | 32.38%

## J-2015
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Forte Group Pty Ltd |  |  |  |  | Steel | 122678.5463 | 0 | 32355.0482 | 0
Estimate Code |  | E00013356 |  |  |  |  | Bolts | 13235.5542 | 0 | 1815.5091 | 0
Contract Code |  | J-2015 |  |  |  |  | Purlin | 67068.2547 | 0 | 16414.4727 | 0
Contract Name |  | 1 Zenith Drive, 2-4 Pinnicle Drive, Warrenheip |  |  |  |  | Labour | 58693.5147 | 0 | 19151.61 | 0
Customer |  | Forte Group Pty Ltd |  |  |  |  | Processing | 26409.0537 | 0 | 11007.5 | 0
Start Date |  | 15 Mar 2024 |  |  |  |  | Rigging | 78861.9648 | 9500 | 47920 | 0
Completion Date |  | 6 Feb 2024 |  |  |  |  | Freight | 6860.436 | 0 | 1368.9 | 0
Budgeted Revenue |  | 475499.99 |  |  |  |  | Shop Drawings | 11914.7139 | 0 | 11000 | 0
Budgeted Job Expenditure |  | 391967.6351 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.57% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 59.0109 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 17.6278 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.22% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 150 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 4475.2725 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1770.327 | 0 | 0 | 0
[7 empty] | OH & Profit | 83532.364 | 0 | 0 | 0
[7 empty] | Total | 475500.002 | 9500 | 141183.04 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 475500 | 475500 | 391967.6351 | 391967.6351 | 83532.3649 | 17.57% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 475500 | 0 | 391967.6351 | 83532.3649 | 17.57% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 475500 | 0 | 391967.6351 | 83532.3649 | 17.57% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 475500 | 0 | 391967.6351 | 83532.3649 | 17.57% | 95100 | 95100 | 0 | 0 | 0%
Jun 2024 | 0 | 475500 | 0 | 391967.6351 | 83532.3649 | 17.57% | 0 | 95100 | 12917.58 | 12917.58 | 3.296%
Jul 2024 | 0 | 475500 | 0 | 391967.6351 | 83532.3649 | 17.57% | 0 | 95100 | 32867.25 | 45784.83 | 11.68%
Aug 2024 | 0 | 475500 | 0 | 391967.6351 | 83532.3649 | 17.57% | 0 | 95100 | 79383.8127 | 125168.6427 | 31.93%
Sep 2024 | 9500 | 485000 | 9500 | 401467.6351 | 83532.3649 | 17.22% | 61781.81 | 156881.81 | 10684.25 | 135852.8927 | 33.84%
Oct 2024 | 0 | 485000 | 0 | 401467.6351 | 83532.3649 | 17.22% | 0 | 156881.81 | 818.7273 | 136671.62 | 34.04%
Nov 2024 | 0 | 485000 | 0 | 401467.6351 | 83532.3649 | 17.22% | 0 | 156881.81 | 3692.52 | 140364.14 | 34.96%
Dec 2024 | 0 | 485000 | 0 | 401467.6351 | 83532.3649 | 17.22% | 0 | 156881.81 | 818.9 | 141183.04 | 35.17%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 95100 | -95100 | -78393.527
Jun 2024 | 15670.4502 | 95100 | -79429.5498 | -65475.947
Jul 2024 | 55542.0517 | 95100 | -39557.9483 | -32608.697
Aug 2024 | 151843.3776 | 95100 | 56743.3776 | 46775.1157
Sep 2024 | 164119.4637 | 156881.81 | 7237.6537 | 5991.1004
Oct 2024 | 165108.5415 | 156881.81 | 8226.7315 | 6809.8277
Nov 2024 | 169569.3549 | 156881.81 | 12687.5449 | 10502.3477
Dec 2024 | 170558.6414 | 156881.81 | 13676.8314 | 11321.2477
Job Profitability Summary
| Beginning | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 0 | 0 | 95100 | 0 | 0 | 0 | 61781.81 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | -95100 | -79429.5498 | -39557.9483 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 95100 | 79429.5498 | 39557.9483 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | -78393.527 | -65475.947 | -32608.697 | 46775.1157 | 5991.1004 | 6809.8277 | 10502.3477 | 0
Construction Costs | 0 | 0 | 0 | 0 | 12917.58 | 32867.25 | 79383.8127 | 10684.25 | 818.7273 | 3692.52 | 818.9 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | -78393.527 | -65475.947 | -32608.697 | 46775.1157 | 5991.1004 | 6809.8277 | 10502.3477 | 11321.2477 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 78393.527 | 0 | 0 | 0 | 51468.2653 | 2.4556e-11 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 3.296% | 11.68% | 31.93% | 33.84% | 34.04% | 34.96% | 35.17% | 35.17%

## J-2019
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Melbourne Industrial Builders |  |  |  |  | Steel | 26422.3801 | 0 | 0 | 0
Estimate Code |  | E00013258 |  |  |  |  | Bolts | 3592.5952 | 0 | 0 | 0
Contract Code |  | J-2019 |  |  |  |  | Purlin | 19198.87 | 0 | 0 | 0
Contract Name |  | 754 Princess Highway, Laverton North- Mezzanine |  |  |  |  | Labour | 10762.6229 | 0 | 0 | 0
Customer |  | Melbourne Industrial Builders |  |  |  |  | Processing | 5570.8406 | 0 | 0 | 0
Start Date |  | 21 Feb 2024 |  |  |  |  | Rigging | 18668.71 | 0 | 0 | 0
Completion Date |  | 16 Jan 2024 |  |  |  |  | Freight | 2000.5871 | 0 | 0 | 0
Budgeted Revenue |  | 110000.02 |  |  |  |  | Shop Drawings | 3754.4033 | 0 | 0 | 0
Budgeted Job Expenditure |  | 90659.3173 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.58% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 12.5147 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.58% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 312.8669 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 375.4403 | 0 | 0 | 0
[7 empty] | OH & Profit | 19340.684 | 0 | 0 | 0
[7 empty] | Total | 110000.0004 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 110000 | 110000 | 90659.3173 | 90659.3173 | 19340.6827 | 17.58% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 110000 | 0 | 90659.3173 | 19340.6827 | 17.58% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 110000 | 0 | 90659.3173 | 19340.6827 | 17.58% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 110000 | 0 | 90659.3173 | 19340.6827 | 17.58% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 110000 | 0 | 90659.3173 | 19340.6827 | 17.58% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0%

## J-2024
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Lowther Builders Pty Ltd |  |  |  |  | Steel | 21788.1675 | 0 | 16177.27 | 0
Estimate Code |  | E00012426 |  |  |  |  | Bolts | 543.9644 | 0 | 335.7273 | 0
Contract Code |  | J-2024 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 22 Avoca Street South Yarra |  |  |  |  | Labour | 9315.7046 | 0 | 9511.6 | 0
Customer |  | Lowther Builders Pty Ltd |  |  |  |  | Processing | 3535.7685 | 0 | 2791.25 | 0
Start Date |  | 1 Aug 2023 |  |  |  |  | Rigging | 15500 | 0 | 14886.5 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 500 | 0 | 312.5 | 0
Budgeted Revenue |  | 71999.99 |  |  |  |  | Shop Drawings | 2991.8042 | 0 | 2991 | 0
Budgeted Job Expenditure |  | 58420.3086 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 18.86% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 8.548 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 8.2457 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 18.86% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 4031.2 | 0 | 4099.1091 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 213.7003 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 13579.6982 | 0 | 0 | 0
[7 empty] | Total | 72000.0079 | 0 | 51104.9564 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 72000.01 | 72000.01 | 58420.3086 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 345 | 345 | 0.5905%
Jun 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 730 | 1075 | 1.84%
Jul 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 800 | 1875 | 3.21%
Aug 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 0 | 0 | 1875 | 3.21%
Sep 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 36000 | 36000 | 31550.1523 | 33425.1523 | 57.21%
Oct 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 30000 | 66000 | 15218.99 | 48644.1423 | 83.27%
Nov 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 66000 | -1071 | 47573.1423 | 81.43%
Dec 2024 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 66000 | 0 | 47573.1423 | 81.43%
Jan 2025 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 66000 | 2392.5 | 49965.6423 | 85.53%
Feb 2025 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 66000 | 0 | 49965.6423 | 85.53%
Mar 2025 | 0 | 72000.01 | 0 | 58420.3086 | 13579.7014 | 18.86% | 0 | 66000 | 1139.3091 | 51104.9514 | 87.48%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 425.1947 | 0 | 425.1947 | 345
Jun 2024 | 1324.8819 | 0 | 1324.8819 | 1075
Jul 2024 | 2310.8406 | 0 | 2310.8406 | 1875
Aug 2024 | 2310.8406 | 0 | 2310.8406 | 1875
Sep 2024 | 41194.7721 | 36000 | 5194.7721 | 4215.002
Oct 2024 | 59951.3904 | 66000 | -6048.6096 | -4907.7999
Nov 2024 | 58631.4383 | 66000 | -7368.5617 | -5978.7999
Dec 2024 | 58631.4383 | 66000 | -7368.5617 | -5978.7999
Jan 2025 | 61580.0708 | 66000 | -4419.9292 | -3586.2999
Feb 2025 | 61580.0708 | 66000 | -4419.9292 | -3586.2999
Mar 2025 | 62984.2104 | 66000 | -3015.7896 | -2446.9908
Job Profitability Summary
| Beginning | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 30000 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6048.6096 | -7368.5617 | -7368.5617 | -4419.9292 | -4419.9292 | -3015.7896 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6048.6096 | 7368.5617 | 7368.5617 | 4419.9292 | 4419.9292
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 1075 | 1875 | 1875 | 4215.002 | -4907.7999 | -5978.7999 | -5978.7999 | -3586.2999 | -3586.2999 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 730 | 800 | 0 | 31550.1523 | 15218.99 | -1071 | 0 | 2392.5 | 0 | 1139.3091 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 1075 | 1875 | 1875 | 4215.002 | -4907.7999 | -5978.7999 | -5978.7999 | -3586.2999 | -3586.2999 | -2446.9908 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29210.1503 | 24341.7919 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5905% | 1.84% | 3.21% | 3.21% | 57.21% | 83.27% | 81.43% | 81.43% | 85.53% | 85.53% | 87.48% | 87.48%

## J-2026
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Genis Steel Internal |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2026 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | RESIDENTIAL OVERHEAD |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Genis Steel Internal |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2033
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 0 | 0 | 773.13 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 202.1909 | 0
Contract Code |  | J-2033 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Kingspan |  |  |  |  | Labour | 0 | 0 | 1199.09 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 0 | 0 | 632.5 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 2880 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.40795 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 5686.9109 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 3590.8209 | 3590.8209 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3590.8209 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 711.59 | 4302.4109 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 4302.4109 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 3590.8209 | 0 | 711.59 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2039
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Chick Constructions Pty Ltd |  |  |  |  | Steel | 300 | 0 | 124.5818 | 0
Estimate Code |  | E00013808 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2039 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Sorbent |  |  |  |  | Labour | 300 | 0 | 292.5 | 0
Customer |  | Chick Constructions Pty Ltd |  |  |  |  | Processing | 2300 | 0 | 2212.2273 | 0
Start Date | [6 empty] | Rigging | 2100 | 0 | 11164.5 | 0
Completion Date |  | 15 May 2024 |  |  |  |  | Freight | 0 | 0 | 45 | 0
Budgeted Revenue |  | 6300 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 5000 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.63% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 20.63% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 214 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 1300 | 0 | 0 | 0
[7 empty] | Total | 6300 | 0 | 14052.8091 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 6300 | 6300 | 5000 | 5000 | 1300 | 20.63% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 6300 | 0 | 5000 | 1300 | 20.63% | 0 | 0 | 1967.3636 | 1967.3636 | 39.35%
Jun 2024 | 0 | 6300 | 0 | 5000 | 1300 | 20.63% | 6300 | 6300 | 1915.1455 | 3882.5091 | 77.65%
Jul 2024 | 0 | 6300 | 0 | 5000 | 1300 | 20.63% | 0 | 6300 | 0 | 3882.5091 | 77.65%
Aug 2024 | 0 | 6300 | 0 | 5000 | 1300 | 20.63% | 0 | 6300 | 0 | 3882.5091 | 77.65%
Sep 2024 | 0 | 6300 | 0 | 5000 | 1300 | 20.63% | 0 | 6300 | 228.5 | 4111.0091 | 82.22%
Oct 2024 | 0 | 6300 | 0 | 5000 | 1300 | 20.63% | 9500 | 15800 | 201.8 | 4312.8091 | 86.26%
Nov 2024 | 0 | 6300 | 0 | 5000 | 1300 | 20.63% | 0 | 15800 | 409.5 | 4722.3091 | 94.45%
Dec 2024 | 0 | 6300 | 0 | 5000 | 1300 | 20.63% | 0 | 15800 | 0 | 4722.3091 | 94.45%
Jan 2025 | 0 | 6300 | 0 | 5000 | 1300 | 20.63% | 0 | 15800 | 9244.5 | 13966.8091 | 279.3%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
May 2024 | 2478.8782 | 0 | 2478.8782 | 1967.3636
Jun 2024 | 4891.9615 | 6300 | -1408.0385 | -1117.4909
Jul 2024 | 4891.9615 | 6300 | -1408.0385 | -1117.4909
Aug 2024 | 4891.9615 | 6300 | -1408.0385 | -1117.4909
Sep 2024 | 5179.8715 | 6300 | -1120.1285 | -888.9909
Oct 2024 | 5434.1395 | 15800 | -10365.8605 | -8226.8734
Nov 2024 | 5950.1095 | 15800 | -9849.8905 | -7817.3734
Dec 2024 | 5950.1095 | 15800 | -9849.8905 | -7817.3734
Jan 2025 | 17598.1795 | 15800 | 1798.1795 | 1427.1266
Job Profitability Summary
| Beginning | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Total
Sales | 0 | 0 | 6300 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | -1408.0385 | -1408.0385 | -1408.0385 | -1120.1285 | -10365.8605 | -9849.8905 | -9849.8905 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 1408.0385 | 1408.0385 | 1408.0385 | 1120.1285 | 10365.8605 | 9849.8905 | 9849.8905
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 1967.3636 | -1117.4909 | -1117.4909 | -1117.4909 | -888.9909 | -8226.8734 | -7817.3734 | -7817.3734 | 0
Construction Costs | 0 | 1967.3636 | 1915.1455 | 0 | 0 | 228.5 | 201.8 | 409.5 | 0 | 9244.5 | #VALUE!
Closing WIP | Difference (GP Exc) | 1967.3636 | -1117.4909 | -1117.4909 | -1117.4909 | -888.9909 | -8226.8734 | -7817.3734 | -7817.3734 | 1427.1266 | 0
Total Costruction Cost | #VALUE! | 0 | 5000 | 0 | 0 | 0 | 7539.6825 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 39.35% | 77.65% | 77.65% | 77.65% | 82.22% | 86.26% | 94.45% | 94.45% | 279.3% | 279.3%

## J-2047
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Mitah |  |  |  |  | Steel | 169801.2639 | 0 | 165410.39 | 0
Estimate Code |  | E00013756 |  |  |  |  | Bolts | 7831.2383 | 0 | 7817.0909 | 0
Contract Code |  | J-2047 |  |  |  |  | Purlin | 72000.0007 | 0 | 71424.1818 | 0
Contract Name |  | Lot 3, 4 Ponting Street, Williamstown |  |  |  |  | Labour | 71427.949 | 0 | 65361.91 | 3472
Customer |  | Mitah |  |  |  |  | Processing | 37214.7598 | 0 | 23962.24 | 0
Start Date |  | 19 Jul 2024 |  |  |  |  | Rigging | 157939.1094 | 0 | 147255 | 0
Completion Date |  | 13 May 2024 |  |  |  |  | Freight | 5559.5017 | 0 | 5737.5 | 0
Budgeted Revenue |  | 663699.99 |  |  |  |  | Shop Drawings | 10785.5098 | 0 | 10340 | 0
Budgeted Job Expenditure |  | 552277.83 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.79% |  |  |  |  | Box Frame | 18340 | 0 | 18340 | 0
Estimated Weight |  | 93.6364 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 87.8502 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 21.78% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 500 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 878.4968 | 0 | 0 | 0
[7 empty] | OH & Profit | 111422.1653 | 0 | 0 | 33157.51
[7 empty] | Total | 663699.9946 | 0 | 515648.3127 | 36629.51
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 663699.99 | 663699.99 | 552277.83 | 552277.83 | 111422.16 | 16.79% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 663699.99 | 0 | 552277.83 | 111422.16 | 16.79% | 132739.98 | 132739.98 | 0 | 0 | 0%
Jun 2024 | 0 | 663699.99 | 0 | 552277.83 | 111422.16 | 16.79% | 0 | 132739.98 | 0 | 0 | 0%
Jul 2024 | 0 | 663699.99 | 0 | 552277.83 | 111422.16 | 16.79% | 0 | 132739.98 | 10704.0833 | 10704.0833 | 1.938%
Aug 2024 | 0 | 663699.99 | 0 | 552277.83 | 111422.16 | 16.79% | 0 | 132739.98 | 192950.0994 | 203654.1827 | 36.88%
Sep 2024 | 0 | 663699.99 | 0 | 552277.83 | 111422.16 | 16.79% | 0 | 132739.98 | 193308.5291 | 396962.7118 | 71.88%
Oct 2024 | 0 | 663699.99 | 0 | 552277.83 | 111422.16 | 16.79% | 0 | 132739.98 | 120518.8109 | 517481.5227 | 93.7%
Nov 2024 | 0 | 663699.99 | 0 | 552277.83 | 111422.16 | 16.79% | 0 | 132739.98 | 1076.3 | 518557.8227 | 93.89%
Dec 2024 | 0 | 663699.99 | 0 | 552277.83 | 111422.16 | 16.79% | 0 | 132739.98 | 562.5 | 519120.3227 | 94%
Jan 2025 | 0 | 663699.99 | 0 | 552277.83 | 111422.16 | 16.79% | 0 | 132739.98 | 0 | 519120.3227 | 94%
Feb 2025 | 0 | 663699.99 | -33157.51 | 519120.32 | 144579.67 | 21.78% | 530960 | 663699.98 | 0 | 519120.3227 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
May 2024 | 0 | 132739.98 | -132739.98 | -110455.551
Jun 2024 | 0 | 132739.98 | -132739.98 | -110455.551
Jul 2024 | 12863.6342 | 132739.98 | -119876.3458 | -99751.4677
Aug 2024 | 244741.4538 | 132739.98 | 112001.4738 | 93198.6317
Sep 2024 | 477050.0164 | 132739.98 | 344310.0364 | 286507.1608
Oct 2024 | 621883.5209 | 132739.98 | 489143.5409 | 407025.9717
Nov 2024 | 623176.9647 | 132739.98 | 490436.9847 | 408102.2717
Dec 2024 | 623852.9491 | 132739.98 | 491112.9691 | 408664.7717
Jan 2025 | 623852.9491 | 132739.98 | 491112.9691 | 408664.7717
Feb 2025 | 663699.9935 | 663699.98 | 0.013461 | 0.010529
Job Profitability Summary
| Beginning | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 132739.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530960 | #VALUE!
Less Current Period Overbills | 0 | -132739.98 | -132739.98 | -119876.3458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 132739.98 | 132739.98 | 119876.3458 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | -110455.551 | -110455.551 | -99751.4677 | 93198.6317 | 286507.1608 | 407025.9717 | 408102.2717 | 408664.7717 | 408664.7717 | 0
Construction Costs | 0 | 0 | 0 | 10704.0833 | 192950.0994 | 193308.5291 | 120518.8109 | 1076.3 | 562.5 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | -110455.551 | -110455.551 | -99751.4677 | 93198.6317 | 286507.1608 | 407025.9717 | 408102.2717 | 408664.7717 | 408664.7717 | 0.010529 | 0
Total Costruction Cost | #VALUE! | 110455.551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408664.7612 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 1.938% | 36.88% | 71.88% | 93.7% | 93.89% | 94% | 94% | 100% | 100%

## J-2049
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Valiant Framing |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2049 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Millers Road, Altona North |  |  |  |  | Labour | 0 | 0 | 93.25 | 0
Customer |  | Valiant Framing |  |  |  |  | Processing | 0 | 0 | 762.83 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 856.08 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2053
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 422677.23 | 154660.6802 | 564983.2864 | 0
Estimate Code |  | E00013278 |  |  |  |  | Bolts | 20613.599 | 9719 | 18343.6727 | 0
Contract Code |  | J-2053 |  |  |  |  | Purlin | 119679.0437 | 1200 | 118973.0091 | 0
Contract Name |  | 1 The Esplanade, North Shore Geelong- D & C |  |  |  |  | Labour | 158588.7285 | 65347.2808 | 109717.85 | 14509
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 83691.9902 | 50745.2793 | 88144.5227 | 0
Start Date |  | 26 Feb 2024 |  |  |  |  | Rigging | 219999.7188 | 87840 | 312240 | 0
Completion Date |  | 19 Jan 2024 |  |  |  |  | Freight | 10499.9092 | 5100 | 16901.2045 | 0
Budgeted Revenue |  | 1300000.03 |  |  |  |  | Shop Drawings | 20386.582 | 11214.2305 | 26882.5 | 0
Budgeted Job Expenditure |  | 1074698.8681 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.33% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 214.5956 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 274.3014 |  |  |  |  | Stairs | 11600.0013 | 0 | 0 | 0
Current GP% |  | 19.42% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 2416.1 | 250 | 2543.6273 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2400 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2145.956 | 747.62 | 0 | 0
[7 empty] | OH & Profit | 225301.1378 | 121051.6914 | 0 | 0
[7 empty] | Total | 1299999.9967 | 507875.7821 | 1258729.6727 | 14509
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1300000.01 | 1300000.01 | 1074698.868 | 1074698.868 | 225301.142 | 17.33% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 1300000.01 | 0 | 1074698.868 | 225301.142 | 17.33% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 1300000.01 | 0 | 1074698.868 | 225301.142 | 17.33% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 1300000.01 | 0 | 1074698.868 | 225301.142 | 17.33% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 1300000.01 | 0 | 1074698.868 | 225301.142 | 17.33% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 1300000.01 | 0 | 1074698.868 | 225301.142 | 17.33% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 1300000.01 | 0 | 1074698.868 | 225301.142 | 17.33% | 0 | 0 | 1807.95 | 1807.95 | 0.1682%
Aug 2024 | 0 | 1300000.01 | 0 | 1074698.868 | 225301.142 | 17.33% | 0 | 0 | 190276.3727 | 192084.3227 | 17.87%
Sep 2024 | 0 | 1300000.01 | 0 | 1074698.868 | 225301.142 | 17.33% | 809250 | 809250 | 456197.0455 | 648281.3682 | 60.32%
Oct 2024 | 0 | 1300000.01 | 0 | 1074698.868 | 225301.142 | 17.33% | 471250 | 1280500 | 231350.0409 | 879631.4091 | 81.85%
Nov 2024 | 467200.03 | 1767200.04 | 349655.3407 | 1424354.2087 | 342845.8313 | 19.4% | 0 | 1280500 | 72198.0891 | 951829.4982 | 66.83%
Dec 2024 | 0 | 1767200.04 | 0 | 1424354.2087 | 342845.8313 | 19.4% | 484000 | 1764500 | 267110.1927 | 1218939.6909 | 85.58%
Jan 2025 | 0 | 1767200.04 | 0 | 1424354.2087 | 342845.8313 | 19.4% | 500 | 1765000 | 34925.75 | 1253865.4409 | 88.03%
Feb 2025 | 0 | 1767200.04 | 0 | 1424354.2087 | 342845.8313 | 19.4% | 0 | 1765000 | 10453.0909 | 1264318.5318 | 88.76%
Mar 2025 | 16297 | 1783497.04 | 12790 | 1437144.2087 | 346352.8313 | 19.42% | 0 | 1765000 | 8920.1409 | 1273238.6727 | 88.6%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 2186.9708 | 0 | 2186.9708 | 1807.95
Aug 2024 | 232353.1074 | 0 | 232353.1074 | 192084.3227
Sep 2024 | 784187.8411 | 809250 | -25062.1589 | -20718.672
Oct 2024 | 1064038.3782 | 1280500 | -216461.6218 | -178946.9678
Nov 2024 | 1180937.3799 | 1280500 | -99562.6201 | -80246.9635
Dec 2024 | 1512341.7036 | 1764500 | -252158.2964 | -203238.2994
Jan 2025 | 1555674.1741 | 1765000 | -209325.8259 | -168715.5468
Feb 2025 | 1568643.3517 | 1765000 | -196356.6483 | -158262.4559
Mar 2025 | 1580090.147 | 1765000 | -184909.853 | -149000.5974
Job Profitability Summary
| Beginning | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 809250 | 471250 | 0 | 484000 | 500 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25062.1589 | -216461.6218 | -99562.6201 | -252158.2964 | -209325.8259 | -196356.6483 | -184909.853 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25062.1589 | 216461.6218 | 99562.6201 | 252158.2964 | 209325.8259 | 196356.6483
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1807.95 | 192084.3227 | -20718.672 | -178946.9678 | -80246.9635 | -203238.2994 | -168715.5468 | -158262.4559 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 1807.95 | 190276.3727 | 456197.0455 | 231350.0409 | 72198.0891 | 267110.1927 | 34925.75 | 10453.0909 | 8920.1409 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 1807.95 | 192084.3227 | -20718.672 | -178946.9678 | -80246.9635 | -203238.2994 | -168715.5468 | -158262.4559 | -149000.5974 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669000.0402 | 389578.3367 | -26501.9152 | 390101.5286 | 402.9974 | 0 | -341.7176 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0.1682% | 17.87% | 60.32% | 81.85% | 66.83% | 85.58% | 88.03% | 88.76% | 88.6% | 88.6%

## J-2055
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Protilt Constructions |  |  |  |  | Steel | 106064.339 | 3300 | 109362.1882 | 0
Estimate Code |  | E00013185 |  |  |  |  | Bolts | 4760.0938 | 1200 | 5942.1818 | 0
Contract Code |  | J-2055 |  |  |  |  | Purlin | 16557.1268 | 0 | 16452.7091 | 0
Contract Name |  | 39 Launceston Street, Williamstown |  |  |  |  | Labour | 50204.6316 | 0 | 51067.33 | 1937
Customer |  | Protilt Constructions |  |  |  |  | Processing | 21109.7974 | 0 | 21130 | 0
Start Date |  | 6 Feb 2024 |  |  |  |  | Rigging | 99059.6641 | 0 | 101875 | 0
Completion Date |  | 5 Dec 2023 |  |  |  |  | Freight | 4428.1338 | 0 | 4901.25 | 0
Budgeted Revenue |  | 389999.98 |  |  |  |  | Shop Drawings | 5165.6211 | 0 | 4770 | 0
Budgeted Job Expenditure |  | 312159.3551 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 19.96% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 52.3642 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 52.6904 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 18.71% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 3500.8399 | 0 | 3495.1091 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1309.1044 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 77840.6488 | 0 | 0 | -4018.41
[7 empty] | Total | 390000.0005 | 4500 | 318995.7682 | -2081.41
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 390000 | 390000 | 312159.3551 | 312159.3551 | 77840.6449 | 19.96% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 390000 | 0 | 312159.3551 | 77840.6449 | 19.96% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 390000 | 0 | 312159.3551 | 77840.6449 | 19.96% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 390000 | 0 | 312159.3551 | 77840.6449 | 19.96% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 390000 | 0 | 312159.3551 | 77840.6449 | 19.96% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 390000 | 0 | 312159.3551 | 77840.6449 | 19.96% | 0 | 0 | 100 | 100 | 0.03203%
Jul 2024 | 0 | 390000 | 0 | 312159.3551 | 77840.6449 | 19.96% | 0 | 0 | 11632.46 | 11732.46 | 3.758%
Aug 2024 | 0 | 390000 | 0 | 312159.3551 | 77840.6449 | 19.96% | 0 | 0 | 101184.4555 | 112916.9155 | 36.17%
Sep 2024 | 0 | 390000 | 0 | 312159.3551 | 77840.6449 | 19.96% | 312000 | 312000 | 153867.0436 | 266783.9591 | 85.46%
Oct 2024 | 0 | 390000 | 0 | 312159.3551 | 77840.6449 | 19.96% | 78000 | 390000 | 47066.9364 | 313850.8955 | 100.5%
Nov 2024 | 0 | 390000 | 0 | 312159.3551 | 77840.6449 | 19.96% | 0 | 390000 | 2654.1227 | 316505.0182 | 101.4%
Dec 2024 | 4500 | 394500 | 4500 | 316659.3551 | 77840.6449 | 19.73% | 0 | 390000 | 4172.75 | 320677.7682 | 101.3%
Jan 2025 | 0 | 394500 | 0 | 316659.3551 | 77840.6449 | 19.73% | 0 | 390000 | 0 | 320677.7682 | 101.3%
Feb 2025 | 0 | 394500 | 4018.41 | 320677.7651 | 73822.2349 | 18.71% | 0 | 390000 | 0 | 320677.7682 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 124.9362 | 0 | 124.9362 | 100
Jul 2024 | 14658.0883 | 0 | 14658.0883 | 11732.46
Aug 2024 | 141074.0902 | 0 | 141074.0902 | 112916.9155
Sep 2024 | 333309.7098 | 312000 | 21309.7098 | 17056.475
Oct 2024 | 392113.346 | 390000 | 2113.346 | 1691.5404
Nov 2024 | 395429.3058 | 390000 | 5429.3058 | 4345.6631
Dec 2024 | 399506.2123 | 390000 | 9506.2123 | 7630.497
Jan 2025 | 399506.2123 | 390000 | 9506.2123 | 7630.497
Feb 2025 | 394500.0038 | 390000 | 4500.0038 | 3657.9244
Job Profitability Summary
| Beginning | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312000 | 78000 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 11732.46 | 112916.9155 | 17056.475 | 1691.5404 | 4345.6631 | 7630.497 | 7630.497 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 100 | 11632.46 | 101184.4555 | 153867.0436 | 47066.9364 | 2654.1227 | 4172.75 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 100 | 11732.46 | 112916.9155 | 17056.475 | 1691.5404 | 4345.6631 | 7630.497 | 7630.497 | 3657.9244 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249727.4841 | 62431.871 | 0 | 887.9161 | 0 | 3972.5726 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0.03203% | 3.758% | 36.17% | 85.46% | 100.5% | 101.4% | 101.3% | 101.3% | 100% | 100%

## J-2061
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Qanstruct (Aust) Pty Ltd |  |  |  |  | Steel | 13999998.2805 | 0 | 1591095.9155 | 0
Estimate Code |  | E00012647 |  |  |  |  | Bolts | 650002.25 | 0 | 135980.7091 | 0
Contract Code |  | J-2061 |  |  |  |  | Purlin | 2200000.2401 | 0 | 409523.4455 | 0
Contract Name |  | Lot 2, 1005 Boundary Road, Tarneit- ALDI DC |  |  |  |  | Labour | 5000000.4375 | 0 | 422599.55 | 13985
Customer |  | Qanstruct (Aust) Pty Ltd |  |  |  |  | Processing | 2800001.875 | 0 | 277045.7091 | 0
Start Date |  | 21 Aug 2023 |  |  |  |  | Rigging | 12000000 | 0 | 1523692.4 | 0
Completion Date |  | 29 Jun 2023 |  |  |  |  | Freight | 300002.125 | 0 | 55081.6045 | 0
Budgeted Revenue |  | 46930604.61 |  |  |  |  | Shop Drawings | 680000 | 0 | 424500 | 0
Budgeted Job Expenditure |  | 39467410.6191 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.9% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 6903.834 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 1834.9676 |  |  |  |  | Stairs | 600000 | 0 | 0 | 0
Current GP% |  | 15.9% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 500000 | 0 | 0 | 0
[7 empty] | Grates | 600000 | 0 | 11665 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 97404.4941 | 0 | 2697.9364 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 40000.8125 | 0 | 3619 | 0
[7 empty] | OH & Profit | 7463194.049 | 0 | 0 | 0
[7 empty] | Total | 46930604.5637 | 0 | 4857501.27 | 13985
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 46930604.62 | 46930604.62 | 39467410.6191 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 66000 | 66000 | 0.1672%
Jul 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 0 | 66000 | 0.1672%
Aug 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 11546.0364 | 77546.0364 | 0.1965%
Sep 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 122899.9773 | 200446.0136 | 0.5079%
Oct 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 0 | 19494.4973 | 219940.5109 | 0.5573%
Nov 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 1000000 | 1000000 | 27958.6673 | 247899.1782 | 0.6281%
Dec 2024 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 1000000 | 2000000 | 496179.1336 | 744078.3118 | 1.885%
Jan 2025 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 3030000 | 5030000 | 1677832.4712 | 2421910.783 | 6.136%
Feb 2025 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 2600000 | 7630000 | 2123114.3564 | 4545025.1394 | 11.52%
Mar 2025 | 0 | 46930604.62 | 0 | 39467410.6191 | 7463194.0009 | 15.9% | 0 | 7630000 | 326461.1273 | 4871486.2667 | 12.34%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 78480.4439 | 0 | 78480.4439 | 66000
Jul 2024 | 78480.4439 | 0 | 78480.4439 | 66000
Aug 2024 | 92209.8084 | 0 | 92209.8084 | 77546.0364
Sep 2024 | 238349.8807 | 0 | 238349.8807 | 200446.0136
Oct 2024 | 261530.7413 | 0 | 261530.7413 | 219940.5109
Nov 2024 | 294776.3265 | 1000000 | -705223.6735 | -593074.6584
Dec 2024 | 884781.7607 | 2000000 | -1115218.2393 | -937869.3613
Jan 2025 | 2879888.3839 | 5030000 | -2150111.6161 | -1808187.6148
Feb 2025 | 5404478.6435 | 7630000 | -2225521.3565 | -1871605.2335
Mar 2025 | 5792672.7978 | 7630000 | -1837327.2022 | -1545144.1063
Job Profitability Summary
| Beginning | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 3030000 | 2600000 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -705223.6735 | -1115218.2393 | -2150111.6161 | -2225521.3565 | -1837327.2022 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705223.6735 | 1115218.2393 | 2150111.6161 | 2225521.3565
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66000 | 66000 | 77546.0364 | 200446.0136 | 219940.5109 | -593074.6584 | -937869.3613 | -1808187.6148 | -1871605.2335 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66000 | 0 | 11546.0364 | 122899.9773 | 19494.4973 | 27958.6673 | 496179.1336 | 1677832.4712 | 2123114.3564 | 326461.1273 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66000 | 66000 | 77546.0364 | 200446.0136 | 219940.5109 | -593074.6584 | -937869.3613 | -1808187.6148 | -1871605.2335 | -1545144.1063 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840973.8366 | 840973.8366 | 2548150.7248 | 2186531.975 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1672% | 0.1672% | 0.1965% | 0.5079% | 0.5573% | 0.6281% | 1.885% | 6.136% | 11.52% | 12.34% | 12.34%

## J-2062
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Impact Designer Homes |  |  |  |  | Steel | 102090.918 | 0 | 101902.3445 | 0
Estimate Code |  | E00013681 |  |  |  |  | Bolts | 9811.2314 | 0 | 5943.6727 | 0
Contract Code |  | J-2062 |  |  |  |  | Purlin | 85000.0346 | 0 | 65468.1455 | 0
Contract Name |  | 492 Fullarton Road, Airport West |  |  |  |  | Labour | 45471.3156 | 0 | 39113.69 | 3325.02
Customer |  | Impact Designer Homes |  |  |  |  | Processing | 22333.6587 | 0 | 20905.66 | 0
Start Date |  | 14 Jun 2024 |  |  |  |  | Rigging | 95000.4297 | 0 | 86000 | 0
Completion Date |  | 19 Apr 2024 |  |  |  |  | Freight | 2000 | 0 | 4590 | 0
Budgeted Revenue |  | 479899.98 |  |  |  |  | Shop Drawings | 6479.2153 | 0 | 5940 | 0
Budgeted Job Expenditure |  | 399502.2607 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.75% |  |  |  |  | Box Frame | 17328.8139 | 0 | 0 | 0
Estimated Weight |  | 53.9935 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 51.4171 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 29.21% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 8086.6502 | 0 | 6515.8818 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 5400.0001 | 0 | 0 | 0
[7 empty] | Other Materials | 500 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 80397.7396 | 0 | 0 | 59797.84
[7 empty] | Total | 479900.0071 | 0 | 336379.3945 | 63122.86
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 479900 | 479900 | 399502.2607 | 399502.2607 | 80397.7393 | 16.75% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 479900 | 0 | 399502.2607 | 80397.7393 | 16.75% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 479900 | 0 | 399502.2607 | 80397.7393 | 16.75% | 0 | 0 | 121667.5385 | 121667.5385 | 30.45%
Aug 2024 | 0 | 479900 | 0 | 399502.2607 | 80397.7393 | 16.75% | 167965 | 167965 | 141150.5345 | 262818.073 | 65.79%
Sep 2024 | 0 | 479900 | 0 | 399502.2607 | 80397.7393 | 16.75% | 134372 | 302337 | 1294.3145 | 264112.3876 | 66.11%
Oct 2024 | 0 | 479900 | 0 | 399502.2607 | 80397.7393 | 16.75% | 0 | 302337 | 0 | 264112.3876 | 66.11%
Nov 2024 | 0 | 479900 | 0 | 399502.2607 | 80397.7393 | 16.75% | 0 | 302337 | 25069.9245 | 289182.3121 | 72.39%
Dec 2024 | 0 | 479900 | 0 | 399502.2607 | 80397.7393 | 16.75% | 129573 | 431910 | 49684.1091 | 338866.4212 | 84.82%
Jan 2025 | 0 | 479900 | 0 | 399502.2607 | 80397.7393 | 16.75% | 0 | 431910 | 810 | 339676.4212 | 85.02%
Feb 2025 | 0 | 479900 | -59797.84 | 339704.4207 | 140195.5793 | 29.21% | 47990 | 479900 | 28 | 339704.4212 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 146152.4939 | 0 | 146152.4939 | 121667.5385
Aug 2024 | 315708.8348 | 167965 | 147743.8348 | 122992.2818
Sep 2024 | 317263.6234 | 302337 | 14926.6234 | 12425.9633
Oct 2024 | 317263.6234 | 302337 | 14926.6234 | 12425.9633
Nov 2024 | 347378.7391 | 302337 | 45041.7391 | 37495.8879
Dec 2024 | 407061.5151 | 431910 | -24848.4849 | -20685.6135
Jan 2025 | 408034.5234 | 431910 | -23875.4766 | -19875.6135
Feb 2025 | 479900.0007 | 479900 | 0.00066697 | 0.00047212
Job Profitability Summary
| Beginning | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 167965 | 134372 | 0 | 0 | 129573 | 0 | 47990 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24848.4849 | -23875.4766 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24848.4849 | 23875.4766
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 121667.5385 | 122992.2818 | 12425.9633 | 12425.9633 | 37495.8879 | -20685.6135 | -19875.6135 | 0
Construction Costs | 0 | 0 | 121667.5385 | 141150.5345 | 1294.3145 | 0 | 25069.9245 | 49684.1091 | 810 | 28 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 121667.5385 | 122992.2818 | 12425.9633 | 12425.9633 | 37495.8879 | -20685.6135 | -19875.6135 | 0.00047212 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 139825.7913 | 111860.633 | 0 | 0 | 107865.6104 | 0 | -19847.6139 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 30.45% | 65.79% | 66.11% | 66.11% | 72.39% | 84.82% | 85.02% | 100% | 100%

## J-2064
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | CIP Constructions Group |  |  |  |  | Steel | 0.001 | 0 | 0 | 0
Estimate Code |  | E00013175 |  |  |  |  | Bolts | 20550 | 0 | 0 | 0
Contract Code |  | J-2064 |  |  |  |  | Purlin | 215000 | 0 | 0 | 0
Contract Name |  | Hobson Engineering, Perth WA |  |  |  |  | Labour | 0 | 0 | 516.5 | 0
Customer |  | CIP Constructions Group |  |  |  |  | Processing | 0 | 0 | 575 | 0
Start Date | [6 empty] | Rigging | 307732 | 0 | 0 | 0
Completion Date |  | 1 Dec 2023 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 25100 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 216 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 582995 | 0 | 667243.3118 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 20000 | 0 | 0 | 0
[7 empty] | OH & Profit | 413522.999 | 0 | 0 | 0
[7 empty] | Total | 1584900 | 0 | 668334.8118 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 102993.1364 | 102993.1364 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 7624.53 | 110617.6664 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 5849.49 | 116467.1564 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 111227.5518 | 227694.7082 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 961824 | 961824 | 236182.1436 | 463876.8518 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 961824 | 204457.96 | 668334.8118 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | -102712.5 | 859111.5 | 0 | 668334.8118 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 961824 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 961824 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 859111.5 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 961824 | 0 | -102712.5 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 102993.1364 | 7624.53 | 5849.49 | 111227.5518 | 236182.1436 | 204457.96 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2066
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | GSR Steel Allocation |  |  |  |  | Steel | 0 | 0 | 5802.7745 | 0
Estimate Code |  | E00013951 |  |  |  |  | Bolts | 0 | 0 | 130.6545 | 0
Contract Code |  | J-2066 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 45-65 O'Herns Road Somerton |  |  |  |  | Labour | 0 | 0 | 3085.63 | 0
Customer |  | GSR Steel Allocation |  |  |  |  | Processing | 0 | 0 | 3105 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 3120 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 2021.25 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 2995 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 1.7863 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 1287.1273 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 445 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 21992.4364 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 4005 | 4005 | 2313.4727 | 2313.4727 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 920 | 4925 | 86 | 2399.4727 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 4925 | 2380.8227 | 4780.2955 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 4925 | 160 | 4940.2955 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 4925 | 0 | 4940.2955 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 4925 | 6707.7482 | 11648.0436 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 4925 | 1599.3518 | 13247.3955 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 5130 | 10055 | 1092.5 | 14339.8955 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 9804 | 19859 | 7327.5409 | 21667.4364 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 1578 | 21437 | 325 | 21992.4364 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jun 2024 | #DIV/0! | 4005 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 4925 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 4925 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 4925 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 4925 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 4925 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 4925 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 10055 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 19859 | #DIV/0! | #DIV/0!
Mar 2025 | #DIV/0! | 21437 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 4005 | 920 | 0 | 0 | 0 | 0 | 0 | 5130 | 9804 | 1578 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 2313.4727 | 86 | 2380.8227 | 160 | 0 | 6707.7482 | 1599.3518 | 1092.5 | 7327.5409 | 325 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2072
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Gama Homes Pty Ltd |  |  |  |  | Steel | 8038.2264 | 2400 | 0 | 0
Estimate Code |  | E00012344 |  |  |  |  | Bolts | 279.3763 | 0 | 0 | 0
Contract Code |  | J-2072 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 10 Eureka Street, Richmond |  |  |  |  | Labour | 2301.3352 | 0 | 0 | 0
Customer |  | Gama Homes Pty Ltd |  |  |  |  | Processing | 1888.463 | 0 | 0 | 0
Start Date |  | 19 Jun 2023 |  |  |  |  | Rigging | 7500 | 0 | 3340 | 0
Completion Date |  | 13 Apr 2023 |  |  |  |  | Freight | 750 | 0 | 157.5 | 0
Budgeted Revenue |  | 29500.01 |  |  |  |  | Shop Drawings | 1097.5498 | 0 | 650 | 0
Budgeted Job Expenditure |  | 22457.678 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 23.87% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 2.1951 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 23.51% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 547.85 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 54.8775 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 7042.3224 | 600 | 0 | 0
[7 empty] | Total | 29500.0006 | 3000 | 4147.5 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 29500 | 29500 | 22457.678 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 29500 | 0 | 22457.678 | 7042.322 | 23.87% | 0 | 0 | 650 | 650 | 2.894%
Aug 2024 | 3000 | 32500 | 2400 | 24857.678 | 7642.322 | 23.51% | 0 | 0 | 0 | 650 | 2.615%
Sep 2024 | 0 | 32500 | 0 | 24857.678 | 7642.322 | 23.51% | 0 | 0 | 3340 | 3990 | 16.05%
Oct 2024 | 0 | 32500 | 0 | 24857.678 | 7642.322 | 23.51% | 0 | 0 | 0 | 3990 | 16.05%
Nov 2024 | 0 | 32500 | 0 | 24857.678 | 7642.322 | 23.51% | 0 | 0 | 0 | 3990 | 16.05%
Dec 2024 | 0 | 32500 | 0 | 24857.678 | 7642.322 | 23.51% | 0 | 0 | 157.5 | 4147.5 | 16.68%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 853.8283 | 0 | 853.8283 | 650
Aug 2024 | 849.838 | 0 | 849.838 | 650
Sep 2024 | 5216.698 | 0 | 5216.698 | 3990
Oct 2024 | 5216.698 | 0 | 5216.698 | 3990
Nov 2024 | 5216.698 | 0 | 5216.698 | 3990
Dec 2024 | 5422.6203 | 0 | 5422.6203 | 4147.5
Job Profitability Summary
| Beginning | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 650 | 3990 | 3990 | 3990 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 3340 | 0 | 0 | 157.5 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 650 | 3990 | 3990 | 3990 | 4147.5 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.894% | 2.615% | 16.05% | 16.05% | 16.05% | 16.68% | 16.68%

## J-2082
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Mitah |  |  |  |  | Steel | 15639.4112 | 0 | 5418.8182 | 0
Estimate Code |  | E00012120 |  |  |  |  | Bolts | 631.6467 | 0 | 215.5 | 0
Contract Code |  | J-2082 |  |  |  |  | Purlin | 2258.97 | 0 | 0 | 0
Contract Name |  | 202 Osborne Street, Williamstown |  |  |  |  | Labour | 5386.5701 | 0 | 5459.77 | 0
Customer |  | Mitah |  |  |  |  | Processing | 2549.1456 | 0 | 1940 | 0
Start Date |  | 24 Apr 2023 |  |  |  |  | Rigging | 10000 | 0 | 6292.8 | 0
Completion Date |  | 10 Feb 2023 |  |  |  |  | Freight | 1000 | 0 | 2315 | 0
Budgeted Revenue |  | 52000 |  |  |  |  | Shop Drawings | 2481.469 | 0 | 2060 | 0
Budgeted Job Expenditure |  | 41238.0732 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.7% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 5.6517 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 2.3671 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 20.7% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 274.0734 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 8778.7156 | 0 | 0 | 0
[7 empty] | Total | 49000.0015 | 0 | 23701.8882 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 52000 | 52000 | 41238.0732 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 496 | 496 | 1.203%
Sep 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 820 | 1316 | 3.191%
Oct 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 1316 | 3.191%
Nov 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 1316 | 3.191%
Dec 2024 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 0 | 1316 | 3.191%
Jan 2025 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 0 | 13001.4482 | 14317.4482 | 34.72%
Feb 2025 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 40000 | 40000 | 8811.64 | 23129.0882 | 56.09%
Mar 2025 | 0 | 52000 | 0 | 41238.0732 | 10761.9268 | 20.7% | 0 | 40000 | 572.8 | 23701.8882 | 57.48%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 625.4414 | 0 | 625.4414 | 496
Sep 2024 | 1659.4374 | 0 | 1659.4374 | 1316
Oct 2024 | 1659.4374 | 0 | 1659.4374 | 1316
Nov 2024 | 1659.4374 | 0 | 1659.4374 | 1316
Dec 2024 | 1659.4374 | 0 | 1659.4374 | 1316
Jan 2025 | 18053.882 | 0 | 18053.882 | 14317.4482
Feb 2025 | 29165.1014 | 40000 | -10834.8986 | -8592.5066
Mar 2025 | 29887.3854 | 40000 | -10112.6146 | -8019.7066
Job Profitability Summary
| Beginning | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10834.8986 | -10112.6146 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10834.8986
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496 | 1316 | 1316 | 1316 | 1316 | 14317.4482 | -8592.5066 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496 | 820 | 0 | 0 | 0 | 13001.4482 | 8811.64 | 572.8 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496 | 1316 | 1316 | 1316 | 1316 | 14317.4482 | -8592.5066 | -8019.7066 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31721.5948 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.203% | 3.191% | 3.191% | 3.191% | 3.191% | 34.72% | 56.09% | 57.48% | 57.48%

## J-2084
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Group Technologies Australasia |  |  |  |  | Steel | 6150.1061 | 0 | 1265.0918 | 0
Estimate Code |  | E00013838 |  |  |  |  | Bolts | 334.2758 | 0 | 27.4545 | 0
Contract Code |  | J-2084 |  |  |  |  | Purlin | 2233.1749 | 0 | 0 | 0
Contract Name |  | 156-160 Memorial Drive, Plenty |  |  |  |  | Labour | 2431.8029 | 0 | 646 | 0
Customer |  | Group Technologies Australasia |  |  |  |  | Processing | 1349.0414 | 0 | 230 | 0
Start Date |  | 1 Aug 2024 |  |  |  |  | Rigging | 7500 | 0 | 1210 | 0
Completion Date |  | 21 May 2024 |  |  |  |  | Freight | 400 | 0 | 0 | 0
Budgeted Revenue |  | 28999.99 |  |  |  |  | Shop Drawings | 919.2584 | 0 | 480 | 0
Budgeted Job Expenditure |  | 22576.665 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 22.15% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 3.3938 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.64225 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 22.15% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1193.344 | 0 | 475.4545 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 65.6613 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 6423.3353 | 0 | 0 | 0
[7 empty] | Total | 29000.0001 | 0 | 4334.0009 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 29000 | 29000 | 22576.665 | 22576.665 | 6423.335 | 22.15% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 29000 | 0 | 22576.665 | 6423.335 | 22.15% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 29000 | 0 | 22576.665 | 6423.335 | 22.15% | 5800 | 5800 | 1468.5464 | 1468.5464 | 6.505%
Sep 2024 | 0 | 29000 | 0 | 22576.665 | 6423.335 | 22.15% | 0 | 5800 | 1271.4545 | 2740.0009 | 12.14%
Oct 2024 | 0 | 29000 | 0 | 22576.665 | 6423.335 | 22.15% | 0 | 5800 | 1210 | 3950.0009 | 17.5%
Nov 2024 | 0 | 29000 | 0 | 22576.665 | 6423.335 | 22.15% | 0 | 5800 | 0 | 3950.0009 | 17.5%
Dec 2024 | 0 | 29000 | 0 | 22576.665 | 6423.335 | 22.15% | 0 | 5800 | 240 | 4190.0009 | 18.56%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 1886.3656 | 5800 | -3913.6344 | -3046.7866
Sep 2024 | 3519.5644 | 5800 | -2280.4356 | -1775.3321
Oct 2024 | 5073.8241 | 5800 | -726.1759 | -565.3321
Nov 2024 | 5073.8241 | 5800 | -726.1759 | -565.3321
Dec 2024 | 5382.107 | 5800 | -417.893 | -325.3321
Job Profitability Summary
| Beginning | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | -3913.6344 | -2280.4356 | -726.1759 | -726.1759 | -417.893 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 3913.6344 | 2280.4356 | 726.1759 | 726.1759
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | -3046.7866 | -1775.3321 | -565.3321 | -565.3321 | 0
Construction Costs | 0 | 0 | 1468.5464 | 1271.4545 | 1210 | 0 | 240 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | -3046.7866 | -1775.3321 | -565.3321 | -565.3321 | -325.3321 | 0
Total Costruction Cost | #VALUE! | 0 | 4515.333 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 6.505% | 12.14% | 17.5% | 17.5% | 18.56% | 18.56%

## J-2093
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | VP Homes |  |  |  |  | Steel | 29101.4194 | 0 | 23401.6636 | 0
Estimate Code |  | E00010322 |  |  |  |  | Bolts | 4609.1271 | 0 | 499.3091 | 0
Contract Code |  | J-2093 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 43 Ferdinand Avenue, North Balwyn |  |  |  |  | Labour | 11866.3085 | 0 | 8418.83 | 0
Customer |  | VP Homes |  |  |  |  | Processing | 7195.7629 | 0 | 2646.25 | 0
Start Date |  | 2 Feb 2022 |  |  |  |  | Rigging | 16300 | 0 | 15731.5091 | 0
Completion Date |  | 3 Aug 2021 |  |  |  |  | Freight | 2500 | 0 | 2550 | 0
Budgeted Revenue |  | 98000.01 |  |  |  |  | Shop Drawings | 4562.5996 | 0 | 5471 | 0
Budgeted Job Expenditure |  | 77379.279 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 21.04% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 13.036 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 9.7613 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 21.04% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 918.16 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 325.9 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 20620.7219 | 0 | 0 | 0
[7 empty] | Total | 97999.9994 | 0 | 58718.5618 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 98000 | 98000 | 77379.279 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Feb 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Mar 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Apr 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
May 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Jun 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Jul 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Aug 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Sep 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Oct 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Nov 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Dec 2022 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Jan 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Feb 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Mar 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 1155 | 1155 | 1.493%
Oct 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 0 | 21643.8682 | 22798.8682 | 29.46%
Nov 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 49000 | 49000 | 27150.4391 | 49949.3073 | 64.55%
Dec 2024 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 49000 | 98000 | 761 | 50710.3073 | 65.53%
Jan 2025 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 98000 | 0 | 50710.3073 | 65.53%
Feb 2025 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 98000 | 3445.7545 | 54156.0618 | 69.99%
Mar 2025 | 0 | 98000 | 0 | 77379.279 | 20620.721 | 21.04% | 0 | 98000 | 4562.5 | 58718.5618 | 75.88%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2022 | 0 | 0 | 0 | 0
Mar 2022 | 0 | 0 | 0 | 0
Apr 2022 | 0 | 0 | 0 | 0
May 2022 | 0 | 0 | 0 | 0
Jun 2022 | 0 | 0 | 0 | 0
Jul 2022 | 0 | 0 | 0 | 0
Aug 2022 | 0 | 0 | 0 | 0
Sep 2022 | 0 | 0 | 0 | 0
Oct 2022 | 0 | 0 | 0 | 0
Nov 2022 | 0 | 0 | 0 | 0
Dec 2022 | 0 | 0 | 0 | 0
Jan 2023 | 0 | 0 | 0 | 0
Feb 2023 | 0 | 0 | 0 | 0
Mar 2023 | 0 | 0 | 0 | 0
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 1462.7947 | 0 | 1462.7947 | 1155
Oct 2024 | 28874.5141 | 0 | 28874.5141 | 22798.8682
Nov 2024 | 63260.2446 | 49000 | 14260.2446 | 11259.6678
Dec 2024 | 64224.0426 | 98000 | -33775.9574 | -26668.9717
Jan 2025 | 64224.0426 | 98000 | -33775.9574 | -26668.9717
Feb 2025 | 68588.0526 | 98000 | -29411.9474 | -23223.2172
Mar 2025 | 74366.4083 | 98000 | -23633.5917 | -18660.7172
Job Profitability Summary
| Beginning | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49000 | 49000 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33775.9574 | -33775.9574 | -29411.9474 | -23633.5917 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33775.9574 | 33775.9574 | 29411.9474
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155 | 22798.8682 | 11259.6678 | -26668.9717 | -26668.9717 | -23223.2172 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155 | 21643.8682 | 27150.4391 | 761 | 0 | 3445.7545 | 4562.5 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155 | 22798.8682 | 11259.6678 | -26668.9717 | -26668.9717 | -23223.2172 | -18660.7172 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38689.6395 | 38689.6395 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.493% | 29.46% | 64.55% | 65.53% | 65.53% | 69.99% | 75.88% | 75.88%

## J-2094
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Protilt Constructions |  |  |  |  | Steel | 30907.78 | 0 | 28486.3673 | 0
Estimate Code |  | E00013882 |  |  |  |  | Bolts | 2344.26 | 0 | 763.3273 | 0
Contract Code |  | J-2094 |  |  |  |  | Purlin | 800 | 0 | 0 | 0
Contract Name |  | 153-163 Fitzgerald Road, Laverton North |  |  |  |  | Labour | 13589.3999 | 0 | 5292.7 | 60
Customer |  | Protilt Constructions |  |  |  |  | Processing | 6837.2998 | 0 | 4036.58 | 0
Start Date |  | 13 Aug 2024 |  |  |  |  | Rigging | 36500 | 0 | 36100 | 0
Completion Date |  | 31 May 2024 |  |  |  |  | Freight | 600 | 0 | 687.5 | 0
Budgeted Revenue |  | 116500 |  |  |  |  | Shop Drawings | 4429.7998 | 0 | 6000 | 0
Budgeted Job Expenditure |  | 96808.5395 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.9% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 13.1376 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 30.11% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 800 | 0 | 0 | 0
[7 empty] | OH & Profit | 19691.4607 | 0 | 0 | 15382.06
[7 empty] | Total | 116500.0002 | 0 | 81366.4745 | 15442.06
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 116500 | 116500 | 96808.5396 | 96808.5396 | 19691.4604 | 16.9% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 116500 | 0 | 96808.5396 | 19691.4604 | 16.9% | 0 | 0 | 126 | 126 | 0.1302%
Aug 2024 | 0 | 116500 | 0 | 96808.5396 | 19691.4604 | 16.9% | 0 | 0 | 13954.1379 | 14080.1379 | 14.54%
Sep 2024 | 0 | 116500 | 0 | 96808.5396 | 19691.4604 | 16.9% | 116500 | 116500 | 65118.84 | 79198.9779 | 81.81%
Oct 2024 | 0 | 116500 | 0 | 96808.5396 | 19691.4604 | 16.9% | 0 | 116500 | 1980 | 81178.9779 | 83.86%
Nov 2024 | 0 | 116500 | 0 | 96808.5396 | 19691.4604 | 16.9% | 0 | 116500 | 0 | 81178.9779 | 83.86%
Dec 2024 | 0 | 116500 | -15382.06 | 81426.4796 | 35073.5205 | 30.11% | 0 | 116500 | 247.5 | 81426.4779 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2024 | 151.6292 | 0 | 151.6292 | 126
Aug 2024 | 16944.1257 | 0 | 16944.1257 | 14080.1379
Sep 2024 | 95308.5437 | 116500 | -21191.4563 | -17609.5617
Oct 2024 | 97691.288 | 116500 | -18808.712 | -15629.5617
Nov 2024 | 97691.288 | 116500 | -18808.712 | -15629.5617
Dec 2024 | 116499.9976 | 116500 | -0.0023911 | -0.0016712
Job Profitability Summary
| Beginning | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 0 | 0 | 116500 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | -21191.4563 | -18808.712 | -18808.712 | -0.0023911 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 21191.4563 | 18808.712 | 18808.712
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 126 | 14080.1379 | -17609.5617 | -15629.5617 | -15629.5617 | 0
Construction Costs | 0 | 126 | 13954.1379 | 65118.84 | 1980 | 0 | 247.5 | #VALUE!
Closing WIP | Difference (GP Exc) | 126 | 14080.1379 | -17609.5617 | -15629.5617 | -15629.5617 | -0.0016712 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 96808.5396 | 0 | 0 | -15382.06 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0.1302% | 14.54% | 81.81% | 83.86% | 83.86% | 100% | 100%

## J-2098
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 237945.4166 | 350 | 187942.4691 | 0
Estimate Code |  | E00012660 |  |  |  |  | Bolts | 18571.7773 | 0 | 29261.2273 | 0
Contract Code |  | J-2098 |  |  |  |  | Purlin | 248902.7372 | 0 | 224328.8727 | 0
Contract Name |  | 89 Lewis Road, Wantirna South |  |  |  |  | Labour | 76736.1133 | 0 | 100102.94 | 20441.68
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 49110.626 | 0 | 56122.5591 | 0
Start Date |  | 17 Nov 2023 |  |  |  |  | Rigging | 213700.5625 | 1650 | 156233.3273 | 0
Completion Date |  | 3 Jul 2023 |  |  |  |  | Freight | 7200.0366 | 0 | 6990 | 0
Budgeted Revenue |  | 1020000.01 |  |  |  |  | Shop Drawings | 12177.5127 | 0 | 12150 | 0
Budgeted Job Expenditure |  | 864844.7976 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.21% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 134.7174 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 128.0254 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.21% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 500 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 155155.2052 | 400 | 0 | 0
[7 empty] | Total | 1019999.9874 | 2400 | 773131.3955 | 20441.68
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1020000 | 1020000 | 864844.7976 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 0 | 0 | 93234.0173 | 93234.0173 | 10.78%
Oct 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 153378 | 153378 | 251071.6718 | 344305.6891 | 39.81%
Nov 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 182088.89 | 335466.89 | 132778.0109 | 477083.7 | 55.16%
Dec 2024 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 145066.66 | 480533.55 | 107004.445 | 584088.145 | 67.54%
Jan 2025 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 135244.45 | 615778 | 34827.5418 | 618915.6868 | 71.56%
Feb 2025 | 0 | 1020000 | 0 | 864844.7976 | 155155.2024 | 15.21% | 11333 | 627111 | 39689.0636 | 658604.7505 | 76.15%
Mar 2025 | 2400 | 1022400 | 2000 | 866844.7976 | 155555.2024 | 15.21% | 0 | 627111 | 134968.325 | 793573.0755 | 91.55%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 109960.4205 | 0 | 109960.4205 | 93234.0173
Oct 2024 | 406074.9441 | 153378 | 252696.9441 | 214258.4681
Nov 2024 | 562673.6443 | 335466.89 | 227206.7543 | 192645.6661
Dec 2024 | 688874.9398 | 480533.55 | 208341.3898 | 176649.9678
Jan 2025 | 729950.625 | 615778 | 114172.625 | 96805.491
Feb 2025 | 776760.0005 | 627111 | 149649.0005 | 126885.4506
Mar 2025 | 935979.6755 | 627111 | 308868.6755 | 261875.2
Job Profitability Summary
| Beginning | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153378 | 182088.89 | 145066.66 | 135244.45 | 11333 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93234.0173 | 214258.4681 | 192645.6661 | 176649.9678 | 96805.491 | 126885.4506 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93234.0173 | 251071.6718 | 132778.0109 | 107004.445 | 34827.5418 | 39689.0636 | 134968.325 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93234.0173 | 214258.4681 | 192645.6661 | 176649.9678 | 96805.491 | 126885.4506 | 261875.2 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130047.2209 | 154390.813 | 123000.1433 | 114672.0186 | 9609.104 | -21.4244 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10.78% | 39.81% | 55.16% | 67.54% | 71.56% | 76.15% | 91.55% | 91.55%

## J-2099
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Khuan M Kon |  |  |  |  | Steel | 163670.7368 | 0 | 165180.0027 | 0
Estimate Code |  | E00012033 |  |  |  |  | Bolts | 8366.4736 | 0 | 4923.5182 | 0
Contract Code |  | J-2099 |  |  |  |  | Purlin | 7751.7623 | 0 | 23694.9545 | 0
Contract Name |  | 3 Gold Court Deer Park, Melbourne- Buddha Hall |  |  |  |  | Labour | 61948.4795 | 0 | 38065.5545 | 14073.35
Customer |  | Khuan M Kon |  |  |  |  | Processing | 33620.7734 | 0 | 18802.5 | 0
Start Date |  | 3 Apr 2023 |  |  |  |  | Rigging | 186998.6562 | 0 | 129785 | 0
Completion Date |  | 20 Jan 2023 |  |  |  |  | Freight | 2999.9595 | 0 | 763.75 | 0
Budgeted Revenue |  | 820000 |  |  |  |  | Shop Drawings | 23256.1992 | 0 | 23000 | 0
Budgeted Job Expenditure |  | 677892.9949 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.33% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 81.281 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 76.895 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.33% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 70714.4807 | 0 | 78805.2818 | 0
[7 empty] | Grates | 114927.0469 | 0 | 45190.8 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1200 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2438.4297 | 0 | 0 | 0
[7 empty] | OH & Profit | 142106.9954 | 0 | 0 | 0
[7 empty] | Total | 819999.9933 | 0 | 528211.3618 | 14073.35
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 819999.99 | 819999.99 | 677892.9949 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 82000 | 82000 | 0 | 0 | 0%
Aug 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 82000 | 15258 | 15258 | 2.251%
Sep 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 82000 | 2343.29 | 17601.29 | 2.596%
Oct 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 82000 | 7000 | 24601.29 | 3.629%
Nov 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 82000 | 167568.3627 | 192169.6527 | 28.35%
Dec 2024 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 0 | 82000 | 141345.5482 | 333515.2009 | 49.2%
Jan 2025 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 574000 | 656000 | 193096.8636 | 526612.0645 | 77.68%
Feb 2025 | 0 | 819999.99 | 0 | 677892.9949 | 142106.9951 | 17.33% | 164000 | 820000 | 15672.6473 | 542284.7118 | 80%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 82000 | -82000 | -67789.3003
Aug 2024 | 18456.541 | 82000 | -63543.459 | -52531.3003
Sep 2024 | 21291.0559 | 82000 | -60708.9441 | -50188.0103
Oct 2024 | 29758.4688 | 82000 | -52241.5312 | -43188.0103
Nov 2024 | 232454.2583 | 82000 | 150454.2583 | 124380.3524
Dec 2024 | 403430.1335 | 82000 | 321430.1335 | 265725.9006
Jan 2025 | 637005.9743 | 656000 | -18994.0257 | -15702.338
Feb 2025 | 655964.0852 | 820000 | -164035.9148 | -135608.2913
Job Profitability Summary
| Beginning | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000 | 0 | 0 | 0 | 0 | 0 | 574000 | 164000 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82000 | -63543.459 | -60708.9441 | -52241.5312 | 0 | 0 | -18994.0257 | -164035.9148 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000 | 63543.459 | 60708.9441 | 52241.5312 | 0 | 0 | 18994.0257
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67789.3003 | -52531.3003 | -50188.0103 | -43188.0103 | 124380.3524 | 265725.9006 | -15702.338 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15258 | 2343.29 | 7000 | 167568.3627 | 141345.5482 | 193096.8636 | 15672.6473 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67789.3003 | -52531.3003 | -50188.0103 | -43188.0103 | 124380.3524 | 265725.9006 | -15702.338 | -135608.2913 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67789.3003 | 0 | 0 | 0 | 0 | 0 | 474525.1022 | 135578.6006 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.251% | 2.596% | 3.629% | 28.35% | 49.2% | 77.68% | 80% | 80%

## J-2100
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Impact Designer Homes |  |  |  |  | Steel | 62751.0253 | 0 | 64815.5182 | 0
Estimate Code |  | E00013992 |  |  |  |  | Bolts | 3195.3879 | 0 | 1341.5091 | 0
Contract Code |  | J-2100 |  |  |  |  | Purlin | 28100.0012 | 0 | 23544.4455 | 0
Contract Name |  | Lot 8, 60 Logistics Street, Keilor Park |  |  |  |  | Labour | 24815.9421 | 0 | 7306.77 | 0
Customer |  | Impact Designer Homes |  |  |  |  | Processing | 12577.8057 | 0 | 8329.7455 | 0
Start Date | [6 empty] | Rigging | 41099.8457 | 0 | 0 | 0
Completion Date |  | 25 Jun 2024 |  |  |  |  | Freight | 1800.0001 | 0 | 6258 | 0
Budgeted Revenue |  | 229000.01 |  |  |  |  | Shop Drawings | 3514.8948 | 0 | 3520 | 0
Budgeted Job Expenditure |  | 193578.4147 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.47% |  |  |  |  | Box Frame | 14900 | 0 | 0 | 0
Estimated Weight |  | 32.0948 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 28.3648 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.47% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | -65.56 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | -3e-05 | 0 | 0 | 0
[7 empty] | Other Materials | 250 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 639.0718 | 0 | 0 | 0
[7 empty] | OH & Profit | 35421.5848 | 0 | 0 | 0
[7 empty] | Total | 228999.9993 | 0 | 115115.9882 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 229000 | 229000 | 193578.4147 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 1525 | 1525 | 0.7878%
Dec 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 10384.4818 | 11909.4818 | 6.152%
Jan 2025 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 61475.16 | 73384.6418 | 37.91%
Feb 2025 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 137400 | 137400 | 41558.8464 | 114943.4882 | 59.38%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 1804.0493 | 0 | 1804.0493 | 1525
Dec 2024 | 14088.7161 | 0 | 14088.7161 | 11909.4818
Jan 2025 | 86812.7937 | 0 | 86812.7937 | 73384.6418
Feb 2025 | 135976.208 | 137400 | -1423.792 | -1203.5607
Job Profitability Summary
| Beginning | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137400 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1423.792 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 1525 | 11909.4818 | 73384.6418 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 1525 | 10384.4818 | 61475.16 | 41558.8464 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 1525 | 11909.4818 | 73384.6418 | -1203.5607 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116147.0488 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0.7878% | 6.152% | 37.91% | 59.38% | 59.38%

## J-2101
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Impact Designer Homes |  |  |  |  | Steel | 62751.0253 | 0 | 53116.6409 | 0
Estimate Code |  | E00013993 |  |  |  |  | Bolts | 3195.3879 | 0 | 1341.3727 | 0
Contract Code |  | J-2101 |  |  |  |  | Purlin | 28100.0012 | 0 | 12915.3909 | 0
Contract Name |  | Lot 9, 66 Logistics Street, Keilor Park |  |  |  |  | Labour | 24815.9421 | 0 | 4050.44 | 0
Customer |  | Impact Designer Homes |  |  |  |  | Processing | 12577.8057 | 0 | 5622.1091 | 0
Start Date | [6 empty] | Rigging | 41099.8457 | 0 | 0 | 0
Completion Date |  | 25 Jun 2024 |  |  |  |  | Freight | 1800.0001 | 0 | 3184.25 | 0
Budgeted Revenue |  | 229000.01 |  |  |  |  | Shop Drawings | 3514.8948 | 0 | 3520 | 0
Budgeted Job Expenditure |  | 193578.4147 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.47% |  |  |  |  | Box Frame | 14900 | 0 | 0 | 0
Estimated Weight |  | 32.0948 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 27.5691 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.47% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | -65.56 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | -3e-05 | 0 | 0 | 0
[7 empty] | Other Materials | 250 | 0 | 89.6091 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 639.0718 | 0 | 0 | 0
[7 empty] | OH & Profit | 35421.5848 | 0 | 0 | 0
[7 empty] | Total | 228999.9993 | 0 | 83839.8127 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 229000 | 229000 | 193578.4147 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 3520 | 3520 | 1.818%
Jan 2025 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 31615.9773 | 35135.9773 | 18.15%
Feb 2025 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 32882.0445 | 68018.0218 | 35.14%
Mar 2025 | 0 | 229000 | 0 | 193578.4147 | 35421.5853 | 15.47% | 0 | 0 | 15821.7909 | 83839.8127 | 43.31%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 4164.1006 | 0 | 4164.1006 | 3520
Jan 2025 | 41565.2686 | 0 | 41565.2686 | 35135.9773
Feb 2025 | 80464.1727 | 0 | 80464.1727 | 68018.0218
Mar 2025 | 99181.0845 | 0 | 99181.0845 | 83839.8127
Job Profitability Summary
| Beginning | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3520 | 35135.9773 | 68018.0218 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 3520 | 31615.9773 | 32882.0445 | 15821.7909 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 3520 | 35135.9773 | 68018.0218 | 83839.8127 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 1.818% | 18.15% | 35.14% | 43.31% | 43.31%

## J-2103
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Tohme Hayek |  |  |  |  | Steel | 0 | 0 | 4901.3909 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 59.1 | 0
Contract Code |  | J-2103 |  |  |  |  | Purlin | 0 | 0 | 328.4273 | 0
Contract Name |  | 122 Berringa Rd Park Orchards |  |  |  |  | Labour | 0 | 0 | 2968.73 | 0
Customer |  | Tohme Hayek |  |  |  |  | Processing | 0 | 0 | 1545 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 1320 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 1.7287 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 11122.6482 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 6833.9182 | 6833.9182 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 4288.73 | 11122.6482 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6833.9182 | 4288.73 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2104
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Genis Steel |  |  |  |  | Steel | 0 | 0 | 8990.2545 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 76.5727 | 0
Contract Code |  | J-2104 |  |  |  |  | Purlin | 0 | 0 | 635.1818 | 0
Contract Name |  | Caretakers Building |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Genis Steel |  |  |  |  | Processing | 0 | 0 | 2292.5 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 8051.5909 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 4356.5 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 3.8283 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 10329.7909 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 34732.3909 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 11994.5091 | 11994.5091 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 11994.5091 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 13342.5 | 25337.0091 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 9011.5182 | 34348.5273 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 34348.5273 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 383.8636 | 34732.3909 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11994.5091 | 0 | 13342.5 | 9011.5182 | 0 | 383.8636 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2109
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Maice Constructions Pty Ltd |  |  |  |  | Steel | 115487.9152 | 0 | 0 | 0
Estimate Code |  | E00014104 |  |  |  |  | Bolts | 6136.7734 | 0 | 4151.4273 | 0
Contract Code |  | J-2109 |  |  |  |  | Purlin | 50000.0403 | 0 | 0 | 0
Contract Name |  | 110 Yale Drive, Epping |  |  |  |  | Labour | 42134.1033 | 0 | 0 | 0
Customer |  | Maice Constructions Pty Ltd |  |  |  |  | Processing | 22174.4917 | 0 | 345 | 0
Start Date |  | 30 Sep 2024 |  |  |  |  | Rigging | 69373.4648 | 0 | 0 | 0
Completion Date |  | 17 Jul 2024 |  |  |  |  | Freight | 2000.0081 | 0 | 0 | 0
Budgeted Revenue |  | 395000.01 |  |  |  |  | Shop Drawings | 8041.1274 | 0 | 12000 | 0
Budgeted Job Expenditure |  | 326550.2681 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.33% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 55.445 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 51.5802 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.33% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 8152.3452 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 3050 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 68449.7316 | 0 | 0 | 0
[7 empty] | Total | 395000.0011 | 0 | 16496.4273 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 395000 | 395000 | 326550.2681 | 326550.2681 | 68449.7319 | 17.33% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 395000 | 0 | 326550.2681 | 68449.7319 | 17.33% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 395000 | 0 | 326550.2681 | 68449.7319 | 17.33% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 395000 | 0 | 326550.2681 | 68449.7319 | 17.33% | 146000 | 146000 | 3000 | 3000 | 0.9187%
Nov 2024 | 0 | 395000 | 0 | 326550.2681 | 68449.7319 | 17.33% | 0 | 146000 | 3000 | 6000 | 1.837%
Dec 2024 | 0 | 395000 | 0 | 326550.2681 | 68449.7319 | 17.33% | 0 | 146000 | 0 | 6000 | 1.837%
Jan 2025 | 0 | 395000 | 0 | 326550.2681 | 68449.7319 | 17.33% | 0 | 146000 | 5000 | 11000 | 3.369%
Feb 2025 | 0 | 395000 | 0 | 326550.2681 | 68449.7319 | 17.33% | 0 | 146000 | 1345 | 12345 | 3.78%
Mar 2025 | 0 | 395000 | 0 | 326550.2681 | 68449.7319 | 17.33% | 0 | 146000 | 4151.4273 | 16496.4273 | 5.052%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 3628.8441 | 146000 | -142371.1559 | -117699.5928
Nov 2024 | 7257.6881 | 146000 | -138742.3119 | -114699.5928
Dec 2024 | 7257.6881 | 146000 | -138742.3119 | -114699.5928
Jan 2025 | 13305.7615 | 146000 | -132694.2385 | -109699.5928
Feb 2025 | 14932.6933 | 146000 | -131067.3067 | -108354.5928
Mar 2025 | 19954.3207 | 146000 | -126045.6793 | -104203.1655
Job Profitability Summary
| Beginning | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 146000 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | -142371.1559 | -138742.3119 | -138742.3119 | -132694.2385 | -131067.3067 | -126045.6793 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 142371.1559 | 138742.3119 | 138742.3119 | 132694.2385 | 131067.3067
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | -117699.5928 | -114699.5928 | -114699.5928 | -109699.5928 | -108354.5928 | 0
Construction Costs | 0 | 0 | 0 | 3000 | 3000 | 0 | 5000 | 1345 | 4151.4273 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | -117699.5928 | -114699.5928 | -114699.5928 | -109699.5928 | -108354.5928 | -104203.1655 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 120699.5928 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0.9187% | 1.837% | 1.837% | 3.369% | 3.78% | 5.052% | 5.052%

## J-2110
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Leomilla |  |  |  |  | Steel | 15103.0173 | 0 | 9311.3409 | 0
Estimate Code |  | E00014162 |  |  |  |  | Bolts | 766.374 | 0 | 118.6364 | 0
Contract Code |  | J-2110 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 5 Thelma Avenue Essendon North |  |  |  |  | Labour | 5543.3553 | 0 | 3171.22 | 0
Customer |  | Leomilla |  |  |  |  | Processing | 2490.7155 | 0 | 1351.25 | 0
Start Date |  | 1 Oct 2024 |  |  |  |  | Rigging | 7500 | 0 | 2925 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 1300 | 0 | 1238.75 | 0
Budgeted Revenue |  | 44999.99 |  |  |  |  | Shop Drawings | 2107.5286 | 0 | 2103 | 0
Budgeted Job Expenditure |  | 36390.878 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 19.13% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 6.0215 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 4.5419 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 19.13% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1429.3501 | 0 | 378.6727 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 150.5377 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 8609.1218 | 0 | 0 | 0
[7 empty] | Total | 45000.0003 | 0 | 20597.87 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 45000 | 45000 | 36390.8781 | 36390.8781 | 8609.1219 | 19.13% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 45000 | 0 | 36390.8781 | 8609.1219 | 19.13% | 0 | 0 | 540 | 540 | 1.484%
Oct 2024 | 0 | 45000 | 0 | 36390.8781 | 8609.1219 | 19.13% | 0 | 0 | 0 | 540 | 1.484%
Nov 2024 | 0 | 45000 | 0 | 36390.8781 | 8609.1219 | 19.13% | 0 | 0 | 13934.025 | 14474.025 | 39.77%
Dec 2024 | 0 | 45000 | 0 | 36390.8781 | 8609.1219 | 19.13% | 20000 | 20000 | 5668.84 | 20142.865 | 55.35%
Jan 2025 | 0 | 45000 | 0 | 36390.8781 | 8609.1219 | 19.13% | 0 | 20000 | 0 | 20142.865 | 55.35%
Feb 2025 | 0 | 45000 | 0 | 36390.8781 | 8609.1219 | 19.13% | 0 | 20000 | 455 | 20597.865 | 56.6%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 667.7498 | 0 | 667.7498 | 540
Oct 2024 | 667.7498 | 0 | 667.7498 | 540
Nov 2024 | 17898.1976 | 0 | 17898.1976 | 14474.025
Dec 2024 | 24908.1356 | 20000 | 4908.1356 | 3969.1414
Jan 2025 | 24908.1356 | 20000 | 4908.1356 | 3969.1414
Feb 2025 | 25470.7766 | 20000 | 5470.7766 | 4424.1414
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 540 | 540 | 14474.025 | 3969.1414 | 3969.1414 | 0
Construction Costs | 0 | 540 | 0 | 13934.025 | 5668.84 | 0 | 455 | #VALUE!
Closing WIP | Difference (GP Exc) | 540 | 540 | 14474.025 | 3969.1414 | 3969.1414 | 4424.1414 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 16173.7236 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 1.484% | 1.484% | 39.77% | 55.35% | 55.35% | 56.6% | 56.6%

## J-2118
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Protilt Constructions |  |  |  |  | Steel | 203692.767 | 0 | 198578.6509 | 0
Estimate Code |  | E00013053 |  |  |  |  | Bolts | 14284.918 | 0 | 13596.6273 | 0
Contract Code |  | J-2118 |  |  |  |  | Purlin | 136170.0317 | 0 | 103186.9727 | 0
Contract Name |  | 50 Bakers Road, Coburg |  |  |  |  | Labour | 97494.4772 | 0 | 96320.32 | 18945.72
Customer |  | Protilt Constructions |  |  |  |  | Processing | 51447.0791 | 0 | 48568.75 | 0
Start Date |  | 30 Nov 2023 |  |  |  |  | Rigging | 140000.0156 | 0 | 141443 | 0
Completion Date |  | 26 Oct 2023 |  |  |  |  | Freight | 4799.98 | 0 | 5758.75 | 0
Budgeted Revenue |  | 886700 |  |  |  |  | Shop Drawings | 16482.707 | 0 | 11000 | 0
Budgeted Job Expenditure |  | 731565.6189 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.5% |  |  |  |  | Box Frame | 58000.0146 | 0 | 53900 | 0
Estimated Weight |  | 109.884 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 104.1332 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.53% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 7984.9076 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1208.7239 | 0 | 0 | 0
[7 empty] | OH & Profit | 155134.3736 | 0 | 0 | 0
[7 empty] | Total | 886699.9953 | 0 | 672353.0709 | 18945.72
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 886699.99 | 886699.99 | 731227.8109 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 0 | 12691.3673 | 12691.3673 | 1.736%
Oct 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 133005 | 133005 | 227771.8764 | 240463.2436 | 32.88%
Nov 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 532020 | 665025 | 316003.9273 | 556467.1709 | 76.1%
Dec 2024 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 177360 | 842385 | 71225.12 | 627692.2909 | 85.84%
Jan 2025 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 842385 | 702.0636 | 628394.3545 | 85.94%
Feb 2025 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 842385 | 57784.4364 | 686178.7909 | 93.84%
Mar 2025 | 0 | 886699.99 | 0 | 731227.8109 | 155472.1791 | 17.53% | 0 | 842385 | 5120 | 691298.7909 | 94.54%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 15389.7801 | 0 | 15389.7801 | 12691.3673
Oct 2024 | 291590.0524 | 133005 | 158585.0524 | 130779.0708
Nov 2024 | 674782.096 | 665025 | 9757.096 | 8046.3065
Dec 2024 | 761150.957 | 842385 | -81234.043 | -66990.6305
Jan 2025 | 762002.292 | 842385 | -80382.708 | -66288.5669
Feb 2025 | 832072.7384 | 842385 | -10312.2616 | -8504.1305
Mar 2025 | 838281.3425 | 842385 | -4103.6575 | -3384.1305
Job Profitability Summary
| Beginning | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133005 | 532020 | 177360 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -81234.043 | -80382.708 | -10312.2616 | -4103.6575 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81234.043 | 80382.708 | 10312.2616
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12691.3673 | 130779.0708 | 8046.3065 | -66990.6305 | -66288.5669 | -8504.1305 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12691.3673 | 227771.8764 | 316003.9273 | 71225.12 | 702.0636 | 57784.4364 | 5120 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12691.3673 | 130779.0708 | 8046.3065 | -66990.6305 | -66288.5669 | -8504.1305 | -3384.1305 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109684.1729 | 438736.6915 | 146262.0571 | 0 | 0 | -4.8203e-11 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.736% | 32.88% | 76.1% | 85.84% | 85.94% | 93.84% | 94.54% | 94.54%

## J-2121
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Richard Crookes Constructions |  |  |  |  | Steel | -1.9662 | 0 | 0 | 0
Estimate Code |  | E00013081 |  |  |  |  | Bolts | 82451 | 0 | 0 | 0
Contract Code |  | J-2121 |  |  |  |  | Purlin | 8804.0024 | 0 | 0 | 0
Contract Name |  | 124 Hollinsworth Road, Marsden Park, NSW- Newcold |  |  |  |  | Labour | 4000 | 0 | 27229.87 | 0
Customer |  | Richard Crookes Constructions |  |  |  |  | Processing | 0 | 0 | 11241.25 | 0
Start Date |  | 7 Dec 2023 |  |  |  |  | Rigging | 964100 | 0 | 0 | 0
Completion Date |  | 6 Nov 2023 |  |  |  |  | Freight | 16000 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 82451 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 670.4894 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 31.6984 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2495715 | 0 | 706077.5091 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 69433 | 0 | 0 | 0
[7 empty] | OH & Profit | 772047.975 | 0 | 0 | 0
[7 empty] | Total | 4495000.0112 | 0 | 744548.6291 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 340716.42 | 340716.42 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 8954.07 | 349670.49 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 227250 | 227250 | 55431.4318 | 405101.9218 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 227250 | 454500 | 227042.6718 | 632144.5936 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 1431675 | 1886175 | 95610.4155 | 727755.0091 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 227250 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 454500 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 1886175 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227250 | 227250 | 1431675 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340716.42 | 8954.07 | 55431.4318 | 227042.6718 | 95610.4155 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2123
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | North |  |  |  |  | Steel | 0 | 0 | 25042.9364 | 0
Estimate Code |  | E00013805 |  |  |  |  | Bolts | 53543 | 0 | 27835.4818 | 0
Contract Code |  | J-2123 |  |  |  |  | Purlin | 197134 | 0 | 117946.6909 | 0
Contract Name |  | Baiada Freezer Store, Beresfield |  |  |  |  | Labour | 2000 | 0 | 3623.52 | 0
Customer |  | North |  |  |  |  | Processing | 0 | 0 | 3687.5409 | 0
Start Date | [6 empty] | Rigging | 418000 | 0 | 171458.6091 | 0
Completion Date |  | 15 May 2024 |  |  |  |  | Freight | 8000 | 0 | 112374.72 | 0
Budgeted Revenue |  | 1869900 |  |  |  |  | Shop Drawings | 27353 | 0 | 0 | 0
Budgeted Job Expenditure |  | 1554043 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.89% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 12.74 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.89% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 839807 | 0 | 575863.06 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 8206 | 0 | 10032.6 | 0
[7 empty] | OH & Profit | 315857 | 0 | 0 | 0
[7 empty] | Total | 1869900 | 0 | 1047865.1591 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1869900 | 1869900 | 1554043 | 1554043 | 315857 | 16.89% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 1869900 | 0 | 1554043 | 315857 | 16.89% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 1869900 | 0 | 1554043 | 315857 | 16.89% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 1869900 | 0 | 1554043 | 315857 | 16.89% | 0 | 0 | 129100 | 129100 | 8.307%
Nov 2024 | 0 | 1869900 | 0 | 1554043 | 315857 | 16.89% | 60150 | 60150 | 0 | 129100 | 8.307%
Dec 2024 | 0 | 1869900 | 0 | 1554043 | 315857 | 16.89% | 0 | 60150 | 5247.5727 | 134347.5727 | 8.645%
Jan 2025 | 0 | 1869900 | 0 | 1554043 | 315857 | 16.89% | 547365 | 607515 | 403714.0964 | 538061.6691 | 34.62%
Feb 2025 | 0 | 1869900 | 0 | 1554043 | 315857 | 16.89% | 354885 | 962400 | 509803.49 | 1047865.1591 | 67.43%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 155339.3889 | 0 | 155339.3889 | 129100
Nov 2024 | 155339.3889 | 60150 | 95189.3889 | 79110.3287
Dec 2024 | 161653.5233 | 60150 | 101503.5233 | 84357.9014
Jan 2025 | 647421.9279 | 607515 | 39906.9279 | 33165.9885
Feb 2025 | 1260842.2425 | 962400 | 298442.2425 | 248030.4176
Job Profitability Summary
| Beginning | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 60150 | 0 | 547365 | 354885 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 129100 | 79110.3287 | 84357.9014 | 33165.9885 | 0
Construction Costs | 0 | 0 | 0 | 129100 | 0 | 5247.5727 | 403714.0964 | 509803.49 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 129100 | 79110.3287 | 84357.9014 | 33165.9885 | 248030.4176 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 49989.6713 | 0 | 454906.0092 | 294939.0609 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 8.307% | 8.307% | 8.645% | 34.62% | 67.43% | 67.43%

## J-2124
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 65218.1975 | 3925 | 68553.53 | 0
Estimate Code |  | E00013366 |  |  |  |  | Bolts | 5608.7695 | 0 | 5184.0909 | 0
Contract Code |  | J-2124 |  |  |  |  | Purlin | 59931.0003 | 0 | 58991.4455 | 0
Contract Name |  | 27 Piper Road, East Bendigo |  |  |  |  | Labour | 30508.9006 | 0 | 32499.18 | 0
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 14284.9756 | 1600 | 14201.25 | 0
Start Date |  | 1 Apr 2024 |  |  |  |  | Rigging | 120901.7891 | 0 | 76000 | 0
Completion Date |  | 12 Feb 2024 |  |  |  |  | Freight | 7499.9994 | 1400 | 4923.1545 | 0
Budgeted Revenue |  | 379999.99 |  |  |  |  | Shop Drawings | 9255.3848 | 0 | 2500 | 0
Budgeted Job Expenditure |  | 314017.5191 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.36% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 29.5102 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 29.8787 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.13% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 1820 | 2128.2455 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 500 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 308.5 | 0 | 0 | 0
[7 empty] | OH & Profit | 65982.4807 | 735 | 0 | 0
[7 empty] | Total | 379999.9975 | 9480 | 264980.8964 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 380000 | 380000 | 314017.5191 | 314017.5191 | 65982.4809 | 17.36% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 380000 | 0 | 314017.5191 | 65982.4809 | 17.36% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 380000 | 0 | 314017.5191 | 65982.4809 | 17.36% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 380000 | 0 | 314017.5191 | 65982.4809 | 17.36% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 380000 | 0 | 314017.5191 | 65982.4809 | 17.36% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 380000 | 0 | 314017.5191 | 65982.4809 | 17.36% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 380000 | 0 | 314017.5191 | 65982.4809 | 17.36% | 0 | 0 | 21 | 21 | 0.006688%
Oct 2024 | 0 | 380000 | 0 | 314017.5191 | 65982.4809 | 17.36% | 0 | 0 | 0 | 21 | 0.006688%
Nov 2024 | 0 | 380000 | 0 | 314017.5191 | 65982.4809 | 17.36% | 0 | 0 | 41925.8627 | 41946.8627 | 13.36%
Dec 2024 | 9480 | 389480 | 8745 | 322762.5191 | 66717.4809 | 17.13% | 9480 | 9480 | 32397.29 | 74344.1527 | 23.03%
Jan 2025 | 0 | 389480 | 0 | 322762.5191 | 66717.4809 | 17.13% | 142800 | 152280 | 99509.3364 | 173853.4891 | 53.86%
Feb 2025 | 0 | 389480 | 0 | 322762.5191 | 66717.4809 | 17.13% | 146612 | 298892 | 90343.8073 | 264197.2964 | 81.86%
Mar 2025 | 0 | 389480 | 0 | 322762.5191 | 66717.4809 | 17.13% | 0 | 298892 | 783.6 | 264980.8964 | 82.1%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 25.4126 | 0 | 25.4126 | 21
Oct 2024 | 25.4126 | 0 | 25.4126 | 21
Nov 2024 | 50760.8871 | 0 | 50760.8871 | 41946.8627
Dec 2024 | 89711.6576 | 9480 | 80231.6576 | 66488.0659
Jan 2025 | 209790.3347 | 152280 | 57510.3347 | 47658.8798
Feb 2025 | 318808.8978 | 298892 | 19916.8978 | 16505.1559
Mar 2025 | 319754.474 | 298892 | 20862.474 | 17288.7559
Job Profitability Summary
| Beginning | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9480 | 142800 | 146612 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 41946.8627 | 66488.0659 | 47658.8798 | 16505.1559 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 41925.8627 | 32397.29 | 99509.3364 | 90343.8073 | 783.6 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 41946.8627 | 66488.0659 | 47658.8798 | 16505.1559 | 17288.7559 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7856.0868 | 118338.5225 | 121497.5312 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0.006688% | 0.006688% | 13.36% | 23.03% | 53.86% | 81.86% | 82.1% | 82.1%

## J-2130
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Forte Group Pty Ltd |  |  |  |  | Steel | 530396.9981 | 0 | 118061.4418 | 0
Estimate Code |  | E00013906 |  |  |  |  | Bolts | 24371.1484 | 0 | 17246.3636 | 0
Contract Code |  | J-2130 |  |  |  |  | Purlin | 179178.0399 | 0 | 19478.2636 | 0
Contract Name |  | 75-105 Bolinda Road, Campbellfield- Stage 2 |  |  |  |  | Labour | 189210.3359 | 0 | 1628.75 | 4711.71
Customer |  | Forte Group Pty Ltd |  |  |  |  | Processing | 113342.0391 | 0 | 47935 | 0
Start Date |  | 15 Aug 2024 |  |  |  |  | Rigging | 414957.625 | 0 | 24000 | 0
Completion Date |  | 6 Jun 2024 |  |  |  |  | Freight | 8000.0352 | 0 | 1125 | 0
Budgeted Revenue |  | 1810000 |  |  |  |  | Shop Drawings | 19952.5625 | 0 | 13000 | 0
Budgeted Job Expenditure |  | 1533624.6846 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.27% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 266.0342 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 227.8641 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.27% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 33078.3498 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1000 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1353.8479 | 0 | 0 | 0
[7 empty] | OH & Profit | 283159.0259 | 0 | 0 | 0
[7 empty] | Total | 1798000.0075 | 0 | 242474.8191 | 4711.71
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1810000 | 1810000 | 1533624.6846 | 1533624.6846 | 276375.3154 | 15.27% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 1810000 | 0 | 1533624.6846 | 276375.3154 | 15.27% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 1810000 | 0 | 1533624.6846 | 276375.3154 | 15.27% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 1810000 | 0 | 1533624.6846 | 276375.3154 | 15.27% | 0 | 0 | 402.5 | 402.5 | 0.02625%
Nov 2024 | 0 | 1810000 | 0 | 1533624.6846 | 276375.3154 | 15.27% | 0 | 0 | 4711.71 | 5114.21 | 0.3335%
Dec 2024 | 0 | 1810000 | 0 | 1533624.6846 | 276375.3154 | 15.27% | 0 | 0 | 0 | 5114.21 | 0.3335%
Jan 2025 | 0 | 1810000 | 0 | 1533624.6846 | 276375.3154 | 15.27% | 0 | 0 | 7732 | 12846.21 | 0.8376%
Feb 2025 | 0 | 1810000 | 0 | 1533624.6846 | 276375.3154 | 15.27% | 0 | 0 | 174292.3782 | 187138.5882 | 12.2%
Mar 2025 | 0 | 1810000 | 0 | 1533624.6846 | 276375.3154 | 15.27% | 0 | 0 | 60047.9409 | 247186.5291 | 16.12%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 475.0347 | 0 | 475.0347 | 402.5
Nov 2024 | 6035.8445 | 0 | 6035.8445 | 5114.21
Dec 2024 | 6035.8445 | 0 | 6035.8445 | 5114.21
Jan 2025 | 15161.2323 | 0 | 15161.2323 | 12846.21
Feb 2025 | 220862.9321 | 0 | 220862.9321 | 187138.5882
Mar 2025 | 291732.1442 | 0 | 291732.1442 | 247186.5291
Job Profitability Summary
| Beginning | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 402.5 | 5114.21 | 5114.21 | 12846.21 | 187138.5882 | 0
Construction Costs | 0 | 0 | 0 | 402.5 | 4711.71 | 0 | 7732 | 174292.3782 | 60047.9409 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 402.5 | 5114.21 | 5114.21 | 12846.21 | 187138.5882 | 247186.5291 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0.02625% | 0.3335% | 0.3335% | 0.8376% | 12.2% | 16.12% | 16.12%

## J-2131
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 113216.6554 | 550 | 88791.5909 | 0
Estimate Code |  | E00013073 |  |  |  |  | Bolts | 9459.4111 | 200 | 4532.7 | 0
Contract Code |  | J-2131 |  |  |  |  | Purlin | 70015.0127 | 0 | 28458.2545 | 0
Contract Name |  | 248-252 Wickham Road, Highett |  |  |  |  | Labour | 46933.2534 | 0 | 2092.22 | 0
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 24070.8613 | 0 | 46619.5818 | 0
Start Date |  | 4 Dec 2023 |  |  |  |  | Rigging | 77953.7891 | 9270 | 45985 | 0
Completion Date |  | 1 Nov 2023 |  |  |  |  | Freight | 3000.0088 | 1580 | 2072.5 | 0
Budgeted Revenue |  | 425000.02 |  |  |  |  | Shop Drawings | 6885.4146 | 0 | 3685 | 0
Budgeted Job Expenditure |  | 353396.2823 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.85% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 62.5941 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 33.6403 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.8% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 735.93 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 500 | 0 | 2819.6818 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 625.9411 | 0 | 0 | 0
[7 empty] | OH & Profit | 71603.7228 | 2080 | 0 | 0
[7 empty] | Total | 425000.0003 | 13680 | 225056.5291 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 425000.01 | 425000.01 | 353396.2823 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 1309 | 1309 | 0.3704%
Nov 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 0 | 0 | 4177.8 | 5486.8 | 1.553%
Dec 2024 | 0 | 425000.01 | 0 | 353396.2823 | 71603.7277 | 16.85% | 118800 | 118800 | 136518.2927 | 142005.0927 | 40.18%
Jan 2025 | 9050 | 434050.01 | 7270 | 360666.2823 | 73383.7277 | 16.91% | 95450 | 214250 | 53690.3364 | 195695.4291 | 54.26%
Feb 2025 | 4630 | 438680.01 | 4330 | 364996.2823 | 73683.7277 | 16.8% | 24300 | 238550 | 25761.1 | 221456.5291 | 60.67%
Mar 2025 | 0 | 438680.01 | 0 | 364996.2823 | 73683.7277 | 16.8% | 0 | 238550 | 3600 | 225056.5291 | 61.66%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 1574.2243 | 0 | 1574.2243 | 1309
Nov 2024 | 6598.5133 | 0 | 6598.5133 | 5486.8
Dec 2024 | 170777.5912 | 118800 | 51977.5912 | 43220.4401
Jan 2025 | 235513.0133 | 214250 | 21263.0133 | 17668.1299
Feb 2025 | 266163.1285 | 238550 | 27613.1285 | 22975.0365
Mar 2025 | 270489.8795 | 238550 | 31939.8795 | 26575.0365
Job Profitability Summary
| Beginning | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118800 | 95450 | 24300 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309 | 5486.8 | 43220.4401 | 17668.1299 | 22975.0365 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309 | 4177.8 | 136518.2927 | 53690.3364 | 25761.1 | 3600 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309 | 5486.8 | 43220.4401 | 17668.1299 | 22975.0365 | 26575.0365 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98784.6526 | 79242.6466 | 20454.1934 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3704% | 1.553% | 40.18% | 54.26% | 60.67% | 61.66% | 61.66%

## J-2133
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Davies Henderson Pty Ltd |  |  |  |  | Steel | 18556.8396 | 0 | 9617.2691 | 0
Estimate Code |  | E00013364 |  |  |  |  | Bolts | 1027.5552 | 0 | 444.4182 | 0
Contract Code |  | J-2133 |  |  |  |  | Purlin | 158.301 | 0 | 0 | 0
Contract Name |  | 10-12 Irving Road, Toorak |  |  |  |  | Labour | 7383.4087 | 0 | 4286.59 | 0
Customer |  | Davies Henderson Pty Ltd |  |  |  |  | Processing | 8032.1896 | 0 | 2170 | 0
Start Date |  | 1 Apr 2024 |  |  |  |  | Rigging | 7000 | 0 | 0 | 0
Completion Date |  | 8 Feb 2024 |  |  |  |  | Freight | 645.8918 | 0 | 312.5 | 0
Budgeted Revenue |  | 63000.01 |  |  |  |  | Shop Drawings | 2825.7769 | 0 | 2825 | 0
Budgeted Job Expenditure |  | 52459.7838 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.73% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 8.1345 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 4.0825 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.73% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 6627.9801 | 0 | 3386.3091 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 201.8412 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 10540.2162 | 0 | 0 | 0
[7 empty] | Total | 63000.0003 | 0 | 23042.0864 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 63000 | 63000 | 52459.7839 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 700 | 700 | 1.334%
Nov 2024 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 0 | 700 | 1.334%
Dec 2024 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 2125 | 2825 | 5.385%
Jan 2025 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 0 | 0 | 11478.6373 | 14303.6373 | 27.27%
Feb 2025 | 0 | 63000 | 0 | 52459.7839 | 10540.2161 | 16.73% | 20000 | 20000 | 8738.4491 | 23042.0864 | 43.92%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 840.644 | 0 | 840.644 | 700
Nov 2024 | 840.644 | 0 | 840.644 | 700
Dec 2024 | 3392.5988 | 0 | 3392.5988 | 2825
Jan 2025 | 17177.5231 | 0 | 17177.5231 | 14303.6373
Feb 2025 | 27671.7008 | 20000 | 7671.7008 | 6388.1867
Job Profitability Summary
| Beginning | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 2825 | 14303.6373 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 2125 | 11478.6373 | 8738.4491 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 2825 | 14303.6373 | 6388.1867 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16653.8996 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 1.334% | 1.334% | 5.385% | 27.27% | 43.92% | 43.92%

## J-2134
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Cota Group |  |  |  |  | Steel | 186847.4244 | 2645 | 207091.5709 | 0
Estimate Code |  | E00014205 |  |  |  |  | Bolts | 11110.8809 | 0 | 10877.6182 | 0
Contract Code |  | J-2134 |  |  |  |  | Purlin | 91574.8583 | 0 | 91257.8273 | 0
Contract Name |  | Rangebank Drive, Cranbourne West- Terra Mater |  |  |  |  | Labour | 76248.0562 | 0 | 82981.91 | 0
Customer |  | Cota Group |  |  |  |  | Processing | 40556.5342 | 0 | 39820.9545 | 0
Start Date |  | 8 Nov 2024 |  |  |  |  | Rigging | 95999.7305 | 0 | 95000 | 0
Completion Date |  | 5 Aug 2024 |  |  |  |  | Freight | 7400.0198 | 0 | 7063.5 | 0
Budgeted Revenue |  | 622000 |  |  |  |  | Shop Drawings | 11066.2236 | 0 | 11000 | 0
Budgeted Job Expenditure |  | 526974.3524 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.28% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 103.6357 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 105.9574 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 11.95% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 3964.2 | 0 | 3734.3455 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1000 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1206.4236 | 0 | 858 | 0
[7 empty] | OH & Profit | 95025.6489 | 0 | 0 | -20364.63
[7 empty] | Total | 622000.0004 | 2645 | 549685.7264 | -20364.63
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 622000 | 622000 | 526974.3524 | 526974.3524 | 95025.6476 | 15.28% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 622000 | 0 | 526974.3524 | 95025.6476 | 15.28% | 0 | 0 | 7430.9273 | 7430.9273 | 1.41%
Oct 2024 | 0 | 622000 | 0 | 526974.3524 | 95025.6476 | 15.28% | 94280 | 94280 | 342306.6864 | 349737.6136 | 66.37%
Nov 2024 | 0 | 622000 | 0 | 526974.3524 | 95025.6476 | 15.28% | 502349.2 | 596629.2 | 184346.28 | 534083.8936 | 101.3%
Dec 2024 | 2645 | 624645 | 2645 | 529619.3524 | 95025.6476 | 15.21% | 2645 | 599274.2 | 14775.1845 | 548859.0782 | 103.6%
Jan 2025 | 0 | 624645 | 0 | 529619.3524 | 95025.6476 | 15.21% | -23839.2 | 575435 | 0 | 548859.0782 | 103.6%
Feb 2025 | 0 | 624645 | 20364.63 | 549983.9824 | 74661.0176 | 11.95% | 0 | 575435 | 826.6482 | 549685.7264 | 99.95%
Mar 2025 | 0 | 624645 | 0 | 549983.9824 | 74661.0176 | 11.95% | 15000 | 590435 | 0 | 549685.7264 | 99.95%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 8770.8951 | 0 | 8770.8951 | 7430.9273
Oct 2024 | 412803.3835 | 94280 | 318523.3835 | 269861.1796
Nov 2024 | 630391.5557 | 596629.2 | 33762.3557 | 28604.3337
Dec 2024 | 647336.7662 | 599274.2 | 48062.5662 | 40750.9308
Jan 2025 | 647336.7662 | 575435 | 71901.7662 | 60963.5342
Feb 2025 | 624306.2553 | 575435 | 48871.2553 | 43029.8932
Mar 2025 | 624306.2553 | 590435 | 33871.2553 | 29822.776
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 94280 | 502349.2 | 2645 | -23839.2 | 0 | 15000 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 7430.9273 | 269861.1796 | 28604.3337 | 40750.9308 | 60963.5342 | 43029.8932 | 0
Construction Costs | 0 | 7430.9273 | 342306.6864 | 184346.28 | 14775.1845 | 0 | 826.6482 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 7430.9273 | 269861.1796 | 28604.3337 | 40750.9308 | 60963.5342 | 43029.8932 | 29822.776 | 0
Total Costruction Cost | #VALUE! | 0 | 79876.434 | 425603.126 | 2628.5874 | -20212.6034 | 18760.2892 | 13207.1172 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 1.41% | 66.37% | 101.3% | 103.6% | 103.6% | 99.95% | 99.95% | 99.95%

## J-2136
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Flowrite Construction Developments |  |  |  |  | Steel | 54152.2891 | 0 | 53851.3827 | 0
Estimate Code |  | E00012609 |  |  |  |  | Bolts | 3764.3628 | 0 | 4214.1273 | 0
Contract Code |  | J-2136 |  |  |  |  | Purlin | 48775.1201 | 0 | 48084.3364 | 0
Contract Name |  | 7 Logic Court, Truganina |  |  |  |  | Labour | 25077.2629 | 0 | 1911.29 | 6992
Customer |  | Flowrite Construction Developments |  |  |  |  | Processing | 17746.8608 | 0 | 14583.75 | 0
Start Date |  | 18 Aug 2023 |  |  |  |  | Rigging | 70721.9141 | 0 | 70940 | 0
Completion Date |  | 21 Jun 2023 |  |  |  |  | Freight | 3932.3599 | 0 | 6003.95 | 0
Budgeted Revenue |  | 379999.99 |  |  |  |  | Shop Drawings | 4864.9839 | 0 | 4840 | 0
Budgeted Job Expenditure |  | 298899.4466 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 21.34% |  |  |  |  | Box Frame | 27878.5864 | 0 | 27800 | 0
Estimated Weight |  | 42.9045 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 29.8695 |  |  |  |  | Stairs | 32000 | 0 | 32000 | 0
Current GP% |  | 28.03% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 8413.296 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1072.6124 | 0 | 2246.8364 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 499.7945 | 0 | 0 | 0
[7 empty] | OH & Profit | 81100.5524 | 0 | 0 | 25431.77
[7 empty] | Total | 379999.9954 | 0 | 266475.6727 | 32423.77
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 380000 | 380000 | 298899.4466 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 0 | 0 | 62887.0391 | 62887.0391 | 21.04%
Dec 2024 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 266000 | 266000 | 137477.4982 | 200364.5373 | 67.03%
Jan 2025 | 0 | 380000 | 0 | 298899.4466 | 81100.5534 | 21.34% | 114000 | 380000 | 40563.1355 | 240927.6727 | 80.6%
Feb 2025 | 0 | 380000 | -25431.77 | 273467.6766 | 106532.3234 | 28.03% | 0 | 380000 | 32540 | 273467.6727 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 79950.2144 | 0 | 79950.2144 | 62887.0391
Dec 2024 | 254729.5588 | 266000 | -11270.4412 | -8865.0754
Jan 2025 | 306298.7124 | 380000 | -73701.2876 | -57971.7739
Feb 2025 | 379999.9946 | 380000 | -0.0054092 | -0.0038927
Job Profitability Summary
| Beginning | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266000 | 114000 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11270.4412 | -73701.2876 | -0.0054092 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270.4412 | 73701.2876
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62887.0391 | -8865.0754 | -57971.7739 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62887.0391 | 137477.4982 | 40563.1355 | 32540 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62887.0391 | -8865.0754 | -57971.7739 | -0.0038927 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209229.6126 | 89669.834 | -25431.77 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.04% | 67.03% | 80.6% | 100% | 100%

## J-2138
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Richard Crookes Constructions |  |  |  |  | Steel | 822534.7898 | 0 | 737589.5545 | 0
Estimate Code |  | E00014317 |  |  |  |  | Bolts | 49215.9258 | 0 | 35627.2364 | 0
Contract Code |  | J-2138 |  |  |  |  | Purlin | 295186.5163 | 0 | 255734.5364 | 0
Contract Name |  | Lot 5A & B Bankstown Airport, South West Precinct, |  |  |  |  | Labour | 338389.6719 | 0 | 710349.94 | 13497
Customer |  | Richard Crookes Constructions |  |  |  |  | Processing | 190316.0859 | 0 | 205860.1591 | 0
Start Date | [6 empty] | Rigging | 649998.625 | 0 | 145855 | 0
Completion Date |  | 2 Sep 2024 |  |  |  |  | Freight | 128000.0469 | 0 | 87623.4727 | 0
Budgeted Revenue |  | 2845999.98 |  |  |  |  | Shop Drawings | 42331.9375 | 0 | 64400 | 0
Budgeted Job Expenditure |  | 2557012.4756 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 10.15% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 445.5993 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 346.4059 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 10.15% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 16882.9004 | 0 | 8201.8 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 19700 | 0 | 20820.9727 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 4455.9932 | 0 | 1427 | 0
[7 empty] | OH & Profit | 288987.495 | 0 | 0 | 0
[7 empty] | Total | 2845999.9876 | 0 | 2273489.6718 | 13497
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 2845999.98 | 2845999.98 | 2557012.4756 | 2557012.4756 | 288987.5044 | 10.15% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 2845999.98 | 0 | 2557012.4756 | 288987.5044 | 10.15% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 2845999.98 | 0 | 2557012.4756 | 288987.5044 | 10.15% | 142300 | 142300 | 6705.1127 | 6705.1127 | 0.2622%
Nov 2024 | 0 | 2845999.98 | 0 | 2557012.4756 | 288987.5044 | 10.15% | 0 | 142300 | 188120.0809 | 194825.1936 | 7.619%
Dec 2024 | 0 | 2845999.98 | 0 | 2557012.4756 | 288987.5044 | 10.15% | 0 | 142300 | 422322.9768 | 617148.1705 | 24.14%
Jan 2025 | 0 | 2845999.98 | 0 | 2557012.4756 | 288987.5044 | 10.15% | 1053000 | 1195300 | 935789.2073 | 1552937.3777 | 60.73%
Feb 2025 | 0 | 2845999.98 | 0 | 2557012.4756 | 288987.5044 | 10.15% | 853820 | 2049120 | 645698.3673 | 2198635.745 | 85.98%
Mar 2025 | 0 | 2845999.98 | 0 | 2557012.4756 | 288987.5044 | 10.15% | 0 | 2049120 | 88350.9318 | 2286986.6768 | 89.44%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 7462.9087 | 142300 | -134837.0913 | -121145.512
Nov 2024 | 216843.8764 | 142300 | 74543.8764 | 66974.569
Dec 2024 | 686896.7975 | 142300 | 544596.7975 | 489297.5458
Jan 2025 | 1728446.6885 | 1195300 | 533146.6885 | 479010.0996
Feb 2025 | 2447120.3586 | 2049120 | 398000.3586 | 357586.7496
Mar 2025 | 2545456.5039 | 2049120 | 496336.5039 | 445937.6815
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 142300 | 0 | 0 | 1053000 | 853820 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | -134837.0913 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 134837.0913 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | -121145.512 | 66974.569 | 489297.5458 | 479010.0996 | 357586.7496 | 0
Construction Costs | 0 | 0 | 6705.1127 | 188120.0809 | 422322.9768 | 935789.2073 | 645698.3673 | 88350.9318 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | -121145.512 | 66974.569 | 489297.5458 | 479010.0996 | 357586.7496 | 445937.6815 | 0
Total Costruction Cost | #VALUE! | 0 | 127850.6247 | 0 | 0 | 946076.6534 | 767121.7172 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.2622% | 7.619% | 24.14% | 60.73% | 85.98% | 89.44% | 89.44%

## J-2139
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Richard Crookes Constructions |  |  |  |  | Steel | -1000.6098 | 0 | 0 | 0
Estimate Code |  | E00012913 |  |  |  |  | Bolts | 47233 | 0 | 0 | 0
Contract Code |  | J-2139 |  |  |  |  | Purlin | 447472.0131 | 0 | 0 | 0
Contract Name |  | Light Horse Lot 3, 165 Wallgrove Rd & 475 Ferrers |  |  |  |  | Labour | 2000 | 0 | 3686.5 | 0
Customer |  | Richard Crookes Constructions |  |  |  |  | Processing | 0 | 0 | 517.5 | 0
Start Date |  | 29 Oct 2023 |  |  |  |  | Rigging | 598107 | 0 | 0 | 0
Completion Date |  | 8 Sep 2023 |  |  |  |  | Freight | 16000 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 39291 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 517.6937 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 1001.1 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1137646 | 0 | 507056.87 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 17681 | 0 | 0 | 0
[7 empty] | OH & Profit | 349569.497 | 0 | 0 | 0
[7 empty] | Total | 2655000.0002 | 0 | 511260.87 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 141000 | 141000 | 152600 | 152600 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 141000 | 22485.8673 | 175085.8673 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 141000 | 386661.5973 | 561747.4645 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 1579200 | 1720200 | -50486.5945 | 511260.87 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 141000 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 141000 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 141000 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 1720200 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141000 | 0 | 0 | 1579200 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152600 | 22485.8673 | 386661.5973 | -50486.5945 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2140
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Ark Industrial Pty Ltd |  |  |  |  | Steel | 315081.036 | 0 | 314690.1536 | 0
Estimate Code |  | E00014117 |  |  |  |  | Bolts | 18295.9043 | 0 | 18692.6636 | 0
Contract Code |  | J-2140 |  |  |  |  | Purlin | 165654.0297 | 0 | 164245.8 | 0
Contract Name |  | 365-466 Melbourne Road, Geelong- Site A & Site B F |  |  |  |  | Labour | 93704.7979 | 45039 | 214111.89 | 13822
Customer |  | Ark Industrial Pty Ltd |  |  |  |  | Processing | 64337.8477 | 0 | 43080.9409 | 0
Start Date |  | 27 Sep 2024 |  |  |  |  | Rigging | 159999.75 | 25000 | 167961 | 0
Completion Date |  | 18 Jul 2024 |  |  |  |  | Freight | 9600.041 | 0 | 15531.0545 | 0
Budgeted Revenue |  | 999000 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 839581.2355 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.96% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 169.2555 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 185.0547 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 14.56% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 4564.56 | 4500 | 8899.9091 | 0
[7 empty] | Grates | 0 | 21000 | 20670 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 5460.0003 | 0 | 0 | 0
[7 empty] | Other Materials | 1220 | 0 | 554.1818 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1663.2738 | 0 | 1308 | 0
[7 empty] | OH & Profit | 159418.7645 | 0 | 0 | 0
[7 empty] | Total | 999000.0051 | 95539 | 969745.5936 | 13822
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 999000 | 999000 | 839581.2355 | 839581.2355 | 159418.7645 | 15.96% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 999000 | 0 | 839581.2355 | 159418.7645 | 15.96% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 999000 | 0 | 839581.2355 | 159418.7645 | 15.96% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 999000 | 0 | 839581.2355 | 159418.7645 | 15.96% | 0 | 0 | 16888.97 | 16888.97 | 2.012%
Dec 2024 | 0 | 999000 | 0 | 839581.2355 | 159418.7645 | 15.96% | 0 | 0 | 192981.5755 | 209870.5455 | 25%
Jan 2025 | 0 | 999000 | 0 | 839581.2355 | 159418.7645 | 15.96% | 333341 | 333341 | 521991.5755 | 731862.1209 | 87.17%
Feb 2025 | 0 | 999000 | 0 | 839581.2355 | 159418.7645 | 15.96% | 588186 | 921527 | 225565.4041 | 957427.525 | 114%
Mar 2025 | 95539 | 1094539 | 95539 | 935120.2355 | 159418.7645 | 14.56% | 0 | 921527 | 26140.0636 | 983567.5886 | 105.2%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 20095.8291 | 0 | 20095.8291 | 16888.97
Dec 2024 | 249720.5345 | 0 | 249720.5345 | 209870.5455
Jan 2025 | 870827.2981 | 333341 | 537486.2981 | 451715.1253
Feb 2025 | 1139222.8138 | 921527 | 217695.8138 | 182956.2766
Mar 2025 | 1151245.6303 | 921527 | 229718.6303 | 196260.2883
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 333341 | 588186 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 16888.97 | 209870.5455 | 451715.1253 | 182956.2766 | 0
Construction Costs | 0 | 0 | 0 | 16888.97 | 192981.5755 | 521991.5755 | 225565.4041 | 26140.0636 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 16888.97 | 209870.5455 | 451715.1253 | 182956.2766 | 196260.2883 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 280146.9956 | 494324.2528 | 12836.0519 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 2.012% | 25% | 87.17% | 114% | 105.2% | 105.2%

## J-2142
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Maxim-Built |  |  |  |  | Steel | 420924.3613 | 0 | 0 | 0
Estimate Code |  | E00013961 |  |  |  |  | Bolts | 30535.3555 | 0 | 0 | 0
Contract Code |  | J-2142 |  |  |  |  | Purlin | 228052.9284 | 0 | 0 | 0
Contract Name |  | 49 Wangara Road, 7 Melaleuca Drive, Cheltenham |  |  |  |  | Labour | 167186.3848 | 0 | 244 | 0
Customer |  | Maxim-Built |  |  |  |  | Processing | 93877.2578 | 0 | 0 | 0
Start Date |  | 28 Aug 2024 |  |  |  |  | Rigging | 255000.0781 | 0 | 0 | 0
Completion Date |  | 19 Jun 2024 |  |  |  |  | Freight | 11200.0337 | 0 | 0 | 0
Budgeted Revenue |  | 1506000 |  |  |  |  | Shop Drawings | 26213.8574 | 0 | 0 | 0
Budgeted Job Expenditure |  | 1244625.8037 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.36% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 222.1231 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.36% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 6914.32 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2500 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2221.231 | 0 | 0 | 0
[7 empty] | OH & Profit | 261374.1889 | 0 | 0 | 0
[7 empty] | Total | 1505999.9968 | 0 | 244 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1506000 | 1506000 | 1244625.8037 | 1244625.8037 | 261374.1963 | 17.36% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 1506000 | 0 | 1244625.8037 | 261374.1963 | 17.36% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 1506000 | 0 | 1244625.8037 | 261374.1963 | 17.36% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Aug 2024 | Sep 2024 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0%

## J-2143
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Protilt Constructions |  |  |  |  | Steel | 361698.1007 | 0 | 244318.0118 | 0
Estimate Code |  | E00013803 |  |  |  |  | Bolts | 15098.6816 | 0 | 10481.2091 | 0
Contract Code |  | J-2143 |  |  |  |  | Purlin | 113499.9811 | 0 | 101304.8455 | 0
Contract Name |  | 110-116 Greens Road, Dandenong South |  |  |  |  | Labour | 119378.5999 | 0 | 62638.89 | 20000
Customer |  | Protilt Constructions |  |  |  |  | Processing | 83098.9297 | 0 | 33591.2409 | 0
Start Date |  | 26 Jul 2024 |  |  |  |  | Rigging | 165999.9688 | 0 | 120240 | 0
Completion Date |  | 14 May 2024 |  |  |  |  | Freight | 8400.0703 | 0 | 8162.39 | 0
Budgeted Revenue |  | 1151699.98 |  |  |  |  | Shop Drawings | 19085.207 | 0 | 19000 | 0
Budgeted Job Expenditure |  | 971953.3049 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.61% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 200.8969 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 122.4718 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.61% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 82684.803 | 0 | 9498.4727 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1000 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2008.9692 | 0 | 0 | 0
[7 empty] | OH & Profit | 179746.6833 | 0 | 0 | 0
[7 empty] | Total | 1151699.9947 | 0 | 609235.06 | 20000
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1151699.98 | 1151699.98 | 971953.3049 | 971953.3049 | 179746.6751 | 15.61% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 1151699.98 | 0 | 971953.3049 | 179746.6751 | 15.61% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 1151699.98 | 0 | 971953.3049 | 179746.6751 | 15.61% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 1151699.98 | 0 | 971953.3049 | 179746.6751 | 15.61% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 1151699.98 | 0 | 971953.3049 | 179746.6751 | 15.61% | 0 | 0 | 1460.39 | 1460.39 | 0.1503%
Nov 2024 | 0 | 1151699.98 | 0 | 971953.3049 | 179746.6751 | 15.61% | 0 | 0 | 57680.9545 | 59141.3445 | 6.085%
Dec 2024 | 0 | 1151699.98 | 0 | 971953.3049 | 179746.6751 | 15.61% | 501080 | 501080 | 424675.2532 | 483816.5977 | 49.78%
Jan 2025 | 0 | 1151699.98 | 0 | 971953.3049 | 179746.6751 | 15.61% | 0 | 501080 | 130906.09 | 614722.6877 | 63.25%
Feb 2025 | 0 | 1151699.98 | 0 | 971953.3049 | 179746.6751 | 15.61% | 0 | 501080 | 13941.3764 | 628664.0641 | 64.68%
Mar 2025 | 0 | 1151699.98 | 0 | 971953.3049 | 179746.6751 | 15.61% | 0 | 501080 | 570.9909 | 629235.055 | 64.74%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 1730.465 | 0 | 1730.465 | 1460.39
Nov 2024 | 70078.5573 | 0 | 70078.5573 | 59141.3445
Dec 2024 | 573290.4689 | 501080 | 72210.4689 | 60940.5271
Jan 2025 | 728405.4734 | 501080 | 227325.4734 | 191846.6171
Feb 2025 | 744925.0765 | 501080 | 243845.0765 | 205787.9935
Mar 2025 | 745601.6627 | 501080 | 244521.6627 | 206358.9844
Job Profitability Summary
| Beginning | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 501080 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 1460.39 | 59141.3445 | 60940.5271 | 191846.6171 | 205787.9935 | 0
Construction Costs | 0 | 0 | 0 | 0 | 1460.39 | 57680.9545 | 424675.2532 | 130906.09 | 13941.3764 | 570.9909 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 1460.39 | 59141.3445 | 60940.5271 | 191846.6171 | 205787.9935 | 206358.9844 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 422876.0706 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0.1503% | 6.085% | 49.78% | 63.25% | 64.68% | 64.74% | 64.74%

## J-2145
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | DTC Family Builders |  |  |  |  | Steel | 193889.3987 | 0 | 0 | 0
Estimate Code |  | E00013887 |  |  |  |  | Bolts | 11434.6455 | 0 | 65 | 0
Contract Code |  | J-2145 |  |  |  |  | Purlin | 90000.0196 | 0 | 0 | 0
Contract Name |  | 45 Wallan Whittlesea Road, Wallan- Stage 1 |  |  |  |  | Labour | 76355.8084 | 0 | 1526 | 0
Customer |  | DTC Family Builders |  |  |  |  | Processing | 40210.2598 | 0 | 25590 | 0
Start Date |  | 16 Aug 2024 |  |  |  |  | Rigging | 103000.2266 | 0 | 0 | 0
Completion Date |  | 3 Jun 2024 |  |  |  |  | Freight | 3200.0315 | 0 | 45 | 0
Budgeted Revenue |  | 660500 |  |  |  |  | Shop Drawings | 8835.8623 | 0 | 9224 | 0
Budgeted Job Expenditure |  | 547027.6394 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.18% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 103.9513 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 104.4042 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.18% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 9503.9699 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 750 | 0 | 0 | 0
[7 empty] | Other Materials | 8600 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1247.4159 | 0 | 0 | 0
[7 empty] | OH & Profit | 113472.3597 | 0 | 0 | 0
[7 empty] | Total | 660499.9978 | 0 | 36450 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 660500 | 660500 | 547027.6394 | 547027.6394 | 113472.3606 | 17.18% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 660500 | 0 | 547027.6394 | 113472.3606 | 17.18% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 660500 | 0 | 547027.6394 | 113472.3606 | 17.18% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 660500 | 0 | 547027.6394 | 113472.3606 | 17.18% | 132600 | 132600 | 0 | 0 | 0%
Nov 2024 | 0 | 660500 | 0 | 547027.6394 | 113472.3606 | 17.18% | 0 | 132600 | 0 | 0 | 0%
Dec 2024 | 0 | 660500 | 0 | 547027.6394 | 113472.3606 | 17.18% | 0 | 132600 | 65 | 65 | 0.01188%
Jan 2025 | 0 | 660500 | 0 | 547027.6394 | 113472.3606 | 17.18% | 0 | 132600 | 0 | 65 | 0.01188%
Feb 2025 | 0 | 660500 | 0 | 547027.6394 | 113472.3606 | 17.18% | 0 | 132600 | 9341 | 9406 | 1.719%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 132600 | -132600 | -109819.629
Nov 2024 | 0 | 132600 | -132600 | -109819.629
Dec 2024 | 78.4832 | 132600 | -132521.5168 | -109754.629
Jan 2025 | 78.4832 | 132600 | -132521.5168 | -109754.629
Feb 2025 | 11357.1281 | 132600 | -121242.8719 | -100413.629
Job Profitability Summary
| Beginning | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 132600 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | -132600 | -132600 | -132521.5168 | -132521.5168 | -121242.8719 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 132600 | 132600 | 132521.5168 | 132521.5168
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | -109819.629 | -109819.629 | -109754.629 | -109754.629 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 9341 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | -109819.629 | -109819.629 | -109754.629 | -109754.629 | -100413.629 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 109819.629 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0.01188% | 0.01188% | 1.719% | 1.719%

## J-2146
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 204544.2873 | 0 | 92024.6491 | 0
Estimate Code |  | E00013130 |  |  |  |  | Bolts | 15037.7314 | 0 | 17441.3273 | 0
Contract Code |  | J-2146 |  |  |  |  | Purlin | 222966.0587 | 0 | 78623.4909 | 0
Contract Name |  | 30 Dairy Drive, Coburg North- Stage 1 |  |  |  |  | Labour | 84770.1377 | 0 | 33933.35 | 0
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 47588.1621 | 0 | 31877.5 | 0
Start Date |  | 22 Jan 2024 |  |  |  |  | Rigging | 251120.3438 | 0 | 31780 | 0
Completion Date |  | 17 Nov 2023 |  |  |  |  | Freight | 5483.8823 | 0 | 1728.75 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 16194.5312 | 0 | 8000 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 146.6498 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 101.5559 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 1090.1273 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 500 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 177329.9451 | 0 | 0 | 0
[7 empty] | Total | 1025535.0797 | 0 | 296499.1945 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 891.25 | 891.25 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 98162.5791 | 99053.8291 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 198600 | 198600 | 171657.8073 | 270711.6364 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 198600 | 25787.5582 | 296499.1945 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 198600 | #DIV/0! | #DIV/0!
Mar 2025 | #DIV/0! | 198600 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198600 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 891.25 | 98162.5791 | 171657.8073 | 25787.5582 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2147
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Flowrite Construction Developments |  |  |  |  | Steel | 26495.5743 | 0 | 0 | 0
Estimate Code |  | E00013612 |  |  |  |  | Bolts | 1522.0886 | 0 | 0 | 0
Contract Code |  | J-2147 |  |  |  |  | Purlin | 13599.9996 | 0 | 0 | 0
Contract Name |  | 1-3 Salisbury Street, Sunshine North |  |  |  |  | Labour | 12296.9617 | 0 | 0 | 0
Customer |  | Flowrite Construction Developments |  |  |  |  | Processing | 5976.1638 | 0 | 0 | 0
Start Date |  | 27 May 2024 |  |  |  |  | Rigging | 19999.5547 | 0 | 0 | 0
Completion Date |  | 5 Apr 2024 |  |  |  |  | Freight | 999.9776 | 0 | 85.5 | 0
Budgeted Revenue |  | 102200 |  |  |  |  | Shop Drawings | 2075.6038 | 0 | 0 | 0
Budgeted Job Expenditure |  | 84481.3257 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.34% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 13.8506 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.34% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 365.4 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 750 | 0 | 0 | 0
[7 empty] | Other Materials | 400 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 17718.6761 | 0 | 0 | 0
[7 empty] | Total | 102200.0002 | 0 | 85.5 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 102200 | 102200 | 84481.3256 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 102200 | 0 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 102200 | 0 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 102200 | 0 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 102200 | 0 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 102200 | 0 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 102200 | 0 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 102200 | 0 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 102200 | 0 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 102200 | 0 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 102200 | 0 | 84481.3256 | 17718.6744 | 17.34% | 0 | 0 | 85.5 | 85.5 | 0.1012%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 103.4323 | 0 | 103.4323 | 85.5
Job Profitability Summary
| Beginning | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.5 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.5 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1012% | 0.1012%

## J-2148
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 129503.0167 | 0 | 0 | 0
Estimate Code |  | E00014387 |  |  |  |  | Bolts | 7467.8267 | 0 | 0 | 0
Contract Code |  | J-2148 |  |  |  |  | Purlin | 44386.2845 | 0 | 0 | 0
Contract Name |  | 30 Dairy Drive, Coburg North- Stgae 2 |  |  |  |  | Labour | 41905.7373 | 0 | 1055 | 0
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 29357.2246 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 54957.8984 | 0 | 0 | 0
Completion Date |  | 11 Sep 2024 |  |  |  |  | Freight | 2994.2671 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 7505.5254 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 50.4974 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 75348.9697 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1777.58 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 500 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 4200 | 0 | 0 | 0
[7 empty] | OH & Profit | 85095.6705 | 0 | 0 | 0
[7 empty] | Total | 485000.0009 | 0 | 1055 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Sep 2024 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-2149
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Flowrite Construction Developments |  |  |  |  | Steel | 25999.5655 | 0 | 19455.8418 | 0
Estimate Code |  | E00013389 |  |  |  |  | Bolts | 1163.5321 | 0 | 1485.7091 | 0
Contract Code |  | J-2149 |  |  |  |  | Purlin | 16779.9998 | 0 | 12675.0636 | 0
Contract Name |  | Lot 18, 11 Sant Court, Ravenhall |  |  |  |  | Labour | 7097.718 | 0 | 4814.64 | 0
Customer |  | Flowrite Construction Developments |  |  |  |  | Processing | 4279.1263 | 0 | 5072.5 | 0
Start Date |  | 4 Apr 2024 |  |  |  |  | Rigging | 16465.1611 | 0 | 16940 | 0
Completion Date |  | 15 Feb 2024 |  |  |  |  | Freight | 500 | 0 | 625 | 0
Budgeted Revenue |  | 85499.99 |  |  |  |  | Shop Drawings | 1163.5341 | 0 | 1100 | 0
Budgeted Job Expenditure |  | 71520.7671 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.35% |  |  |  |  | Box Frame | 3000 | 0 | 2300 | 0
Estimated Weight |  | 10.9127 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 9.7369 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.35% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 600 | 0 | 0 | 0
[7 empty] | Other Materials | 1022.8175 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 105.7768 | 0 | 0 | 0
[7 empty] | OH & Profit | 16822.7678 | 0 | 0 | 0
[7 empty] | Total | 94999.9991 | 0 | 64468.7545 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 85500 | 85500 | 71520.7671 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 1100 | 1100 | 1.538%
Dec 2024 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 22515.3418 | 23615.3418 | 33.02%
Jan 2025 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 0 | 7947.4764 | 31562.8182 | 44.13%
Feb 2025 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 81000 | 81000 | 32665.9364 | 64228.7545 | 89.8%
Mar 2025 | 0 | 85500 | 0 | 71520.7671 | 13979.2329 | 16.35% | 0 | 81000 | 240 | 64468.7545 | 90.14%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 1315.0027 | 0 | 1315.0027 | 1100
Dec 2024 | 28231.1251 | 0 | 28231.1251 | 23615.3418
Jan 2025 | 37731.9912 | 0 | 37731.9912 | 31562.8182
Feb 2025 | 76782.7127 | 81000 | -4217.2873 | -3527.7617
Mar 2025 | 77069.6224 | 81000 | -3930.3776 | -3287.7617
Job Profitability Summary
| Beginning | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4217.2873 | -3930.3776 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4217.2873
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 23615.3418 | 31562.8182 | -3527.7617 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 22515.3418 | 7947.4764 | 32665.9364 | 240 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 23615.3418 | 31562.8182 | -3527.7617 | -3287.7617 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67756.5162 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.538% | 33.02% | 44.13% | 89.8% | 90.14% | 90.14%

## J-2150
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Flowrite Construction Developments |  |  |  |  | Steel | 21554.1963 | 0 | 19706.2645 | 0
Estimate Code |  | E00014241 |  |  |  |  | Bolts | 1556.9951 | 0 | 1229.4273 | 0
Contract Code |  | J-2150 |  |  |  |  | Purlin | 15884.3798 | 0 | 12180.1636 | 0
Contract Name |  | Lot 16, 15 Sant Court, Ravenhall |  |  |  |  | Labour | 7978.6721 | 0 | 6761.84 | 0
Customer |  | Flowrite Construction Developments |  |  |  |  | Processing | 4059.2223 | 0 | 4341.25 | 0
Start Date |  | 30 Oct 2024 |  |  |  |  | Rigging | 17219.0176 | 0 | 19750 | 0
Completion Date |  | 13 Aug 2024 |  |  |  |  | Freight | 500 | 0 | 90 | 0
Budgeted Revenue |  | 81100 |  |  |  |  | Shop Drawings | 1583.2294 | 0 | 1100 | 0
Budgeted Job Expenditure |  | 67816.5023 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.38% |  |  |  |  | Box Frame | 4000 | 0 | 0 | 0
Estimated Weight |  | 10.8608 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 9.7215 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.38% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 600 | 0 | 0 | 0
[7 empty] | Other Materials | 900 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 105.5566 | 0 | 0 | 0
[7 empty] | OH & Profit | 16258.73 | 0 | 0 | 0
[7 empty] | Total | 92199.9991 | 0 | 65158.9455 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 81100 | 81100 | 67816.5023 | 67816.5023 | 13283.4977 | 16.38% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 81100 | 0 | 67816.5023 | 13283.4977 | 16.38% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 81100 | 0 | 67816.5023 | 13283.4977 | 16.38% | 0 | 0 | 159.5 | 159.5 | 0.2352%
Nov 2024 | 0 | 81100 | 0 | 67816.5023 | 13283.4977 | 16.38% | 0 | 0 | 0 | 159.5 | 0.2352%
Dec 2024 | 0 | 81100 | 0 | 67816.5023 | 13283.4977 | 16.38% | 0 | 0 | 0 | 159.5 | 0.2352%
Jan 2025 | 0 | 81100 | 0 | 67816.5023 | 13283.4977 | 16.38% | 0 | 0 | 2243.9348 | 2403.4348 | 3.544%
Feb 2025 | 0 | 81100 | 0 | 67816.5023 | 13283.4977 | 16.38% | 0 | 0 | 42909.5073 | 45312.9421 | 66.82%
Mar 2025 | 0 | 81100 | 0 | 67816.5023 | 13283.4977 | 16.38% | 0 | 0 | 19846 | 65158.9421 | 96.08%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 190.7419 | 0 | 190.7419 | 159.5
Nov 2024 | 190.7419 | 0 | 190.7419 | 159.5
Dec 2024 | 190.7419 | 0 | 190.7419 | 159.5
Jan 2025 | 2874.2055 | 0 | 2874.2055 | 2403.4348
Feb 2025 | 54188.5748 | 0 | 54188.5748 | 45312.9421
Mar 2025 | 77921.8926 | 0 | 77921.8926 | 65158.9421
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 159.5 | 159.5 | 159.5 | 2403.4348 | 45312.9421 | 0
Construction Costs | 0 | 0 | 159.5 | 0 | 0 | 2243.9348 | 42909.5073 | 19846 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 159.5 | 159.5 | 159.5 | 2403.4348 | 45312.9421 | 65158.9421 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.2352% | 0.2352% | 0.2352% | 3.544% | 66.82% | 96.08% | 96.08%

## J-2151
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Flowrite Construction Developments |  |  |  |  | Steel | 27897.1506 | 0 | 23850.3191 | 0
Estimate Code |  | E00014242 |  |  |  |  | Bolts | 1668.6514 | 0 | 1171.4091 | 0
Contract Code |  | J-2151 |  |  |  |  | Purlin | 18064.9972 | 0 | 14153.1909 | 0
Contract Name |  | Lot 15, 17 Sant Court, Ravenhall |  |  |  |  | Labour | 8599.699 | 0 | 5560.61 | 0
Customer |  | Flowrite Construction Developments |  |  |  |  | Processing | 4636.4482 | 0 | 2645 | 0
Start Date |  | 30 Oct 2024 |  |  |  |  | Rigging | 17437.3672 | 0 | 20710 | 0
Completion Date |  | 13 Aug 2024 |  |  |  |  | Freight | 500 | 0 | 0 | 0
Budgeted Revenue |  | 93000.02 |  |  |  |  | Shop Drawings | 1260.661 | 0 | 1100 | 0
Budgeted Job Expenditure |  | 77809.3914 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.33% |  |  |  |  | Box Frame | 3000 | 0 | 0 | 0
Estimated Weight |  | 11.7666 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 10.4697 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.33% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 600 | 0 | 0 | 0
[7 empty] | Other Materials | 1044.1648 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 114.6066 | 0 | 0 | 0
[7 empty] | OH & Profit | 17676.2553 | 0 | 0 | 0
[7 empty] | Total | 102500.0014 | 0 | 69190.5291 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 93000 | 93000 | 77809.3913 | 77809.3913 | 15190.6087 | 16.33% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 93000 | 0 | 77809.3913 | 15190.6087 | 16.33% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 93000 | 0 | 77809.3913 | 15190.6087 | 16.33% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 93000 | 0 | 77809.3913 | 15190.6087 | 16.33% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 93000 | 0 | 77809.3913 | 15190.6087 | 16.33% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 93000 | 0 | 77809.3913 | 15190.6087 | 16.33% | 0 | 0 | 1209.4167 | 1209.4167 | 1.554%
Feb 2025 | 0 | 93000 | 0 | 77809.3913 | 15190.6087 | 16.33% | 0 | 0 | 47117.6091 | 48327.0258 | 62.11%
Mar 2025 | 0 | 93000 | 0 | 77809.3913 | 15190.6087 | 16.33% | 0 | 0 | 20863.5 | 69190.5258 | 88.92%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 1445.5292 | 0 | 1445.5292 | 1209.4167
Feb 2025 | 57761.8372 | 0 | 57761.8372 | 48327.0258
Mar 2025 | 82698.4865 | 0 | 82698.4865 | 69190.5258
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 1209.4167 | 48327.0258 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 1209.4167 | 47117.6091 | 20863.5 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 1209.4167 | 48327.0258 | 69190.5258 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 1.554% | 62.11% | 88.92% | 88.92%

## J-2152
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Flowrite Construction Developments |  |  |  |  | Steel | 21886.2599 | 0 | 13597.4273 | 0
Estimate Code |  | E00014244 |  |  |  |  | Bolts | 1603.4225 | 0 | 1084.0818 | 0
Contract Code |  | J-2152 |  |  |  |  | Purlin | 12574.5027 | 0 | 0 | 0
Contract Name |  | Lot 7 Sant Court, Ravenhall |  |  |  |  | Labour | 8540.3782 | 0 | 3765.75 | 0
Customer |  | Flowrite Construction Developments |  |  |  |  | Processing | 6380.9501 | 0 | 3191.25 | 0
Start Date |  | 30 Oct 2024 |  |  |  |  | Rigging | 18033.9805 | 0 | 0 | 0
Completion Date |  | 13 Aug 2024 |  |  |  |  | Freight | 500 | 0 | 0 | 0
Budgeted Revenue |  | 88300.01 |  |  |  |  | Shop Drawings | 1191.3639 | 0 | 1100 | 0
Budgeted Job Expenditure |  | 74246.7831 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.92% |  |  |  |  | Box Frame | 2400 | 0 | 0 | 0
Estimated Weight |  | 11.105 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 9.9117 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.92% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 449.995 | 0 | 0 | 0
[7 empty] | Other Materials | 577.6244 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 108.3068 | 0 | 0 | 0
[7 empty] | OH & Profit | 14053.2164 | 0 | 0 | 0
[7 empty] | Total | 88300.0003 | 0 | 22738.5091 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 88300 | 88300 | 74246.7831 | 74246.7831 | 14053.2169 | 15.92% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 88300 | 0 | 74246.7831 | 14053.2169 | 15.92% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 88300 | 0 | 74246.7831 | 14053.2169 | 15.92% | 0 | 0 | 671 | 671 | 0.9037%
Nov 2024 | 0 | 88300 | 0 | 74246.7831 | 14053.2169 | 15.92% | 0 | 0 | 0 | 671 | 0.9037%
Dec 2024 | 0 | 88300 | 0 | 74246.7831 | 14053.2169 | 15.92% | 0 | 0 | 0 | 671 | 0.9037%
Jan 2025 | 0 | 88300 | 0 | 74246.7831 | 14053.2169 | 15.92% | 0 | 0 | 0 | 671 | 0.9037%
Feb 2025 | 0 | 88300 | 0 | 74246.7831 | 14053.2169 | 15.92% | 0 | 0 | 1100 | 1771 | 2.385%
Mar 2025 | 0 | 88300 | 0 | 74246.7831 | 14053.2169 | 15.92% | 0 | 0 | 20967.5091 | 22738.5091 | 30.63%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 798.0049 | 0 | 798.0049 | 671
Nov 2024 | 798.0049 | 0 | 798.0049 | 671
Dec 2024 | 798.0049 | 0 | 798.0049 | 671
Jan 2025 | 798.0049 | 0 | 798.0049 | 671
Feb 2025 | 2106.2098 | 0 | 2106.2098 | 1771
Mar 2025 | 27042.3885 | 0 | 27042.3885 | 22738.5091
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 671 | 671 | 671 | 671 | 1771 | 0
Construction Costs | 0 | 0 | 671 | 0 | 0 | 0 | 1100 | 20967.5091 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 671 | 671 | 671 | 671 | 1771 | 22738.5091 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.9037% | 0.9037% | 0.9037% | 0.9037% | 2.385% | 30.63% | 30.63%

## J-2153
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Flowrite Construction Developments |  |  |  |  | Steel | 25165.1514 | 0 | 19293.2545 | 0
Estimate Code |  | E00014243 |  |  |  |  | Bolts | 1628.7825 | 0 | 0 | 0
Contract Code |  | J-2153 |  |  |  |  | Purlin | 11803.5 | 0 | 11163.3727 | 0
Contract Name |  | Lot 8, 12 Sant Court, Ravenhall |  |  |  |  | Labour | 9388.8138 | 0 | 4006 | 0
Customer |  | Flowrite Construction Developments |  |  |  |  | Processing | 4489.517 | 0 | 3722.5 | 0
Start Date |  | 30 Oct 2024 |  |  |  |  | Rigging | 16037.3955 | 0 | 0 | 0
Completion Date |  | 13 Aug 2024 |  |  |  |  | Freight | 500 | 0 | 90 | 0
Budgeted Revenue |  | 88500.01 |  |  |  |  | Shop Drawings | 1220.7711 | 0 | 1100 | 0
Budgeted Job Expenditure |  | 73929.2296 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.46% |  |  |  |  | Box Frame | 2400 | 0 | 0 | 0
Estimated Weight |  | 11.373 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 9.9164 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.46% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 449.995 | 0 | 0 | 0
[7 empty] | Other Materials | 734.3261 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 110.9781 | 0 | 0 | 0
[7 empty] | OH & Profit | 14570.7697 | 0 | 0 | 0
[7 empty] | Total | 88500.0002 | 0 | 39375.1273 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 88500 | 88500 | 73929.2296 | 73929.2296 | 14570.7704 | 16.46% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 88500 | 0 | 73929.2296 | 14570.7704 | 16.46% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 88500 | 0 | 73929.2296 | 14570.7704 | 16.46% | 0 | 0 | 316.25 | 316.25 | 0.4278%
Nov 2024 | 0 | 88500 | 0 | 73929.2296 | 14570.7704 | 16.46% | 0 | 0 | 223 | 539.25 | 0.7294%
Dec 2024 | 0 | 88500 | 0 | 73929.2296 | 14570.7704 | 16.46% | 0 | 0 | 0 | 539.25 | 0.7294%
Jan 2025 | 0 | 88500 | 0 | 73929.2296 | 14570.7704 | 16.46% | 0 | 0 | 48 | 587.25 | 0.7943%
Feb 2025 | 0 | 88500 | 0 | 73929.2296 | 14570.7704 | 16.46% | 0 | 0 | 1394.5 | 1981.75 | 2.681%
Mar 2025 | 0 | 88500 | 0 | 73929.2296 | 14570.7704 | 16.46% | 0 | 0 | 37393.3773 | 39375.1273 | 53.26%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 378.58 | 0 | 378.58 | 316.25
Nov 2024 | 645.5312 | 0 | 645.5312 | 539.25
Dec 2024 | 645.5312 | 0 | 645.5312 | 539.25
Jan 2025 | 702.9916 | 0 | 702.9916 | 587.25
Feb 2025 | 2372.3347 | 0 | 2372.3347 | 1981.75
Mar 2025 | 47135.6023 | 0 | 47135.6023 | 39375.1273
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 316.25 | 539.25 | 539.25 | 587.25 | 1981.75 | 0
Construction Costs | 0 | 0 | 316.25 | 223 | 0 | 48 | 1394.5 | 37393.3773 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 316.25 | 539.25 | 539.25 | 587.25 | 1981.75 | 39375.1273 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.4278% | 0.7294% | 0.7294% | 0.7943% | 2.681% | 53.26% | 53.26%

## J-2155
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Texco Construction Pty Ltd |  |  |  |  | Steel | 105000.0123 | 0 | 84603.8 | 0
Estimate Code |  | E00013296 |  |  |  |  | Bolts | 6000.0059 | 0 | 3971.8818 | 0
Contract Code |  | J-2155 |  |  |  |  | Purlin | 43999.9317 | 0 | 0 | 0
Contract Name |  | 4 Westgate Drive, Laverton North |  |  |  |  | Labour | 36999.9487 | 0 | 2736.79 | 0
Customer |  | Texco Construction Pty Ltd |  |  |  |  | Processing | 23000.103 | 0 | 16292.5909 | 0
Start Date |  | 4 Mar 2024 |  |  |  |  | Rigging | 60000.1836 | 0 | 0 | 0
Completion Date |  | 23 Jan 2024 |  |  |  |  | Freight | 2500.0034 | 0 | 921.6545 | 0
Budgeted Revenue |  | 339999.99 |  |  |  |  | Shop Drawings | 6000.0269 | 0 | 6000 | 0
Budgeted Job Expenditure |  | 288500.2115 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.15% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 57.6073 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 59.8923 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.15% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 3199.996 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 800 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1000.0045 | 0 | 672 | 0
[7 empty] | OH & Profit | 51499.7829 | 0 | 0 | 0
[7 empty] | Total | 339999.9989 | 0 | 115198.7173 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 339999.99 | 339999.99 | 288500.2116 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 189 | 189 | 0.06551%
Nov 2024 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 6160.53 | 6349.53 | 2.201%
Dec 2024 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 1457.75 | 7807.28 | 2.706%
Jan 2025 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 2373.76 | 10181.04 | 3.529%
Feb 2025 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 421.6545 | 10602.6945 | 3.675%
Mar 2025 | 0 | 339999.99 | 0 | 288500.2116 | 51499.7784 | 15.15% | 0 | 0 | 104596.0227 | 115198.7173 | 39.93%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 222.7381 | 0 | 222.7381 | 189
Nov 2024 | 7482.9759 | 0 | 7482.9759 | 6349.53
Dec 2024 | 9200.9469 | 0 | 9200.9469 | 7807.28
Jan 2025 | 11998.4435 | 0 | 11998.4435 | 10181.04
Feb 2025 | 12495.3671 | 0 | 12495.3671 | 10602.6945
Mar 2025 | 135762.6828 | 0 | 135762.6828 | 115198.7173
Job Profitability Summary
| Beginning | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 6349.53 | 7807.28 | 10181.04 | 10602.6945 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 6160.53 | 1457.75 | 2373.76 | 421.6545 | 104596.0227 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 6349.53 | 7807.28 | 10181.04 | 10602.6945 | 115198.7173 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.06551% | 2.201% | 2.706% | 3.529% | 3.675% | 39.93% | 39.93%

## J-2157
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Flowrite Construction Developments |  |  |  |  | Steel | 21554.1963 | 0 | 19829.4636 | 0
Estimate Code |  | E00014240 |  |  |  |  | Bolts | 2306.9464 | 0 | 1117.4636 | 0
Contract Code |  | J-2157 |  |  |  |  | Purlin | 15884.3798 | 0 | 12693.6182 | 0
Contract Name |  | Lot 19, 9 Sant Court, Ravenhall |  |  |  |  | Labour | 7978.6721 | 0 | 5236.39 | 0
Customer |  | Flowrite Construction Developments |  |  |  |  | Processing | 4059.2223 | 0 | 5015 | 0
Start Date |  | 30 Oct 2024 |  |  |  |  | Rigging | 17219.0176 | 0 | 18550 | 0
Completion Date |  | 13 Aug 2024 |  |  |  |  | Freight | 500 | 0 | 675 | 0
Budgeted Revenue |  | 92199.99 |  |  |  |  | Shop Drawings | 1583.2294 | 0 | 1100 | 0
Budgeted Job Expenditure |  | 76691.2198 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.82% |  |  |  |  | Box Frame | 4000 | 0 | 2300 | 0
Estimated Weight |  | 10.8608 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 9.7061 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.82% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 600 | 0 | 0 | 0
[7 empty] | Other Materials | 900 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 105.5566 | 0 | 0 | 0
[7 empty] | OH & Profit | 15508.7789 | 0 | 0 | 0
[7 empty] | Total | 92199.9992 | 0 | 66516.9355 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 92200 | 92200 | 76691.2198 | 76691.2198 | 15508.7802 | 16.82% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 92200 | 0 | 76691.2198 | 15508.7802 | 16.82% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 92200 | 0 | 76691.2198 | 15508.7802 | 16.82% | 0 | 0 | 1310 | 1310 | 1.708%
Dec 2024 | 0 | 92200 | 0 | 76691.2198 | 15508.7802 | 16.82% | 0 | 0 | 23267.7136 | 24577.7136 | 32.05%
Jan 2025 | 0 | 92200 | 0 | 76691.2198 | 15508.7802 | 16.82% | 0 | 0 | 8395.6036 | 32973.3173 | 42.99%
Feb 2025 | 0 | 92200 | 0 | 76691.2198 | 15508.7802 | 16.82% | 82000 | 82000 | 33543.6182 | 66516.9355 | 86.73%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 1574.913 | 0 | 1574.913 | 1310
Dec 2024 | 29547.9092 | 0 | 29547.9092 | 24577.7136
Jan 2025 | 39641.3026 | 0 | 39641.3026 | 32973.3173
Feb 2025 | 79968.2346 | 82000 | -2031.7654 | -1690.0062
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 82000 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | -2031.7654 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 1310 | 24577.7136 | 32973.3173 | 0
Construction Costs | 0 | 0 | 1310 | 23267.7136 | 8395.6036 | 33543.6182 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 1310 | 24577.7136 | 32973.3173 | -1690.0062 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 68206.9416 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 1.708% | 32.05% | 42.99% | 86.73% | 86.73%

## J-2158
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Quadrant Building |  |  |  |  | Steel | 94806.771 | 0 | 86418.1927 | 0
Estimate Code |  | E00013537 |  |  |  |  | Bolts | 5621.917 | 0 | 4301.4727 | 0
Contract Code |  | J-2158 |  |  |  |  | Purlin | 31496.2138 | 0 | 31253.5727 | 0
Contract Name |  | 650 Hume Highway, Craigieburn- The Base Precinct 3 |  |  |  |  | Labour | 43348.7146 | 0 | 40991.9 | 11299
Customer |  | Quadrant Building |  |  |  |  | Processing | 19421.498 | 0 | 21152.1318 | 0
Start Date |  | 7 May 2024 |  |  |  |  | Rigging | 62433.8516 | 0 | 64520 | 0
Completion Date |  | 18 Mar 2024 |  |  |  |  | Freight | 1665.1429 | 0 | 4198.75 | 0
Budgeted Revenue |  | 369999.99 |  |  |  |  | Shop Drawings | 7666.3018 | 0 | 6600 | 0
Budgeted Job Expenditure |  | 302447.5472 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 18.26% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 51.1083 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 43.4872 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 18.26% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 34726.0489 | 0 | 33947.1818 | 0
[7 empty] | Grates | 0 | 0 | 623.8 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 750 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 511.0834 | 0 | 0 | 0
[7 empty] | OH & Profit | 67552.4578 | 0 | 0 | 0
[7 empty] | Total | 370000.0007 | 0 | 294007.0018 | 11299
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 370000 | 370000 | 302447.5472 | 302447.5472 | 67552.4528 | 18.26% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | 0 | 0 | 48 | 48 | 0.01587%
Nov 2024 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | 0 | 0 | 86284.3609 | 86332.3609 | 28.54%
Dec 2024 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | 299300 | 299300 | 200058.3482 | 286390.7091 | 94.69%
Jan 2025 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | 37000 | 336300 | 4324.5427 | 290715.2518 | 96.12%
Feb 2025 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | 33700 | 370000 | 9211 | 299926.2518 | 99.17%
Mar 2025 | 0 | 370000 | 0 | 302447.5472 | 67552.4528 | 18.26% | -20185 | 349815 | 5379.75 | 305306.0018 | 100.9%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 58.7209 | 0 | 58.7209 | 48
Nov 2024 | 105614.9201 | 0 | 105614.9201 | 86332.3609
Dec 2024 | 350356.8249 | 299300 | 51056.8249 | 41735.1661
Jan 2025 | 355647.2656 | 336300 | 19347.2656 | 15814.9542
Feb 2025 | 366915.5666 | 370000 | -3084.4334 | -2521.2954
Mar 2025 | 373496.8979 | 349815 | 23681.8979 | 19358.1944
Job Profitability Summary
| Beginning | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299300 | 37000 | 33700 | -20185 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3084.4334 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3084.4334
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 86332.3609 | 41735.1661 | 15814.9542 | -2521.2954 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 86284.3609 | 200058.3482 | 4324.5427 | 9211 | 5379.75 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 48 | 86332.3609 | 41735.1661 | 15814.9542 | -2521.2954 | 19358.1944 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244655.5429 | 30244.7547 | 27547.2496 | -16499.7398 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0.01587% | 28.54% | 94.69% | 96.12% | 99.17% | 100.9% | 100.9%

## J-2159
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Mainbrace Constructions (NSW) |  |  |  |  | Steel | 399999.8963 | 0 | 519064.5609 | 0
Estimate Code |  | E00013933 |  |  |  |  | Bolts | 37000 | 0 | 35084.2818 | 0
Contract Code |  | J-2159 |  |  |  |  | Purlin | 350000.1982 | 0 | 349313.9455 | 0
Contract Name |  | FPI- Bisley Workwear Australia- Lot 8, The Yards |  |  |  |  | Labour | 139999.8906 | 0 | 152870.6 | 0
Customer |  | Mainbrace Constructions (NSW) |  |  |  |  | Processing | 95000.0059 | 0 | 108564.8391 | 0
Start Date | [6 empty] | Rigging | 324000 | 0 | 321599.34 | 0
Completion Date |  | 13 Jun 2024 |  |  |  |  | Freight | 65000 | 0 | 63965.0909 | 0
Budgeted Revenue |  | 1700000.01 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 1442999.9902 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.12% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 321.9024 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 267.179 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 5.02% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 30000 | 0 | 20306 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2000 | 0 | 1569 | 0
[7 empty] | OH & Profit | 257000.017 | 0 | 0 | -171661.17
[7 empty] | Total | 1700000.008 | 0 | 1572337.6582 | -171661.17
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1700000.01 | 1700000.01 | 1442999.9902 | 1442999.9902 | 257000.0198 | 15.12% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 1700000.01 | 0 | 1442999.9902 | 257000.0198 | 15.12% | 0 | 0 | 167514.6809 | 167514.6809 | 11.61%
Oct 2024 | 0 | 1700000.01 | 0 | 1442999.9902 | 257000.0198 | 15.12% | 826000 | 826000 | 874216.8479 | 1041731.5288 | 72.19%
Nov 2024 | 0 | 1700000.01 | 0 | 1442999.9902 | 257000.0198 | 15.12% | 602140 | 1428140 | 457121.3836 | 1498852.9124 | 103.9%
Dec 2024 | 0 | 1700000.01 | 0 | 1442999.9902 | 257000.0198 | 15.12% | 0 | 1428140 | 102778.44 | 1601631.3524 | 111%
Jan 2025 | 0 | 1700000.01 | 171661.17 | 1614661.1602 | 85338.8498 | 5.02% | 168360 | 1596500 | -29856.1909 | 1571775.1615 | 97.34%
Feb 2025 | 0 | 1700000.01 | 0 | 1614661.1602 | 85338.8498 | 5.02% | 0 | 1596500 | 562.5 | 1572337.6615 | 97.38%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 197349.2454 | 0 | 197349.2454 | 167514.6809
Oct 2024 | 1227265.1569 | 826000 | 401265.1569 | 340603.3024
Nov 2024 | 1765800.4043 | 1428140 | 337660.4043 | 286614.0925
Dec 2024 | 1886883.807 | 1428140 | 458743.807 | 389392.5325
Jan 2025 | 1654847.3798 | 1596500 | 58347.3798 | 55418.3808
Feb 2025 | 1655439.6093 | 1596500 | 58939.6093 | 55980.8808
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 826000 | 602140 | 0 | 168360 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 167514.6809 | 340603.3024 | 286614.0925 | 389392.5325 | 55418.3808 | 0
Construction Costs | 0 | 167514.6809 | 874216.8479 | 457121.3836 | 102778.44 | -29856.1909 | 562.5 | #VALUE!
Closing WIP | Difference (GP Exc) | 167514.6809 | 340603.3024 | 286614.0925 | 389392.5325 | 55418.3808 | 55980.8808 | 0
Total Costruction Cost | #VALUE! | 0 | 701128.2264 | 511110.5935 | 0 | 304117.9607 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 11.61% | 72.19% | 103.9% | 111% | 97.34% | 97.38% | 97.38%

## J-2160
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | LSR Construction Group Pty Ltd |  |  |  |  | Steel | 203977.4894 | 0 | 216386.6845 | 0
Estimate Code |  | E00014092 |  |  |  |  | Bolts | 13097.1191 | 0 | 7874.9 | 0
Contract Code |  | J-2160 |  |  |  |  | Purlin | 120600.0443 | 0 | 110304.6 | 0
Contract Name |  | 469 Somerville Road, Brooklyn |  |  |  |  | Labour | 67324.46 | 0 | 74068.87 | 16587
Customer |  | LSR Construction Group Pty Ltd |  |  |  |  | Processing | 43385.3731 | 0 | 42303.75 | 0
Start Date |  | 24 Sep 2024 |  |  |  |  | Rigging | 110000.1016 | 0 | 110000 | 0
Completion Date |  | 15 Jul 2024 |  |  |  |  | Freight | 3600 | 0 | 7220.9545 | 0
Budgeted Revenue |  | 720000.01 |  |  |  |  | Shop Drawings | 10846.2627 | 0 | 11400 | 0
Budgeted Job Expenditure |  | 606963.3219 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.7% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 114.1712 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 119.787 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.7% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 24317.438 | 0 | 23738.5182 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 9130 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 685.0271 | 0 | 0 | 0
[7 empty] | OH & Profit | 113036.6848 | 0 | 0 | 0
[7 empty] | Total | 720000 | 0 | 603298.2773 | 16587
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 720000.01 | 720000.01 | 606963.3219 | 606963.3219 | 113036.6881 | 15.7% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 720000.01 | 0 | 606963.3219 | 113036.6881 | 15.7% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 720000.01 | 0 | 606963.3219 | 113036.6881 | 15.7% | 0 | 0 | 115 | 115 | 0.01895%
Nov 2024 | 0 | 720000.01 | 0 | 606963.3219 | 113036.6881 | 15.7% | 0 | 0 | 50695.43 | 50810.43 | 8.371%
Dec 2024 | 0 | 720000.01 | 0 | 606963.3219 | 113036.6881 | 15.7% | 395900 | 395900 | 421751.9245 | 472562.3545 | 77.86%
Jan 2025 | 0 | 720000.01 | 0 | 606963.3219 | 113036.6881 | 15.7% | 185100 | 581000 | 110688.5764 | 583250.9309 | 96.09%
Feb 2025 | 0 | 720000.01 | 0 | 606963.3219 | 113036.6881 | 15.7% | 61500 | 642500 | 14809.5309 | 598060.4618 | 98.53%
Mar 2025 | 0 | 720000.01 | 0 | 606963.3219 | 113036.6881 | 15.7% | 0 | 642500 | 21824.8205 | 619885.2823 | 102.1%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 136.4168 | 0 | 136.4168 | 115
Nov 2024 | 60273.0162 | 0 | 60273.0162 | 50810.43
Dec 2024 | 560569.1279 | 395900 | 164669.1279 | 138816.8326
Jan 2025 | 691871.5859 | 581000 | 110871.5859 | 93465.2571
Feb 2025 | 709439.1423 | 642500 | 66939.1423 | 56430.005
Mar 2025 | 735328.4677 | 642500 | 92828.4677 | 78254.8255
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 395900 | 185100 | 61500 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 115 | 50810.43 | 138816.8326 | 93465.2571 | 56430.005 | 0
Construction Costs | 0 | 0 | 115 | 50695.43 | 421751.9245 | 110688.5764 | 14809.5309 | 21824.8205 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 115 | 50810.43 | 138816.8326 | 93465.2571 | 56430.005 | 78254.8255 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 333745.5219 | 156040.1518 | 51844.783 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.01895% | 8.371% | 77.86% | 96.09% | 98.53% | 102.1% | 102.1%

## J-2161
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Able Constructions & Management Pty Ltd |  |  |  |  | Steel | 140138.4956 | 2700 | 85561.1155 | 0
Estimate Code |  | E00013163 |  |  |  |  | Bolts | 10019.7793 | 0 | 3958.9818 | 0
Contract Code |  | J-2161 |  |  |  |  | Purlin | 59969.9976 | 0 | 23066.7091 | 0
Contract Name |  | 264-270 Craigieburn Road, Craigieburn |  |  |  |  | Labour | 71607.8783 | 0 | 31277.53 | 0
Customer |  | Able Constructions & Management Pty Ltd |  |  |  |  | Processing | 39059.6924 | 0 | 23081.25 | 0
Start Date |  | 30 Jan 2024 |  |  |  |  | Rigging | 103461.998 | 0 | 68100 | 0
Completion Date |  | 28 Nov 2023 |  |  |  |  | Freight | 3600.0205 | 0 | 3844.5 | 0
Budgeted Revenue |  | 555000.01 |  |  |  |  | Shop Drawings | 10019.7314 | 0 | 7000 | 0
Budgeted Job Expenditure |  | 459005.9227 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.3% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 75.6989 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 50.243 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.21% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 18553.3875 | 0 | 8267.9818 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1100 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1233.2105 | 0 | 0 | 0
[7 empty] | OH & Profit | 96235.8095 | 0 | 0 | 0
[7 empty] | Total | 555000.0005 | 2700 | 254158.0682 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 555000 | 555000 | 459005.9227 | 459005.9227 | 95994.0773 | 17.3% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 555000 | 0 | 459005.9227 | 95994.0773 | 17.3% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 555000 | 0 | 459005.9227 | 95994.0773 | 17.3% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 555000 | 0 | 459005.9227 | 95994.0773 | 17.3% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 555000 | 0 | 459005.9227 | 95994.0773 | 17.3% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 555000 | 0 | 459005.9227 | 95994.0773 | 17.3% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 555000 | 0 | 459005.9227 | 95994.0773 | 17.3% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 555000 | 0 | 459005.9227 | 95994.0773 | 17.3% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 555000 | 0 | 459005.9227 | 95994.0773 | 17.3% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 555000 | 0 | 459005.9227 | 95994.0773 | 17.3% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 2700 | 557700 | 2700 | 461705.9227 | 95994.0773 | 17.21% | 2700 | 2700 | 629 | 629 | 0.1362%
Nov 2024 | 0 | 557700 | 0 | 461705.9227 | 95994.0773 | 17.21% | 0 | 2700 | 35783.2 | 36412.2 | 7.886%
Dec 2024 | 0 | 557700 | 0 | 461705.9227 | 95994.0773 | 17.21% | 0 | 2700 | 18908.8455 | 55321.0455 | 11.98%
Jan 2025 | 0 | 557700 | 0 | 461705.9227 | 95994.0773 | 17.21% | 144450 | 147150 | 72286.1755 | 127607.2209 | 27.64%
Feb 2025 | 0 | 557700 | 0 | 461705.9227 | 95994.0773 | 17.21% | 0 | 147150 | 57332.82 | 184940.0409 | 40.06%
Mar 2025 | 0 | 557700 | 0 | 461705.9227 | 95994.0773 | 17.21% | 212650 | 359800 | 69218.0273 | 254158.0682 | 55.05%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 759.7765 | 2700 | -1940.2235 | -1606.2627
Nov 2024 | 43982.7235 | 2700 | 41282.7235 | 34176.9373
Dec 2024 | 66822.9397 | 2700 | 64122.9397 | 53085.7828
Jan 2025 | 154138.259 | 147150 | 6988.259 | 5785.4054
Feb 2025 | 223391.2448 | 147150 | 76241.2448 | 63118.2254
Mar 2025 | 307000.5119 | 359800 | -52799.4881 | -43711.3795
Job Profitability Summary
| Beginning | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 0 | 144450 | 0 | 212650 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1940.2235 | 0 | 0 | 0 | 0 | -52799.4881 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940.2235 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1606.2627 | 34176.9373 | 53085.7828 | 5785.4054 | 63118.2254 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629 | 35783.2 | 18908.8455 | 72286.1755 | 57332.82 | 69218.0273 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1606.2627 | 34176.9373 | 53085.7828 | 5785.4054 | 63118.2254 | -43711.3795 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2235.2627 | 0 | 0 | 119586.5529 | 0 | 176047.6322 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1362% | 7.886% | 11.98% | 27.64% | 40.06% | 55.05% | 55.05%

## J-2162
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Comfy Pod Pty Ltd |  |  |  |  | Steel | 2000 | 0 | 0 | 0
Estimate Code |  | E00014402 |  |  |  |  | Bolts | 250 | 0 | 0 | 0
Contract Code |  | J-2162 |  |  |  |  | Purlin | 1120 | 0 | 0 | 0
Contract Name |  | Kitchen |  |  |  |  | Labour | 4130 | 0 | 235 | 0
Customer |  | Comfy Pod Pty Ltd |  |  |  |  | Processing | 500 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 16 Sep 2024 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 10100 |  |  |  |  | Shop Drawings | 600 | 0 | 0 | 0
Budgeted Job Expenditure |  | 8600 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 14.85% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 14.85% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 1500 | 0 | 0 | 0
[7 empty] | Total | 10100 | 0 | 235 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 10100 | 10100 | 8600 | 8600 | 1500 | 14.85% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 10100 | 0 | 8600 | 1500 | 14.85% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Sep 2024 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-2163
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Impact Designer Homes |  |  |  |  | Steel | 55272.395 | 0 | 45049.7091 | 0
Estimate Code |  | E00013907 |  |  |  |  | Bolts | 2547.7842 | 0 | 2533.1727 | 0
Contract Code |  | J-2163 |  |  |  |  | Purlin | 34800.0028 | 0 | 27646.3727 | 0
Contract Name |  | Lot 25 Reddish Close, Epping |  |  |  |  | Labour | 24226.9482 | 0 | 18401.81 | 0
Customer |  | Impact Designer Homes |  |  |  |  | Processing | 11999.5208 | 0 | 8286.25 | 0
Start Date |  | 15 Aug 2024 |  |  |  |  | Rigging | 41727.6074 | 0 | 41500 | 0
Completion Date |  | 5 Jun 2024 |  |  |  |  | Freight | 790.5941 | 0 | 1191.25 | 0
Budgeted Revenue |  | 223399.98 |  |  |  |  | Shop Drawings | 3235.7888 | 0 | 3300 | 0
Budgeted Job Expenditure |  | 182685.2626 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 18.23% |  |  |  |  | Box Frame | 5699.998 | 0 | 4800 | 0
Estimated Weight |  | 28.6525 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 24.3396 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 18.23% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1073.822 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 716.3136 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 594.483 | 0 | 0 | 0
[7 empty] | OH & Profit | 40714.7426 | 0 | 0 | 0
[7 empty] | Total | 223400.0004 | 0 | 152708.5645 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 223400 | 223400 | 182685.2626 | 182685.2626 | 40714.7374 | 18.23% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 223400 | 0 | 182685.2626 | 40714.7374 | 18.23% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 223400 | 0 | 182685.2626 | 40714.7374 | 18.23% | 0 | 0 | 250 | 250 | 0.1368%
Oct 2024 | 0 | 223400 | 0 | 182685.2626 | 40714.7374 | 18.23% | 0 | 0 | 50 | 300 | 0.1642%
Nov 2024 | 0 | 223400 | 0 | 182685.2626 | 40714.7374 | 18.23% | 0 | 0 | 0 | 300 | 0.1642%
Dec 2024 | 0 | 223400 | 0 | 182685.2626 | 40714.7374 | 18.23% | 0 | 0 | 3645 | 3945 | 2.159%
Jan 2025 | 0 | 223400 | 0 | 182685.2626 | 40714.7374 | 18.23% | 0 | 0 | 55229.5191 | 59174.5191 | 32.39%
Feb 2025 | 0 | 223400 | 0 | 182685.2626 | 40714.7374 | 18.23% | 223400 | 223400 | 93450.0455 | 152624.5645 | 83.55%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 305.7171 | 0 | 305.7171 | 250
Oct 2024 | 366.8605 | 0 | 366.8605 | 300
Nov 2024 | 366.8605 | 0 | 366.8605 | 300
Dec 2024 | 4824.2151 | 0 | 4824.2151 | 3945
Jan 2025 | 72362.6382 | 0 | 72362.6382 | 59174.5191
Feb 2025 | 186639.728 | 223400 | -36760.272 | -30060.698
Job Profitability Summary
| Beginning | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223400 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36760.272 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 250 | 300 | 300 | 3945 | 59174.5191 | 0
Construction Costs | 0 | 0 | 250 | 50 | 0 | 3645 | 55229.5191 | 93450.0455 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 250 | 300 | 300 | 3945 | 59174.5191 | -30060.698 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 182685.2626 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.1368% | 0.1642% | 0.1642% | 2.159% | 32.39% | 83.55% | 83.55%

## J-3500
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | EPX Build |  |  |  |  | Steel | 0 | 0 | 19752.1136 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-3500 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | J-3500 - 76 Beach Rd, Sandringham |  |  |  |  | Labour | 0 | 0 | 636 | 0
Customer |  | EPX Build |  |  |  |  | Processing | 0 | 0 | 2656.5 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 1285 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 9.0985 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 24329.6136 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 22987.1136 | 22987.1136 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 925 | 23912.1136 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 23912.1136 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 23912.1136 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 417.5 | 24329.6136 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22987.1136 | 925 | 0 | 0 | 417.5 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2165
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 391920.6399 | 0 | 439062.2536 | 0
Estimate Code |  | E00014299 |  |  |  |  | Bolts | 21532.9336 | 0 | 23667 | 0
Contract Code |  | J-2165 |  |  |  |  | Purlin | 188539.2613 | 0 | 181595.5818 | 0
Contract Name |  | 441-459 Kororoit Creek Road, Altona- WH A |  |  |  |  | Labour | 131481.7495 | 0 | 107550.29 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 83098.2031 | 0 | 91437.6364 | 0
Start Date |  | 18 Nov 2024 |  |  |  |  | Rigging | 198000.1562 | 0 | 209706.3818 | 0
Completion Date |  | 26 Aug 2024 |  |  |  |  | Freight | 8000.0381 | 0 | 10166.25 | 0
Budgeted Revenue |  | 1260000.01 |  |  |  |  | Shop Drawings | 20128.8125 | 0 | 18564 | 0
Budgeted Job Expenditure |  | 1103116.0808 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 12.45% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 237.0354 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 228.1087 |  |  |  |  | Stairs | 22499.9881 | 0 | 0 | 0
Current GP% |  | 12.45% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 25170.2937 | 0 | 5471.7273 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 11559.9922 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1183.9921 | 0 | 393 | 0
[7 empty] | OH & Profit | 156883.936 | 0 | 0 | 0
[7 empty] | Total | 1259999.9963 | 0 | 1087614.1209 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1260000.02 | 1260000.02 | 1103116.0808 | 1103116.0808 | 156883.9392 | 12.45% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 1260000.02 | 0 | 1103116.0808 | 156883.9392 | 12.45% | 0 | 0 | 8237.4273 | 8237.4273 | 0.7467%
Dec 2024 | 0 | 1260000.02 | 0 | 1103116.0808 | 156883.9392 | 12.45% | 0 | 0 | 72587.4055 | 80824.8327 | 7.327%
Jan 2025 | 0 | 1260000.02 | 0 | 1103116.0808 | 156883.9392 | 12.45% | 328000 | 328000 | 420109.6214 | 500934.4541 | 45.41%
Feb 2025 | 0 | 1260000.02 | 0 | 1103116.0808 | 156883.9392 | 12.45% | 715592 | 1043592 | 528977.1795 | 1029911.6336 | 93.36%
Mar 2025 | 0 | 1260000.02 | 0 | 1103116.0808 | 156883.9392 | 12.45% | 0 | 1043592 | 57652.4773 | 1087564.1109 | 98.59%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2024 | 9408.945 | 0 | 9408.945 | 8237.4273
Dec 2024 | 92319.6503 | 0 | 92319.6503 | 80824.8327
Jan 2025 | 572176.7937 | 328000 | 244176.7937 | 213774.0821
Feb 2025 | 1176384.518 | 1043592 | 132792.518 | 116258.3807
Mar 2025 | 1242236.2663 | 1043592 | 198644.2663 | 173910.8579
Job Profitability Summary
| Beginning | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 328000 | 715592 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 8237.4273 | 80824.8327 | 213774.0821 | 116258.3807 | 0
Construction Costs | 0 | 8237.4273 | 72587.4055 | 420109.6214 | 528977.1795 | 57652.4773 | #VALUE!
Closing WIP | Difference (GP Exc) | 8237.4273 | 80824.8327 | 213774.0821 | 116258.3807 | 173910.8579 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 287160.372 | 626492.8809 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0.7467% | 7.327% | 45.41% | 93.36% | 98.59% | 98.59%

## J-2166
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Leomilla |  |  |  |  | Steel | 7031.6326 | 0 | 6927.7636 | 0
Estimate Code |  | E00014152 |  |  |  |  | Bolts | 229.397 | 0 | 154.9727 | 0
Contract Code |  | J-2166 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 56 McNamara Street Preston |  |  |  |  | Labour | 2632.9661 | 0 | 1193.5 | 0
Customer |  | Leomilla |  |  |  |  | Processing | 1130.5995 | 0 | 535 | 0
Start Date |  | 1 Sep 2024 |  |  |  |  | Rigging | 3900 | 0 | 3879 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 200 | 0 | 180 | 0
Budgeted Revenue |  | 18000.01 |  |  |  |  | Shop Drawings | 600 | 0 | 485 | 0
Budgeted Job Expenditure |  | 15931.4151 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 11.49% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 3.6048 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 2.4297 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 11.49% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 116.7 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 90.1202 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 2068.5887 | 0 | 0 | 0
[7 empty] | Total | 18000.0041 | 0 | 13355.2364 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 18000 | 18000 | 15931.4151 | 15931.4151 | 2068.5849 | 11.49% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 18000 | 0 | 15931.4151 | 2068.5849 | 11.49% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 18000 | 0 | 15931.4151 | 2068.5849 | 11.49% | 0 | 0 | 12596.2364 | 12596.2364 | 79.07%
Nov 2024 | 0 | 18000 | 0 | 15931.4151 | 2068.5849 | 11.49% | 0 | 0 | 759 | 13355.2364 | 83.83%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 14231.7712 | 0 | 14231.7712 | 12596.2364
Nov 2024 | 15089.3222 | 0 | 15089.3222 | 13355.2364
Job Profitability Summary
| Beginning | Sep 2024 | Oct 2024 | Nov 2024 | Total
Sales | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 12596.2364 | 0
Construction Costs | 0 | 0 | 12596.2364 | 759 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 12596.2364 | 13355.2364 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 79.07% | 83.83% | 83.83%

## J-2168
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Genis Steel Somerton Factory 2 |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2168 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Genis Steel Somerton Factory 2 |  |  |  |  | Labour | 0 | 0 | 2796.38 | 0
Customer |  | Genis Steel Somerton Factory 2 |  |  |  |  | Processing | 0 | 0 | 4512.5 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 56769.3818 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 11250 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 18.6052 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 126889.6182 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 202217.88 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 34787 | 34787 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 53346 | 88133 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 5440.1909 | 93573.1909 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 10564.5455 | 104137.7364 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 47295.0345 | 151432.7709 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 50785.1091 | 202217.88 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34787 | 53346 | 5440.1909 | 10564.5455 | 47295.0345 | 50785.1091 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2170
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | ATG Projects |  |  |  |  | Steel | 264000 | 0 | 299528.6182 | 0
Estimate Code |  | E00014478 |  |  |  |  | Bolts | 4000 | 0 | 17559.1727 | 0
Contract Code |  | J-2170 |  |  |  |  | Purlin | 112600 | 0 | 103237.6818 | 0
Contract Name |  | MACS 20 X 5 Mods |  |  |  |  | Labour | 214000 | 0 | 370169.57 | 12196
Customer |  | ATG Projects |  |  |  |  | Processing | 32000 | 0 | 29245 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 1 Oct 2024 |  |  |  |  | Freight | 0 | 0 | 52840 | 0
Budgeted Revenue |  | 770000 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 680000 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 11.69% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 6.4894 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | -15.31% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 52000 | 0 | 303.9727 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1400 | 0 | 2822 | 0
[7 empty] | OH & Profit | 90000 | 0 | 0 | -207902.2
[7 empty] | Total | 770000 | 0 | 875706.0155 | -195706.2
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 770000 | 770000 | 680000 | 680000 | 90000 | 11.69% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 770000 | 0 | 680000 | 90000 | 11.69% | 115500 | 115500 | 316086.7191 | 316086.7191 | 46.48%
Nov 2024 | 0 | 770000 | 0 | 680000 | 90000 | 11.69% | 269500 | 385000 | 334750.3673 | 650837.0864 | 95.71%
Dec 2024 | 0 | 770000 | 0 | 680000 | 90000 | 11.69% | 231000 | 616000 | 163599.1336 | 814436.22 | 119.8%
Jan 2025 | 0 | 770000 | 0 | 680000 | 90000 | 11.69% | 109870 | 725870 | 70315.7955 | 884752.0155 | 130.1%
Feb 2025 | 0 | 770000 | 207902.2 | 887902.2 | -117902.2 | -15.31% | 0 | 725870 | 1618 | 886370.0155 | 99.83%
Mar 2025 | 0 | 770000 | 0 | 887902.2 | -117902.2 | -15.31% | 0 | 725870 | 1532 | 887902.0155 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | 357921.726 | 115500 | 242421.726 | 214086.7191
Nov 2024 | 736977.289 | 385000 | 351977.289 | 310837.0864
Dec 2024 | 922229.2491 | 616000 | 306229.2491 | 270436.22
Jan 2025 | 1001851.5469 | 725870 | 275981.5469 | 243723.9635
Feb 2025 | 768671.2702 | 725870 | 42801.2702 | 49354.9896
Mar 2025 | 769999.84 | 725870 | 44129.84 | 50886.9896
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 115500 | 269500 | 231000 | 109870 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 214086.7191 | 310837.0864 | 270436.22 | 243723.9635 | 49354.9896 | 0
Construction Costs | 0 | 316086.7191 | 334750.3673 | 163599.1336 | 70315.7955 | 1618 | 1532 | #VALUE!
Closing WIP | Difference (GP Exc) | 214086.7191 | 310837.0864 | 270436.22 | 243723.9635 | 49354.9896 | 50886.9896 | 0
Total Costruction Cost | #VALUE! | 102000 | 238000 | 204000 | 97028.0519 | 195986.9739 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 46.48% | 95.71% | 119.8% | 130.1% | 99.83% | 100% | 100%

## J-2171
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 191256.0603 | 0 | 31773.6818 | 0
Estimate Code |  | E00012665 |  |  |  |  | Bolts | 28535.1523 | 0 | 4024.9636 | 0
Contract Code |  | J-2171 |  |  |  |  | Purlin | 126995.4167 | 0 | 0 | 0
Contract Name |  | 121-125 Northern Road, Heidelberg West |  |  |  |  | Labour | 81182.9678 | 0 | 635 | 0
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 42691.4922 | 0 | 9448.75 | 0
Start Date |  | 24 Aug 2023 |  |  |  |  | Rigging | 146298.75 | 0 | 4200 | 0
Completion Date |  | 4 Jul 2023 |  |  |  |  | Freight | 4223.7729 | 0 | 375 | 0
Budgeted Revenue |  | 819999.99 |  |  |  |  | Shop Drawings | 15941.9316 | 0 | 360 | 0
Budgeted Job Expenditure |  | 683875.9907 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.6% |  |  |  |  | Box Frame | 23466.7964 | 0 | 0 | 0
Estimated Weight |  | 101.0659 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 44.8324 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.6% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 3292.995 | 0 | 780.6909 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 750.0038 | 0 | 0 | 0
[7 empty] | Other Materials | 1000 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1169.0292 | 0 | 0 | 0
[7 empty] | OH & Profit | 146865.7891 | 0 | 0 | 0
[7 empty] | Total | 813670.1572 | 0 | 51598.0864 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 819999.99 | 819999.99 | 683875.9907 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 1920.9864 | 1920.9864 | 0.2809%
Nov 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 5878.6909 | 7799.6773 | 1.141%
Dec 2024 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 7799.6773 | 1.141%
Jan 2025 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 0 | 7799.6773 | 1.141%
Feb 2025 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 31874.4273 | 39674.1045 | 5.801%
Mar 2025 | 0 | 819999.99 | 0 | 683875.9907 | 136123.9993 | 16.6% | 0 | 0 | 11923.9818 | 51598.0864 | 7.545%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 2303.3544 | 0 | 2303.3544 | 1920.9864
Nov 2024 | 9352.1857 | 0 | 9352.1857 | 7799.6773
Dec 2024 | 9352.1857 | 0 | 9352.1857 | 7799.6773
Jan 2025 | 9352.1857 | 0 | 9352.1857 | 7799.6773
Feb 2025 | 47571.1471 | 0 | 47571.1471 | 39674.1045
Mar 2025 | 61868.571 | 0 | 61868.571 | 51598.0864
Job Profitability Summary
| Beginning | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920.9864 | 7799.6773 | 7799.6773 | 7799.6773 | 39674.1045 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920.9864 | 5878.6909 | 0 | 0 | 31874.4273 | 11923.9818 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920.9864 | 7799.6773 | 7799.6773 | 7799.6773 | 39674.1045 | 51598.0864 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2809% | 1.141% | 1.141% | 1.141% | 5.801% | 7.545% | 7.545%

## J-2173
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | FDC Construction & Fitout (Vic) Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00014167 |  |  |  |  | Bolts | 54369 | 0 | 0 | 0
Contract Code |  | J-2173 |  |  |  |  | Purlin | 176160 | 0 | 0 | 0
Contract Name |  | McGrath, 2 Helles Avenue, Moorebank NSW |  |  |  |  | Labour | 1000 | 0 | 0 | 0
Customer |  | FDC Construction & Fitout (Vic) Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 236871 | 0 | 0 | 0
Completion Date |  | 30 Jul 2024 |  |  |  |  | Freight | 8000 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 18000 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 546559 | 0 | 92583.87 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 15541 | 0 | 0 | 0
[7 empty] | OH & Profit | 146500 | 0 | 0 | 0
[7 empty] | Total | 1203000 | 0 | 92583.87 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 90300 | 90300 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 90300 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 2283.87 | 92583.87 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 150375 | 150375 | 0 | 92583.87 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 150375 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Total
Sales | 0 | 0 | 0 | 0 | 150375 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 90300 | 0 | 2283.87 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2175
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Atwal Investment Group |  |  |  |  | Steel | 56000.0417 | 0 | 52294.7364 | 0
Estimate Code |  | E00014217 |  |  |  |  | Bolts | 4539.96 | 0 | 3192.9636 | 0
Contract Code |  | J-2175 |  |  |  |  | Purlin | 30000.0007 | 0 | 26354.4364 | 0
Contract Name |  | Lot 747 Trafalgar Road, Epping |  |  |  |  | Labour | 13287.0072 | 0 | 504.34 | 0
Customer |  | Atwal Investment Group |  |  |  |  | Processing | 48000.0012 | 0 | 46948.6864 | 0
Start Date |  | 25 Oct 2024 |  |  |  |  | Rigging | 49999.7773 | 0 | 0 | 0
Completion Date |  | 8 Aug 2024 |  |  |  |  | Freight | 2499.984 | 0 | 1447.5 | 0
Budgeted Revenue |  | 249999.98 |  |  |  |  | Shop Drawings | 5999.9522 | 0 | 6000 | 0
Budgeted Job Expenditure |  | 212286.725 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.09% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 33.5748 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 29.0965 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.09% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1960 | 0 | 2497.6545 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 37713.2743 | 0 | 0 | 0
[7 empty] | Total | 249999.9987 | 0 | 139240.3173 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 250000 | 250000 | 212286.725 | 212286.725 | 37713.275 | 15.09% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 250000 | 0 | 212286.725 | 37713.275 | 15.09% | 75000 | 75000 | 2143.75 | 2143.75 | 1.01%
Nov 2024 | 0 | 250000 | 0 | 212286.725 | 37713.275 | 15.09% | 0 | 75000 | 2408 | 4551.75 | 2.144%
Dec 2024 | 0 | 250000 | 0 | 212286.725 | 37713.275 | 15.09% | 0 | 75000 | 258.75 | 4810.5 | 2.266%
Jan 2025 | 0 | 250000 | 0 | 212286.725 | 37713.275 | 15.09% | 0 | 75000 | 2000 | 6810.5 | 3.208%
Feb 2025 | 0 | 250000 | 0 | 212286.725 | 37713.275 | 15.09% | 162500 | 237500 | 131715.1945 | 138525.6945 | 65.25%
Mar 2025 | 0 | 250000 | 0 | 212286.725 | 37713.275 | 15.09% | 12500 | 250000 | 714.6227 | 139240.3173 | 65.59%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | 2524.5926 | 75000 | -72475.4074 | -61542.2675
Nov 2024 | 5360.3799 | 75000 | -69639.6201 | -59134.2675
Dec 2024 | 5665.0975 | 75000 | -69334.9025 | -58875.5175
Jan 2025 | 8020.4026 | 75000 | -66979.5974 | -56875.5175
Feb 2025 | 163135.1355 | 237500 | -74364.8645 | -63146.6942
Mar 2025 | 163976.7127 | 250000 | -86023.2873 | -73046.4077
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 75000 | 0 | 0 | 0 | 162500 | 12500 | #VALUE!
Less Current Period Overbills | 0 | -72475.4074 | -69639.6201 | -69334.9025 | -66979.5974 | -74364.8645 | -86023.2873 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 72475.4074 | 69639.6201 | 69334.9025 | 66979.5974 | 74364.8645
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | -61542.2675 | -59134.2675 | -58875.5175 | -56875.5175 | -63146.6942 | 0
Construction Costs | 0 | 2143.75 | 2408 | 258.75 | 2000 | 131715.1945 | 714.6227 | #VALUE!
Closing WIP | Difference (GP Exc) | -61542.2675 | -59134.2675 | -58875.5175 | -56875.5175 | -63146.6942 | -73046.4077 | 0
Total Costruction Cost | #VALUE! | 63686.0175 | 0 | 0 | 0 | 137986.3712 | 10614.3362 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 1.01% | 2.144% | 2.266% | 3.208% | 65.25% | 65.59% | 65.59%

## J-2176
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Built Environs (VIC) |  |  |  |  | Steel | 843051.3939 | 0 | 724251.7627 | 0
Estimate Code |  | E00013890 |  |  |  |  | Bolts | 68775.7969 | 0 | 51682.6727 | 0
Contract Code |  | J-2176 |  |  |  |  | Purlin | 217619.557 | 0 | 168053.0182 | 0
Contract Name |  | Pegasus Drive, Weir Views- Toolern Waters School |  |  |  |  | Labour | 600191.5 | 0 | 328891.4 | 28179
Customer |  | Built Environs (VIC) |  |  |  |  | Processing | 312048.0547 | 0 | 192153.4682 | 0
Start Date | [6 empty] | Rigging | 734000.5 | 0 | 810985 | 0
Completion Date |  | 5 Jun 2024 |  |  |  |  | Freight | 20999.9949 | 0 | 42582.7545 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 471 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 82.2849 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 270.9388 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 31200.0404 | 0 | 0 | 0
[7 empty] | Grates | 23100 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 59057.1182 | 0 | 0 | 0
[7 empty] | Special Paint | 15000 | 0 | 58860 | 0
[7 empty] | Quality Assurance | 13755.2002 | 0 | 3795 | 0
[7 empty] | OH & Profit | 616715.8438 | 0 | 0 | 0
[7 empty] | Total | 3555514.9998 | 0 | 2381726.0764 | 28179
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 42774.2345 | 42774.2345 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 1170667.2 | 1170667.2 | 745306.2955 | 788080.53 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 1170667.2 | 531800.5259 | 1319881.0559 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 238965.16 | 1409632.36 | 516762.1118 | 1836643.1677 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 1175513.72 | 2585146.08 | 568370.9036 | 2405014.0714 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | -153365.2 | 2431780.88 | 4891 | 2409905.0714 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 1170667.2 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 1170667.2 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 1409632.36 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 2585146.08 | #DIV/0! | #DIV/0!
Mar 2025 | #DIV/0! | 2431780.88 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 1170667.2 | 0 | 238965.16 | 1175513.72 | -153365.2 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 42774.2345 | 745306.2955 | 531800.5259 | 516762.1118 | 568370.9036 | 4891 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2179
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Mercs Projects & Developments Pty Ltd |  |  |  |  | Steel | 6571.0576 | 0 | 0 | 0
Estimate Code |  | E00012938 |  |  |  |  | Bolts | 339.7926 | 0 | 50.5364 | 0
Contract Code |  | J-2179 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 37 Golf Road, Coburg North |  |  |  |  | Labour | 2439.1715 | 0 | 1913.75 | 0
Customer |  | Mercs Projects & Developments Pty Ltd |  |  |  |  | Processing | 837.346 | 0 | 402.5 | 0
Start Date |  | 3 Nov 2023 |  |  |  |  | Rigging | 5000 | 0 | 0 | 0
Completion Date |  | 14 Sep 2023 |  |  |  |  | Freight | 350 | 0 | 0 | 0
Budgeted Revenue |  | 20999.99 |  |  |  |  | Shop Drawings | 934.4296 | 0 | 480 | 0
Budgeted Job Expenditure |  | 16839.8949 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 19.81% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 2.6698 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 2.5034 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 19.81% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 301.352 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 66.745 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 4160.1058 | 0 | 0 | 0
[7 empty] | Total | 21000.0001 | 0 | 2846.7864 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 21000 | 21000 | 16839.8949 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 1183.5 | 1183.5 | 7.028%
Dec 2024 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 1183.5 | 7.028%
Jan 2025 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 1183.5 | 7.028%
Feb 2025 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 0 | 1183.5 | 7.028%
Mar 2025 | 0 | 21000 | 0 | 16839.8949 | 4160.1051 | 19.81% | 0 | 0 | 1663.2864 | 2846.7864 | 16.91%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 1475.8703 | 0 | 1475.8703 | 1183.5
Dec 2024 | 1475.8703 | 0 | 1475.8703 | 1183.5
Jan 2025 | 1475.8703 | 0 | 1475.8703 | 1183.5
Feb 2025 | 1475.8703 | 0 | 1475.8703 | 1183.5
Mar 2025 | 3550.0526 | 0 | 3550.0526 | 2846.7864
Job Profitability Summary
| Beginning | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183.5 | 1183.5 | 1183.5 | 1183.5 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183.5 | 0 | 0 | 0 | 1663.2864 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183.5 | 1183.5 | 1183.5 | 1183.5 | 2846.7864 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.028% | 7.028% | 7.028% | 7.028% | 16.91% | 16.91%

## J-2181
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Sage Group |  |  |  |  | Steel | -1098.43 | 0 | 2175.01 | 0
Estimate Code |  | E00013830 |  |  |  |  | Bolts | 786.25 | 0 | 759.6273 | 0
Contract Code |  | J-2181 |  |  |  |  | Purlin | 0 | 0 | 1994 | 0
Contract Name |  | Garage and Farm Shed |  |  |  |  | Labour | 3984.6899 | 0 | 3820.95 | 85
Customer |  | Sage Group |  |  |  |  | Processing | 890.32 | 0 | 876.25 | 0
Start Date | [6 empty] | Rigging | 2000 | 0 | 0 | 0
Completion Date |  | 21 May 2024 |  |  |  |  | Freight | 0 | 0 | 405 | 0
Budgeted Revenue |  | 9150.03 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 9150.0299 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 1.639e-06% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.87692 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 1.639e-06% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 831.25 | 0 | 837.6818 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1755.9499 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 9150.0299 | 0 | 10868.5191 | 85
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 9150.03 | 9150.03 | 9150.0299 | 9150.0299 | 0.00015 | 1.639e-06% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 9150.03 | 0 | 9150.0299 | 0.00015 | 1.639e-06% | 0 | 0 | 1419.95 | 1419.95 | 15.52%
Nov 2024 | 0 | 9150.03 | 0 | 9150.0299 | 0.00015 | 1.639e-06% | 0 | 0 | 4136.75 | 5556.7 | 60.73%
Dec 2024 | 0 | 9150.03 | 0 | 9150.0299 | 0.00015 | 1.639e-06% | 0 | 0 | 7143.8391 | 12700.5391 | 138.8%
Jan 2025 | 0 | 9150.03 | 0 | 9150.0299 | 0.00015 | 1.639e-06% | 0 | 0 | 0 | 12700.5391 | 138.8%
Feb 2025 | 0 | 9150.03 | 0 | 9150.0299 | 0.00015 | 1.639e-06% | 0 | 0 | -1747.02 | 10953.5191 | 119.7%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | 1419.95 | 0 | 1419.95 | 1419.95
Nov 2024 | 5556.7001 | 0 | 5556.7001 | 5556.7
Dec 2024 | 12700.5393 | 0 | 12700.5393 | 12700.5391
Jan 2025 | 12700.5393 | 0 | 12700.5393 | 12700.5391
Feb 2025 | 10953.5193 | 0 | 10953.5193 | 10953.5191
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 1419.95 | 5556.7 | 12700.5391 | 12700.5391 | 0
Construction Costs | 0 | 1419.95 | 4136.75 | 7143.8391 | 0 | -1747.02 | #VALUE!
Closing WIP | Difference (GP Exc) | 1419.95 | 5556.7 | 12700.5391 | 12700.5391 | 10953.5191 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 15.52% | 60.73% | 138.8% | 138.8% | 119.7% | 119.7%

## J-2184
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Hutchinson Builders |  |  |  |  | Steel | 450688.373 | 0 | 413920.2464 | 0
Estimate Code |  | E00013810 |  |  |  |  | Bolts | 50050.0469 | 0 | 39596.9818 | 0
Contract Code |  | J-2184 |  |  |  |  | Purlin | 74529.5009 | 0 | 47248.8182 | 0
Contract Name |  | 28-32 Carrick Drive, Tullamarine- NS Tullamarine |  |  |  |  | Labour | 190904.2031 | 0 | 5745.64 | 0
Customer |  | Hutchinson Builders |  |  |  |  | Processing | 56370.4316 | 0 | 69742.9955 | 0
Start Date |  | 25 Jul 2024 |  |  |  |  | Rigging | 288492.7031 | 0 | 252736.8 | 0
Completion Date |  | 15 May 2024 |  |  |  |  | Freight | 6607.0967 | 0 | 14795.4245 | 0
Budgeted Revenue |  | 1450000.02 |  |  |  |  | Shop Drawings | 22407.998 | 0 | 20754.9091 | 0
Budgeted Job Expenditure |  | 1146781.252 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.91% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 225.1381 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 220.8276 |  |  |  |  | Stairs | 0 | 0 | 175100 | 0
Current GP% |  | 20.91% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1000 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 5730.8911 | 0 | 5320 | 0
[7 empty] | OH & Profit | 303218.756 | 0 | 0 | 0
[7 empty] | Total | 1450000.0005 | 0 | 1044961.8155 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1450000 | 1450000 | 1146781.2519 | 1146781.2519 | 303218.748 | 20.91% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 1450000 | 0 | 1146781.2519 | 303218.748 | 20.91% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 1450000 | 0 | 1146781.2519 | 303218.748 | 20.91% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 1450000 | 0 | 1146781.2519 | 303218.748 | 20.91% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 1450000 | 0 | 1146781.2519 | 303218.748 | 20.91% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 1450000 | 0 | 1146781.2519 | 303218.748 | 20.91% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 1450000 | 0 | 1146781.2519 | 303218.748 | 20.91% | 0 | 0 | 211656.9955 | 211656.9955 | 18.46%
Jan 2025 | 0 | 1450000 | 0 | 1146781.2519 | 303218.748 | 20.91% | 165355 | 165355 | 302189.5555 | 513846.5509 | 44.81%
Feb 2025 | 0 | 1450000 | 0 | 1146781.2519 | 303218.748 | 20.91% | 712374.45 | 877729.45 | 438753.4964 | 952600.0473 | 83.07%
Mar 2025 | 0 | 1450000 | 0 | 1146781.2519 | 303218.748 | 20.91% | 0 | 877729.45 | 92361.7682 | 1044961.8155 | 91.12%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 267620.911 | 0 | 267620.911 | 211656.9955
Jan 2025 | 649711.9634 | 165355 | 484356.9634 | 383069.9896
Feb 2025 | 1204475.6279 | 877729.45 | 326746.1779 | 258418.2007
Mar 2025 | 1321258.6357 | 877729.45 | 443529.1857 | 350779.9689
Job Profitability Summary
| Beginning | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165355 | 712374.45 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211656.9955 | 383069.9896 | 258418.2007 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 211656.9955 | 302189.5555 | 438753.4964 | 92361.7682 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 211656.9955 | 383069.9896 | 258418.2007 | 350779.9689 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 130776.5613 | 563405.2853 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 18.46% | 44.81% | 83.07% | 91.12% | 91.12%

## J-2190
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Texco Construction Pty Ltd |  |  |  |  | Steel | 498198.4577 | 0 | 198052.1273 | 0
Estimate Code |  | E00013927 |  |  |  |  | Bolts | 32119.9434 | 0 | 22970.7727 | 0
Contract Code |  | J-2190 |  |  |  |  | Purlin | 177651.9283 | 0 | 75725 | 0
Contract Name |  | 813-913 Wallgrove Road, Eastern Creek- Chanel Lot |  |  |  |  | Labour | 169339.6445 | 0 | 60053.64 | 0
Customer |  | Texco Construction Pty Ltd |  |  |  |  | Processing | 112110.877 | 0 | 54003.6682 | 0
Start Date |  | 21 Aug 2024 |  |  |  |  | Rigging | 354153.375 | 0 | 0 | 0
Completion Date |  | 13 Jun 2024 |  |  |  |  | Freight | 76999.9229 | 0 | 2444.3 | 0
Budgeted Revenue |  | 1889179.97 |  |  |  |  | Shop Drawings | 24819.8516 | 0 | 20000 | 0
Budgeted Job Expenditure |  | 1577944.8548 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.47% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 287.8131 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 289.8961 |  |  |  |  | Stairs | 48000 | 0 | 0 | 0
Current GP% |  | 16.47% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 8291.0098 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 23340 | 0 | 0 | 0
[7 empty] | Special Paint | 50000 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2919.864 | 0 | 1062 | 0
[7 empty] | OH & Profit | 311235.1239 | 0 | 0 | 0
[7 empty] | Total | 1889179.998 | 0 | 434311.5082 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1889179.98 | 1889179.98 | 1577944.8547 | 1577944.8547 | 311235.1253 | 16.47% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 1889179.98 | 0 | 1577944.8547 | 311235.1253 | 16.47% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 1889179.98 | 0 | 1577944.8547 | 311235.1253 | 16.47% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 1889179.98 | 0 | 1577944.8547 | 311235.1253 | 16.47% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 1889179.98 | 0 | 1577944.8547 | 311235.1253 | 16.47% | 0 | 0 | 6529.8945 | 6529.8945 | 0.4138%
Dec 2024 | 0 | 1889179.98 | 0 | 1577944.8547 | 311235.1253 | 16.47% | 0 | 0 | 5447.01 | 11976.9045 | 0.759%
Jan 2025 | 0 | 1889179.98 | 0 | 1577944.8547 | 311235.1253 | 16.47% | 0 | 0 | 24001.78 | 35978.6845 | 2.28%
Feb 2025 | 0 | 1889179.98 | 0 | 1577944.8547 | 311235.1253 | 16.47% | 0 | 0 | 244632.5382 | 280611.2227 | 17.78%
Mar 2025 | 0 | 1889179.98 | 0 | 1577944.8547 | 311235.1253 | 16.47% | 0 | 0 | 153700.2955 | 434311.5182 | 27.52%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 7817.8563 | 0 | 7817.8563 | 6529.8945
Dec 2024 | 14339.2389 | 0 | 14339.2389 | 11976.9045
Jan 2025 | 43075.1495 | 0 | 43075.1495 | 35978.6845
Feb 2025 | 335959.2083 | 0 | 335959.2083 | 280611.2227
Mar 2025 | 519975.4749 | 0 | 519975.4749 | 434311.5182
Job Profitability Summary
| Beginning | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 6529.8945 | 11976.9045 | 35978.6845 | 280611.2227 | 0
Construction Costs | 0 | 0 | 0 | 0 | 6529.8945 | 5447.01 | 24001.78 | 244632.5382 | 153700.2955 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 6529.8945 | 11976.9045 | 35978.6845 | 280611.2227 | 434311.5182 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0.4138% | 0.759% | 2.28% | 17.78% | 27.52% | 27.52%

## J-2191
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | A Grade Concrete Pty Ltd |  |  |  |  | Steel | 98612.0127 | 0 | 0 | 0
Estimate Code |  | E00014346 |  |  |  |  | Bolts | 5114.542 | 0 | 0 | 0
Contract Code |  | J-2191 |  |  |  |  | Purlin | 33889.4198 | 0 | 0 | 0
Contract Name |  | Lot 65 Forefront Drive, Mickleham- Factory 1 |  |  |  |  | Labour | 32536.5342 | 0 | 0 | 0
Customer |  | A Grade Concrete Pty Ltd |  |  |  |  | Processing | 17435.3667 | 0 | 0 | 0
Start Date |  | 2 Dec 2024 |  |  |  |  | Rigging | 60000.375 | 0 | 0 | 0
Completion Date |  | 4 Sep 2024 |  |  |  |  | Freight | 2000.0251 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 4794.5776 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 9000 | 0 | 0 | 0
Estimated Weight |  | 43.5875 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 26000.0085 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1424.278 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 900 | 0 | 0 | 0
[7 empty] | Other Materials | 1985 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 435.8747 | 0 | 0 | 0
[7 empty] | OH & Profit | 56971.9862 | 0 | 0 | 0
[7 empty] | Total | 351100.0005 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2192
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | A Grade Concrete Pty Ltd |  |  |  |  | Steel | 81090.5879 | 0 | 0 | 0
Estimate Code |  | E00014347 |  |  |  |  | Bolts | 3663.4382 | 0 | 0 | 0
Contract Code |  | J-2192 |  |  |  |  | Purlin | 30127.5008 | 0 | 0 | 0
Contract Name |  | Lot 65 Forefront Drive, Mickleham- Factory 2 |  |  |  |  | Labour | 22994.3218 | 0 | 0 | 0
Customer |  | A Grade Concrete Pty Ltd |  |  |  |  | Processing | 13321.7266 | 0 | 0 | 0
Start Date |  | 2 Dec 2024 |  |  |  |  | Rigging | 49999.6211 | 0 | 0 | 0
Completion Date |  | 4 Sep 2024 |  |  |  |  | Freight | 1500 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 3663.4656 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 6000 | 0 | 0 | 0
Estimated Weight |  | 33.3045 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 30.1024 |  |  |  |  | Stairs | 12999.9958 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 2668.3841 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 900 | 0 | 0 | 0
[7 empty] | Other Materials | 1215 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 333.0453 | 0 | 0 | 0
[7 empty] | OH & Profit | 44322.9131 | 0 | 0 | 0
[7 empty] | Total | 274800.0002 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2193
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | A Grade Concrete Pty Ltd |  |  |  |  | Steel | 12144.1367 | 0 | 0 | 0
Estimate Code |  | E00014426 |  |  |  |  | Bolts | 1003.1307 | 0 | 0 | 0
Contract Code |  | J-2193 |  |  |  |  | Purlin | 7317.495 | 0 | 0 | 0
Contract Name |  | 35 Prime Street, Thomastown |  |  |  |  | Labour | 5055.2275 | 0 | 273 | 0
Customer |  | A Grade Concrete Pty Ltd |  |  |  |  | Processing | 2705.413 | 0 | 1581.25 | 0
Start Date |  | 17 Jan 2025 |  |  |  |  | Rigging | 17698.9434 | 0 | 0 | 0
Completion Date |  | 19 Sep 2024 |  |  |  |  | Freight | 400 | 0 | 0 | 0
Budgeted Revenue |  | 61600 |  |  |  |  | Shop Drawings | 1003.1307 | 0 | 0 | 0
Budgeted Job Expenditure |  | 51644.3524 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.16% |  |  |  |  | Box Frame | 4000 | 0 | 0 | 0
Estimated Weight |  | 6.6875 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 6.5136 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.16% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 250 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 66.8754 | 0 | 0 | 0
[7 empty] | OH & Profit | 9955.648 | 0 | 0 | 0
[7 empty] | Total | 61600.0003 | 0 | 1854.25 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 61600 | 61600 | 51644.3524 | 51644.3524 | 9955.6476 | 16.16% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 61600 | 0 | 51644.3524 | 9955.6476 | 16.16% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2024 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Nov 2024 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-2194
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Lane Con Building |  |  |  |  | Steel | 10902.3737 | 0 | 7201.8636 | 0
Estimate Code |  | E00014396 |  |  |  |  | Bolts | 621.6462 | 0 | 113.8636 | 0
Contract Code |  | J-2194 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 6 Hardinge Street, Beaumaris |  |  |  |  | Labour | 4526.9177 | 0 | 1001.25 | 0
Customer |  | Lane Con Building |  |  |  |  | Processing | 2508.7865 | 0 | 1056.25 | 0
Start Date |  | 13 Jan 2025 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 12 Sep 2024 |  |  |  |  | Freight | 600 | 0 | 312.5 | 0
Budgeted Revenue |  | 27000 |  |  |  |  | Shop Drawings | 1709.5271 | 0 | 1700 | 0
Budgeted Job Expenditure |  | 21569.6911 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.11% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 4.8844 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 4.1782 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 20.11% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 578.33 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 122.1091 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 5430.3102 | 0 | 0 | 0
[7 empty] | Total | 27000.0005 | 0 | 11385.7273 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 27000 | 27000 | 21569.6911 | 21569.6911 | 5430.3089 | 20.11% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 27000 | 0 | 21569.6911 | 5430.3089 | 20.11% | 5400 | 5400 | 0 | 0 | 0%
Nov 2024 | 0 | 27000 | 0 | 21569.6911 | 5430.3089 | 20.11% | 0 | 5400 | 9907.9773 | 9907.9773 | 45.93%
Dec 2024 | 0 | 27000 | 0 | 21569.6911 | 5430.3089 | 20.11% | 11600 | 17000 | 1477.75 | 11385.7273 | 52.79%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | 0 | 5400 | -5400 | -4313.9382
Nov 2024 | 12402.3745 | 5400 | 7002.3745 | 5594.0391
Dec 2024 | 14252.1576 | 17000 | -2747.8424 | -2195.1893
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 5400 | 0 | 11600 | #VALUE!
Less Current Period Overbills | 0 | -5400 | 0 | -2747.8424 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 5400 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | -4313.9382 | 5594.0391 | 0
Construction Costs | 0 | 0 | 9907.9773 | 1477.75 | #VALUE!
Closing WIP | Difference (GP Exc) | -4313.9382 | 5594.0391 | -2195.1893 | 0
Total Costruction Cost | #VALUE! | 4313.9382 | 0 | 9266.9784 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 45.93% | 52.79% | 52.79%

## J-2195
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Marven Construction |  |  |  |  | Steel | 6663.7237 | 0 | 1137.45 | 0
Estimate Code |  | E00013843 |  |  |  |  | Bolts | 421.1305 | 0 | 103.9091 | 0
Contract Code |  | J-2195 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 17 Martin Street Brighton |  |  |  |  | Labour | 3545.9278 | 0 | 2046 | 0
Customer |  | Marven Construction |  |  |  |  | Processing | 1037.7859 | 0 | 1227.5 | 0
Start Date |  | 1 Aug 2024 |  |  |  |  | Rigging | 8500 | 0 | 5033.6 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 500 | 0 | 0 | 0
Budgeted Revenue |  | 28800.01 |  |  |  |  | Shop Drawings | 1158.1089 | 0 | 1158 | 0
Budgeted Job Expenditure |  | 22365.6649 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 22.34% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 3.3089 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 3.4407 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 22.34% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 456.265 | 0 | 1723.9182 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 82.7221 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 6434.3365 | 0 | 0 | 0
[7 empty] | Total | 28800.0004 | 0 | 12430.3773 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 28800 | 28800 | 22365.6649 | 22365.6649 | 6434.3351 | 22.34% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 28800 | 0 | 22365.6649 | 6434.3351 | 22.34% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 28800 | 0 | 22365.6649 | 6434.3351 | 22.34% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 28800 | 0 | 22365.6649 | 6434.3351 | 22.34% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 28800 | 0 | 22365.6649 | 6434.3351 | 22.34% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 28800 | 0 | 22365.6649 | 6434.3351 | 22.34% | 0 | 0 | 590 | 590 | 2.638%
Jan 2025 | 0 | 28800 | 0 | 22365.6649 | 6434.3351 | 22.34% | 0 | 0 | 0 | 590 | 2.638%
Feb 2025 | 0 | 28800 | 0 | 22365.6649 | 6434.3351 | 22.34% | 0 | 0 | 2330.95 | 2920.95 | 13.06%
Mar 2025 | 0 | 28800 | 0 | 22365.6649 | 6434.3351 | 22.34% | 0 | 0 | 9509.4273 | 12430.3773 | 55.58%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 759.736 | 0 | 759.736 | 590
Jan 2025 | 759.736 | 0 | 759.736 | 590
Feb 2025 | 3761.2725 | 0 | 3761.2725 | 2920.95
Mar 2025 | 16006.4486 | 0 | 16006.4486 | 12430.3773
Job Profitability Summary
| Beginning | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 590 | 590 | 2920.95 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 590 | 0 | 2330.95 | 9509.4273 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 590 | 590 | 2920.95 | 12430.3773 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 2.638% | 2.638% | 13.06% | 55.58% | 55.58%

## J-2196
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 86116.0597 | 0 | 69283.7236 | 0
Estimate Code |  | E00014427 |  |  |  |  | Bolts | 5262.9204 | 0 | 3343.7091 | 0
Contract Code |  | J-2196 |  |  |  |  | Purlin | 21004.2494 | 0 | 5054.5545 | 0
Contract Name |  | 144-150 Hall Street, Spotwood- Building A, B & C |  |  |  |  | Labour | 35612.4332 | 0 | 17064.52 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 19355.4316 | 0 | 19353.25 | 0
Start Date |  | 20 Jan 2025 |  |  |  |  | Rigging | 94349.0156 | 0 | 0 | 0
Completion Date |  | 20 Sep 2024 |  |  |  |  | Freight | 3000.0081 | 0 | 850.0591 | 0
Budgeted Revenue |  | 344999.99 |  |  |  |  | Shop Drawings | 7176.7202 | 0 | 4096 | 0
Budgeted Job Expenditure |  | 285193.724 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.34% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 51.1071 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 41.5223 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.34% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 2924.916 | 0 | 1213.2909 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 9770 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 621.9739 | 0 | 0 | 0
[7 empty] | OH & Profit | 59806.2726 | 0 | 0 | 0
[7 empty] | Total | 345000.0008 | 0 | 120259.1073 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 345000 | 345000 | 285193.724 | 285193.724 | 59806.276 | 17.34% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 345000 | 0 | 285193.724 | 59806.276 | 17.34% | 0 | 0 | 2889 | 2889 | 1.013%
Jan 2025 | 0 | 345000 | 0 | 285193.724 | 59806.276 | 17.34% | 0 | 0 | 33010.4318 | 35899.4318 | 12.59%
Feb 2025 | 0 | 345000 | 0 | 285193.724 | 59806.276 | 17.34% | 59800 | 59800 | 55383.5073 | 91282.9391 | 32.01%
Mar 2025 | 0 | 345000 | 0 | 285193.724 | 59806.276 | 17.34% | 0 | 59800 | 28847.1682 | 120130.1073 | 42.12%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 3494.835 | 0 | 3494.835 | 2889
Jan 2025 | 43427.6877 | 0 | 43427.6877 | 35899.4318
Feb 2025 | 110425.3402 | 59800 | 50625.3402 | 41849.3603
Mar 2025 | 145321.876 | 59800 | 85521.876 | 70696.5284
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 59800 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 2889 | 35899.4318 | 41849.3603 | 0
Construction Costs | 0 | 2889 | 33010.4318 | 55383.5073 | 28847.1682 | #VALUE!
Closing WIP | Difference (GP Exc) | 2889 | 35899.4318 | 41849.3603 | 70696.5284 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 49433.5788 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 1.013% | 12.59% | 32.01% | 42.12% | 42.12%

## J-2197
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | AusPro Steel |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2197 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Lot 41, 9 Interchange Drive, Mickleham |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | AusPro Steel |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 1700 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 1700 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 1700 | 1700 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | 0
Construction Costs | 0 | 0 | 1700 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2199
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Squared |  |  |  |  | Steel | 36313.8444 | 0 | 32600.7364 | 0
Estimate Code |  | E00014293 |  |  |  |  | Bolts | 3068.4084 | 0 | 1922.6818 | 0
Contract Code |  | J-2199 |  |  |  |  | Purlin | 4869.2969 | 0 | 4278.1364 | 0
Contract Name |  | Beon Energy-BUW Substation |  |  |  |  | Labour | 21918.5719 | 0 | 20238.13 | 0
Customer |  | Squared |  |  |  |  | Processing | 9347.6965 | 0 | 6710.0818 | 0
Start Date |  | 18 Nov 2024 |  |  |  |  | Rigging | 0 | 8000 | 0 | 0
Completion Date |  | 21 Aug 2024 |  |  |  |  | Freight | 1800 | 0 | 4833.4909 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 19.3116 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 16.0136 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 0% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 17564.7815 | 0 | 253.6 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2432.7898 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 192000 | 192000 | 0
[7 empty] | Quality Assurance | 1615.15 | 0 | 2157.5 | 0
[7 empty] | OH & Profit | 25669.4593 | 0 | 0 | 0
[7 empty] | Total | 124599.9988 | 200000 | 264994.3573 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 43429.2848 | 43429.2848 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 221565.0641 | 264994.3489 | #DIV/0!
Mar 2025 | 200000 | 200000 | 200000 | 200000 | 0 | 0% | 338000 | 338000 | 0 | 264994.3489 | 132.5%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2025 | 264994.3489 | 338000 | -73005.6511 | -73005.6511
Job Profitability Summary
| Beginning | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 338000 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -73005.6511 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 43429.2848 | 221565.0641 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -73005.6511 | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 73005.6511 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 132.5% | 132.5%

## J-2200
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | LSR Construction Group Pty Ltd |  |  |  |  | Steel | 425698.6509 | 0 | 256966.3036 | 0
Estimate Code |  | E00013652 |  |  |  |  | Bolts | 31510.3945 | 0 | 21062.2273 | 0
Contract Code |  | J-2200 |  |  |  |  | Purlin | 149160.6755 | 0 | 0 | 0
Contract Name |  | 32-36 Peet Street, Pakenham |  |  |  |  | Labour | 171444.523 | 0 | 7609.96 | 0
Customer |  | LSR Construction Group Pty Ltd |  |  |  |  | Processing | 93239.6543 | 0 | 11678.75 | 0
Start Date |  | 11 Jun 2024 |  |  |  |  | Rigging | 231000.2031 | 0 | 0 | 0
Completion Date |  | 12 Apr 2024 |  |  |  |  | Freight | 14400.0745 | 0 | 1361.4045 | 0
Budgeted Revenue |  | 1499999.99 |  |  |  |  | Shop Drawings | 22573.7832 | 0 | 37000 | 0
Budgeted Job Expenditure |  | 1239390.7034 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.37% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 245.3672 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 194.3338 |  |  |  |  | Stairs | 62999.982 | 0 | 0 | 0
Current GP% |  | 17.37% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 7389.1001 | 0 | 6072.4 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 27520 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2453.6721 | 0 | 0 | 0
[7 empty] | OH & Profit | 260609.2987 | 0 | 0 | 0
[7 empty] | Total | 1500000.0118 | 0 | 341751.0455 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1499999.99 | 1499999.99 | 1239390.7034 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 1499999.99 | 0 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 1499999.99 | 0 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 1499999.99 | 0 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 1499999.99 | 0 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 1499999.99 | 0 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 1499999.99 | 0 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 7500 | 7500 | 0.6051%
Dec 2024 | 0 | 1499999.99 | 0 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 14218.02 | 21718.02 | 1.752%
Jan 2025 | 0 | 1499999.99 | 0 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 77690.2276 | 99408.2476 | 8.021%
Feb 2025 | 0 | 1499999.99 | 0 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 236270.3945 | 335678.6421 | 27.08%
Mar 2025 | 0 | 1499999.99 | 0 | 1239390.7034 | 260609.2866 | 17.37% | 0 | 0 | 6072.4 | 341751.0421 | 27.57%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 9077.0408 | 0 | 9077.0408 | 7500
Dec 2024 | 26284.7137 | 0 | 26284.7137 | 21718.02
Jan 2025 | 120311.0286 | 0 | 120311.0286 | 99408.2476
Feb 2025 | 406262.4953 | 0 | 406262.4953 | 335678.6421
Mar 2025 | 413611.7516 | 0 | 413611.7516 | 341751.0421
Job Profitability Summary
| Beginning | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 21718.02 | 99408.2476 | 335678.6421 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 14218.02 | 77690.2276 | 236270.3945 | 6072.4 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 7500 | 21718.02 | 99408.2476 | 335678.6421 | 341751.0421 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0.6051% | 1.752% | 8.021% | 27.08% | 27.57% | 27.57%

## J-2201
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Flowrite Construction Developments |  |  |  |  | Steel | 59113.904 | 0 | 0 | 0
Estimate Code |  | E00014349 |  |  |  |  | Bolts | 3802.429 | 0 | 1787.9182 | 0
Contract Code |  | J-2201 |  |  |  |  | Purlin | 23885.1744 | 0 | 0 | 0
Contract Name |  | Lot 69, 31 East Derrimut Crescent, Derrimut |  |  |  |  | Labour | 21606.4512 | 0 | 680 | 0
Customer |  | Flowrite Construction Developments |  |  |  |  | Processing | 10977.2864 | 0 | 0 | 0
Start Date |  | 3 Dec 2024 |  |  |  |  | Rigging | 45699.5977 | 0 | 0 | 0
Completion Date |  | 5 Sep 2024 |  |  |  |  | Freight | 1500.0005 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 3449.9729 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 3000 | 0 | 0 | 0
Estimated Weight |  | 32.3186 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1074.22 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 1350 | 0 | 0 | 0
[7 empty] | Other Materials | 1000 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 504.234 | 0 | 0 | 0
[7 empty] | OH & Profit | 43036.7304 | 0 | 0 | 0
[7 empty] | Total | 220000.0004 | 0 | 2467.9182 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 120 | 120 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 120 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 2347.9182 | 2467.9182 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 120 | 0 | 2347.9182 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2202
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 363058.9273 | 0 | 389927.5755 | 0
Estimate Code |  | E00014623 |  |  |  |  | Bolts | 24569.8887 | 0 | 21101.6455 | 0
Contract Code |  | J-2202 |  |  |  |  | Purlin | 190658.8051 | 0 | 174027.9455 | 0
Contract Name |  | 441-459 Kororoit Creek Road, Altona- WH B |  |  |  |  | Labour | 128087.8876 | 0 | 100706.01 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 79838.7012 | 0 | 52377.5 | 0
Start Date |  | 18 Feb 2025 |  |  |  |  | Rigging | 219028.3281 | 0 | 122750 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 8000.0796 | 0 | 15887.04 | 0
Budgeted Revenue |  | 1270000.01 |  |  |  |  | Shop Drawings | 20425.043 | 0 | 25018.1818 | 0
Budgeted Job Expenditure |  | 1094662.829 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 13.81% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 228.3429 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 207.2694 |  |  |  |  | Stairs | 29999.9962 | 0 | 0 | 0
Current GP% |  | 13.81% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 13395.095 | 0 | 3682.2727 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 15450 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2150.0767 | 0 | 0 | 0
[7 empty] | OH & Profit | 175337.1753 | 0 | 0 | 0
[7 empty] | Total | 1270000.0037 | 0 | 905478.1709 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1270000.01 | 1270000.01 | 1094662.829 | 1094662.829 | 175337.181 | 13.81% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 1270000.01 | 0 | 1094662.829 | 175337.181 | 13.81% | 0 | 0 | 17362 | 17362 | 1.586%
Jan 2025 | 0 | 1270000.01 | 0 | 1094662.829 | 175337.181 | 13.81% | 0 | 0 | 197095.2921 | 214457.2921 | 19.59%
Feb 2025 | 0 | 1270000.01 | 0 | 1094662.829 | 175337.181 | 13.81% | 714197 | 714197 | 535675.7773 | 750133.0694 | 68.53%
Mar 2025 | 0 | 1270000.01 | 0 | 1094662.829 | 175337.181 | 13.81% | 0 | 714197 | 155345.0982 | 905478.1676 | 82.72%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 20142.9514 | 0 | 20142.9514 | 17362
Jan 2025 | 248807.9032 | 0 | 248807.9032 | 214457.2921
Feb 2025 | 870285.3339 | 714197 | 156088.3339 | 134538.6581
Mar 2025 | 1050512.7711 | 714197 | 336315.7711 | 289883.7563
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 714197 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 17362 | 214457.2921 | 134538.6581 | 0
Construction Costs | 0 | 17362 | 197095.2921 | 535675.7773 | 155345.0982 | #VALUE!
Closing WIP | Difference (GP Exc) | 17362 | 214457.2921 | 134538.6581 | 289883.7563 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 615594.4113 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 1.586% | 19.59% | 68.53% | 82.72% | 82.72%

## J-2203
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Balo Built |  |  |  |  | Steel | 541778.3158 | 0 | 440331.7864 | 0
Estimate Code |  | E00014200 |  |  |  |  | Bolts | 25338.3184 | 0 | 16697.6909 | 0
Contract Code |  | J-2203 |  |  |  |  | Purlin | 205434.191 | 0 | 101085.5545 | 0
Contract Name |  | 650 Hume Highway, Craigieburn- The Base Precinct 2 |  |  |  |  | Labour | 237872.7288 | 0 | 92729.92 | 0
Customer |  | Balo Built |  |  |  |  | Processing | 126691.0176 | 0 | 72037.5 | 0
Start Date |  | 22 Oct 2024 |  |  |  |  | Rigging | 360000 | 0 | 55000 | 0
Completion Date |  | 3 Aug 2024 |  |  |  |  | Freight | 11500 | 0 | 4170 | 0
Budgeted Revenue |  | 1930720 |  |  |  |  | Shop Drawings | 28505.6074 | 0 | 0 | 0
Budgeted Job Expenditure |  | 1659875.0654 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 14.03% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 316.729 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 332.6778 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 14.03% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 20177.5939 | 0 | 6773.2091 | 0
[7 empty] | Grates | 95370 | 0 | 89938.5455 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 4040 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 3167.2898 | 0 | 1208.5 | 0
[7 empty] | OH & Profit | 270844.933 | 0 | 0 | 0
[7 empty] | Total | 1930719.9957 | 0 | 879972.7064 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1930720 | 1930720 | 1659875.0654 | 1659875.0654 | 270844.9346 | 14.03% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 1930720 | 0 | 1659875.0654 | 270844.9346 | 14.03% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 1930720 | 0 | 1659875.0654 | 270844.9346 | 14.03% | 0 | 0 | 991.75 | 991.75 | 0.05975%
Dec 2024 | 0 | 1930720 | 0 | 1659875.0654 | 270844.9346 | 14.03% | 0 | 0 | 1559.89 | 2551.64 | 0.1537%
Jan 2025 | 0 | 1930720 | 0 | 1659875.0654 | 270844.9346 | 14.03% | 193072 | 193072 | 2893.5 | 5445.14 | 0.328%
Feb 2025 | 0 | 1930720 | 0 | 1659875.0654 | 270844.9346 | 14.03% | 300000 | 493072 | 747923.1245 | 753368.2645 | 45.39%
Mar 2025 | 0 | 1930720 | 0 | 1659875.0654 | 270844.9346 | 14.03% | 0 | 493072 | 126604.4418 | 879972.7064 | 53.01%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 1153.5757 | 0 | 1153.5757 | 991.75
Dec 2024 | 2967.9959 | 0 | 2967.9959 | 2551.64
Jan 2025 | 6333.6337 | 193072 | -186738.3663 | -160542.3665
Feb 2025 | 876296.7804 | 493072 | 383224.7804 | 329465.307
Mar 2025 | 1023559.507 | 493072 | 530487.507 | 456069.7488
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 193072 | 300000 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | -186738.3663 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 186738.3663 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 991.75 | 2551.64 | -160542.3665 | 329465.307 | 0
Construction Costs | 0 | 0 | 991.75 | 1559.89 | 2893.5 | 747923.1245 | 126604.4418 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 991.75 | 2551.64 | -160542.3665 | 329465.307 | 456069.7488 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 165987.5065 | 257915.451 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.05975% | 0.1537% | 0.328% | 45.39% | 53.01% | 53.01%

## J-2204
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Quadrant Building |  |  |  |  | Steel | 67447.8955 | 0 | 0 | 0
Estimate Code |  | E00013692 |  |  |  |  | Bolts | 4954.3379 | 0 | 2703.5909 | 0
Contract Code |  | J-2204 |  |  |  |  | Purlin | 8763.7556 | 0 | 0 | 0
Contract Name |  | 17 Elmhurst Avenue, Aintree- Woodlea Swim School |  |  |  |  | Labour | 17058.6437 | 0 | 332 | 0
Customer |  | Quadrant Building |  |  |  |  | Processing | 18279.4614 | 0 | 12770 | 0
Start Date | [6 empty] | Rigging | 36047.209 | 0 | 0 | 0
Completion Date |  | 22 Apr 2024 |  |  |  |  | Freight | 1800 | 0 | 55.6545 | 0
Budgeted Revenue |  | 233700.01 |  |  |  |  | Shop Drawings | 4154.2656 | 0 | 4125 | 0
Budgeted Job Expenditure |  | 193279.1158 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.3% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 36.1247 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 32.8444 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.3% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 29458.4207 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 4673.1169 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 642.0077 | 0 | 0 | 0
[7 empty] | OH & Profit | 40420.885 | 0 | 0 | 0
[7 empty] | Total | 233699.9991 | 0 | 19986.2455 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 233700 | 233700 | 193279.1158 | 193279.1158 | 40420.8842 | 17.3% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 233700 | 0 | 193279.1158 | 40420.8842 | 17.3% | 33700 | 33700 | 0 | 0 | 0%
Dec 2024 | 0 | 233700 | 0 | 193279.1158 | 40420.8842 | 17.3% | 0 | 33700 | 542.6545 | 542.6545 | 0.2808%
Jan 2025 | 0 | 233700 | 0 | 193279.1158 | 40420.8842 | 17.3% | 0 | 33700 | 4125 | 4667.6545 | 2.415%
Feb 2025 | 0 | 233700 | 0 | 193279.1158 | 40420.8842 | 17.3% | 0 | 33700 | 2279.7818 | 6947.4364 | 3.595%
Mar 2025 | 0 | 233700 | 0 | 193279.1158 | 40420.8842 | 17.3% | 0 | 33700 | 13038.8091 | 19986.2455 | 10.34%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2024 | 0 | 33700 | -33700 | -27871.2289
Dec 2024 | 656.1411 | 33700 | -33043.8589 | -27328.5744
Jan 2025 | 5643.8113 | 33700 | -28056.1887 | -23203.5744
Feb 2025 | 8400.3689 | 33700 | -25299.6311 | -20923.7926
Mar 2025 | 24166.0127 | 33700 | -9533.9873 | -7884.9835
Job Profitability Summary
| Beginning | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 33700 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | -33700 | -33043.8589 | -28056.1887 | -25299.6311 | -9533.9873 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 33700 | 33043.8589 | 28056.1887 | 25299.6311
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | -27871.2289 | -27328.5744 | -23203.5744 | -20923.7926 | 0
Construction Costs | 0 | 0 | 542.6545 | 4125 | 2279.7818 | 13038.8091 | #VALUE!
Closing WIP | Difference (GP Exc) | -27871.2289 | -27328.5744 | -23203.5744 | -20923.7926 | -7884.9835 | 0
Total Costruction Cost | #VALUE! | 27871.2289 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.2808% | 2.415% | 3.595% | 10.34% | 10.34%

## J-2205
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Genis Steel Victoria |  |  |  |  | Steel | 0 | 0 | 2954 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2205 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Form Work |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Genis Steel Victoria |  |  |  |  | Processing | 0 | 0 | 1125.2909 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 4079.2909 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 2954 | 2954 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2954 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 1125.2909 | 4079.2909 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2954 | 0 | 1125.2909 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2206
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | LSR Construction Group Pty Ltd |  |  |  |  | Steel | 106036.2544 | 0 | 48167.2909 | 0
Estimate Code |  | E00013772 |  |  |  |  | Bolts | 8541.3716 | 0 | 11282.8 | 0
Contract Code |  | J-2206 |  |  |  |  | Purlin | 75441.5519 | 0 | 32942.4818 | 0
Contract Name |  | 9-11 Maria Street, Laverton North |  |  |  |  | Labour | 38363.9146 | 0 | 16288.3 | 0
Customer |  | LSR Construction Group Pty Ltd |  |  |  |  | Processing | 20939.5083 | 0 | 12166.5364 | 0
Start Date |  | 17 Jul 2024 |  |  |  |  | Rigging | 70181.5586 | 2000 | 35000 | 0
Completion Date |  | 7 May 2024 |  |  |  |  | Freight | 3025.9617 | 0 | 2157.6545 | 0
Budgeted Revenue |  | 431999.99 |  |  |  |  | Shop Drawings | 8265.5615 | 0 | 0 | 0
Budgeted Job Expenditure |  | 352119.9496 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 18.49% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 55.1034 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 52.2744 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 18.41% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 9311.17 | 0 | 12240.4909 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 3900 | 0 | 0 | 0
[7 empty] | Other Materials | 6460 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1653.1013 | 0 | 0 | 0
[7 empty] | OH & Profit | 79880.047 | 0 | 0 | 0
[7 empty] | Total | 432000.0009 | 2000 | 170245.5545 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 432000 | 432000 | 352119.9496 | 352119.9496 | 79880.0504 | 18.49% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 432000 | 0 | 352119.9496 | 79880.0504 | 18.49% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 432000 | 0 | 352119.9496 | 79880.0504 | 18.49% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 432000 | 0 | 352119.9496 | 79880.0504 | 18.49% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 432000 | 0 | 352119.9496 | 79880.0504 | 18.49% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 432000 | 0 | 352119.9496 | 79880.0504 | 18.49% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 432000 | 0 | 352119.9496 | 79880.0504 | 18.49% | 0 | 0 | 71666.3318 | 71666.3318 | 20.35%
Jan 2025 | 0 | 432000 | 0 | 352119.9496 | 79880.0504 | 18.49% | 205200 | 205200 | 98080.5227 | 169746.8545 | 48.21%
Feb 2025 | 0 | 432000 | 0 | 352119.9496 | 79880.0504 | 18.49% | 0 | 205200 | 0 | 169746.8545 | 48.21%
Mar 2025 | 2000 | 434000 | 2000 | 354119.9496 | 79880.0504 | 18.41% | 0 | 205200 | 498.7 | 170245.5545 | 48.08%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 87924.1729 | 0 | 87924.1729 | 71666.3318
Jan 2025 | 208254.719 | 205200 | 3054.719 | 2489.8785
Feb 2025 | 208254.719 | 205200 | 3054.719 | 2489.8785
Mar 2025 | 208648.4276 | 205200 | 3448.4276 | 2813.7259
Job Profitability Summary
| Beginning | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205200 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71666.3318 | 2489.8785 | 2489.8785 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 71666.3318 | 98080.5227 | 0 | 498.7 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 71666.3318 | 2489.8785 | 2489.8785 | 2813.7259 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 167256.9761 | 0 | 174.8526 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 20.35% | 48.21% | 48.21% | 48.08% | 48.08%

## J-2209
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Panache Developments |  |  |  |  | Steel | 35182.7591 | 0 | 0 | 0
Estimate Code |  | E00013204 |  |  |  |  | Bolts | 1818.173 | 0 | 0 | 0
Contract Code |  | J-2209 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 39 Maling Road, Canterbury |  |  |  |  | Labour | 14761.108 | 0 | 0 | 0
Customer |  | Panache Developments |  |  |  |  | Processing | 7337.6266 | 0 | 0 | 0
Start Date |  | 9 Feb 2024 |  |  |  |  | Rigging | 25000 | 0 | 0 | 0
Completion Date |  | 12 Dec 2023 |  |  |  |  | Freight | 2000 | 0 | 0 | 0
Budgeted Revenue |  | 126000.01 |  |  |  |  | Shop Drawings | 4999.9756 | 0 | 2560 | 0
Budgeted Job Expenditure |  | 91846.7338 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 27.11% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 14.2856 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 27.11% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 389.95 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 357.1411 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 34153.2667 | 0 | 0 | 0
[7 empty] | Total | 126000 | 0 | 2560 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 126000 | 126000 | 91846.7338 | 91846.7338 | 34153.2662 | 27.11% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 25200 | 25200 | 0 | 0 | 0%
Dec 2024 | 0 | 126000 | 0 | 91846.7338 | 34153.2662 | 27.11% | 0 | 25200 | 2560 | 2560 | 2.787%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 25200 | -25200 | -18369.3468
Dec 2024 | 3511.9376 | 25200 | -21688.0624 | -15809.3468
Job Profitability Summary
| Beginning | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25200 | -21688.0624 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18369.3468 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18369.3468 | -15809.3468 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18369.3468 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.787% | 2.787%

## J-2210
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Number 34 |  |  |  |  | Steel | 27517.5402 | 0 | 0 | 0
Estimate Code |  | E00014446 |  |  |  |  | Bolts | 2258.5027 | 0 | 0 | 0
Contract Code |  | J-2210 |  |  |  |  | Purlin | 8283.727 | 0 | 0 | 0
Contract Name |  | 551, 553A & 553B Geelong Road, Brooklyn |  |  |  |  | Labour | 20949.9387 | 0 | 0 | 0
Customer |  | Number 34 |  |  |  |  | Processing | 6592.3503 | 0 | 0 | 0
Start Date |  | 16 Jan 2025 |  |  |  |  | Rigging | 20000 | 0 | 0 | 0
Completion Date |  | 24 Sep 2024 |  |  |  |  | Freight | 1200 | 0 | 0 | 0
Budgeted Revenue |  | 128400.01 |  |  |  |  | Shop Drawings | 4492.1323 | 0 | 1770 | 0
Budgeted Job Expenditure |  | 106723.3788 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.88% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 15.5483 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.88% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 10007 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 1201.32 | 0 | 0 | 0
[7 empty] | Other Materials | 4220.8666 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 21676.6223 | 0 | 0 | 0
[7 empty] | Total | 128400.0002 | 0 | 1770 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 128400 | 128400 | 106723.3788 | 106723.3788 | 21676.6211 | 16.88% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 128400 | 0 | 106723.3788 | 21676.6211 | 16.88% | 25680 | 25680 | 0 | 0 | 0%
Dec 2024 | 0 | 128400 | 0 | 106723.3788 | 21676.6211 | 16.88% | 0 | 25680 | 1770 | 1770 | 1.658%
Jan 2025 | 0 | 128400 | 0 | 106723.3788 | 21676.6211 | 16.88% | 0 | 25680 | 0 | 1770 | 1.658%
Feb 2025 | 0 | 128400 | 0 | 106723.3788 | 21676.6211 | 16.88% | -25680 | 0 | 0 | 1770 | 1.658%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2024 | 0 | 25680 | -25680 | -21344.6758
Dec 2024 | 2129.5053 | 25680 | -23550.4947 | -19574.6758
Jan 2025 | 2129.5053 | 25680 | -23550.4947 | -19574.6758
Feb 2025 | 2129.5053 | 0 | 2129.5053 | 1770
Job Profitability Summary
| Beginning | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 25680 | 0 | 0 | -25680 | #VALUE!
Less Current Period Overbills | 0 | -25680 | -23550.4947 | -23550.4947 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 25680 | 23550.4947 | 23550.4947
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | -21344.6758 | -19574.6758 | -19574.6758 | 0
Construction Costs | 0 | 0 | 1770 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | -21344.6758 | -19574.6758 | -19574.6758 | 1770 | 0
Total Costruction Cost | #VALUE! | 21344.6758 | 0 | 0 | -21344.6758 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 1.658% | 1.658% | 1.658% | 1.658%

## J-2215
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Nexus Communities |  |  |  |  | Steel | 5500 | 0 | 5406.0964 | 0
Estimate Code |  | E00014733 |  |  |  |  | Bolts | 250 | 0 | 104.4364 | 0
Contract Code |  | J-2215 |  |  |  |  | Purlin | 1600 | 0 | 663.6273 | 0
Contract Name |  | Sommers Nexus |  |  |  |  | Labour | 4200 | 0 | 10108.94 | 0
Customer |  | Nexus Communities |  |  |  |  | Processing | 250 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 21 Nov 2024 |  |  |  |  | Freight | 0 | 0 | 180 | 0
Budgeted Revenue |  | 25050 |  |  |  |  | Shop Drawings | 600 | 0 | 0 | 0
Budgeted Job Expenditure |  | 21450 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 14.37% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 2.1078 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 14.37% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 8450 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 600 | 0 | 0 | 0
[7 empty] | OH & Profit | 3600 | 0 | 0 | 0
[7 empty] | Total | 25050 | 0 | 16463.1 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 25050 | 25050 | 21450 | 21450 | 3600 | 14.37% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 25050 | 0 | 21450 | 3600 | 14.37% | 21830 | 21830 | 1567.5964 | 1567.5964 | 7.308%
Dec 2024 | 0 | 25050 | 0 | 21450 | 3600 | 14.37% | 0 | 21830 | 14537.9536 | 16105.55 | 75.08%
Jan 2025 | 0 | 25050 | 0 | 21450 | 3600 | 14.37% | 0 | 21830 | 357.55 | 16463.1 | 76.75%
Feb 2025 | 0 | 25050 | 0 | 21450 | 3600 | 14.37% | 0 | 21830 | 0 | 16463.1 | 76.75%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2024 | 1830.6895 | 21830 | -19999.3105 | -17125.1581
Dec 2024 | 18808.5794 | 21830 | -3021.4206 | -2587.2045
Jan 2025 | 19226.1378 | 21830 | -2603.8622 | -2229.6545
Feb 2025 | 19226.1378 | 21830 | -2603.8622 | -2229.6545
Job Profitability Summary
| Beginning | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 21830 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | -19999.3105 | -3021.4206 | -2603.8622 | -2603.8622 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 19999.3105 | 3021.4206 | 2603.8622
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | -17125.1581 | -2587.2045 | -2229.6545 | 0
Construction Costs | 0 | 1567.5964 | 14537.9536 | 357.55 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | -17125.1581 | -2587.2045 | -2229.6545 | -2229.6545 | 0
Total Costruction Cost | #VALUE! | 18692.7545 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 7.308% | 75.08% | 76.75% | 76.75% | 76.75%

## J-2216
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 612648.6466 | 0 | 353500.7618 | 0
Estimate Code |  | E00014505 |  |  |  |  | Bolts | 36074.707 | 0 | 33992.8182 | 0
Contract Code |  | J-2216 |  |  |  |  | Purlin | 323580.5163 | 0 | 71647.2636 | 0
Contract Name |  | Lot 2, 100 Missens Road, Cranbourne West |  |  |  |  | Labour | 205332.0846 | 0 | 5085.19 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 133804.2266 | 0 | 84169.3636 | 0
Start Date |  | 29 Jan 2025 |  |  |  |  | Rigging | 367888 | 0 | 43800 | 0
Completion Date |  | 8 Oct 2024 |  |  |  |  | Freight | 15599.9443 | 0 | 7427.07 | 0
Budgeted Revenue |  | 2100000.03 |  |  |  |  | Shop Drawings | 34270.8086 | 0 | 15971 | 0
Budgeted Job Expenditure |  | 1838527.9503 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 12.45% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 359.0108 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 335.9807 |  |  |  |  | Stairs | 14999.985 | 0 | 0 | 0
Current GP% |  | 12.45% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 57516.2203 | 0 | 688.5 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 9599.9984 | 0 | 0 | 0
[7 empty] | Other Materials | 8630 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1803.67 | 0 | 1641.5 | 0
[7 empty] | OH & Profit | 278251.188 | 0 | 0 | 0
[7 empty] | Total | 2099999.9958 | 0 | 617923.4673 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 2100000.01 | 2100000.01 | 1838527.9503 | 1838527.9503 | 261472.0597 | 12.45% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 2100000.01 | 0 | 1838527.9503 | 261472.0597 | 12.45% | 0 | 0 | 7161.7091 | 7161.7091 | 0.3895%
Jan 2025 | 0 | 2100000.01 | 0 | 1838527.9503 | 261472.0597 | 12.45% | 0 | 0 | 64483.0791 | 71644.7882 | 3.897%
Feb 2025 | 0 | 2100000.01 | 0 | 1838527.9503 | 261472.0597 | 12.45% | 337600 | 337600 | 468805.7564 | 540450.5445 | 29.4%
Mar 2025 | 0 | 2100000.01 | 0 | 1838527.9503 | 261472.0597 | 12.45% | 0 | 337600 | 77472.9227 | 617923.4673 | 33.61%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 8180.2342 | 0 | 8180.2342 | 7161.7091
Jan 2025 | 81833.978 | 0 | 81833.978 | 71644.7882
Feb 2025 | 617312.4258 | 337600 | 279712.4258 | 244885.2907
Mar 2025 | 705803.405 | 337600 | 368203.405 | 322358.2134
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 337600 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 7161.7091 | 71644.7882 | 244885.2907 | 0
Construction Costs | 0 | 7161.7091 | 64483.0791 | 468805.7564 | 77472.9227 | #VALUE!
Closing WIP | Difference (GP Exc) | 7161.7091 | 71644.7882 | 244885.2907 | 322358.2134 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 295565.2538 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0.3895% | 3.897% | 29.4% | 33.61% | 33.61%

## J-2217
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Rockford Building Group |  |  |  |  | Steel | 11218.6925 | 0 | 2162.9273 | 0
Estimate Code |  | E00014315 |  |  |  |  | Bolts | 564.396 | 0 | 122.5091 | 0
Contract Code |  | J-2217 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 85 New Street Brighton |  |  |  |  | Labour | 4053.2372 | 0 | 4290.12 | 0
Customer |  | Rockford Building Group |  |  |  |  | Processing | 1834.287 | 0 | 2213.75 | 0
Start Date |  | 1 Nov 2024 |  |  |  |  | Rigging | 6000 | 0 | 2360 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 600 | 0 | 172.4 | 0
Budgeted Revenue |  | 34000.01 |  |  |  |  | Shop Drawings | 1552.089 | 0 | 1552 | 0
Budgeted Job Expenditure |  | 26375.5657 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 22.42% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 4.4345 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 22.42% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 442 | 0 | 351.9 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 110.8635 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 7624.4355 | 0 | 0 | 0
[7 empty] | Total | 34000.0007 | 0 | 13225.6064 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 34000 | 34000 | 26375.5657 | 26375.5657 | 7624.4343 | 22.42% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 34000 | 0 | 26375.5657 | 7624.4343 | 22.42% | 0 | 0 | 103.4 | 103.4 | 0.392%
Dec 2024 | 0 | 34000 | 0 | 26375.5657 | 7624.4343 | 22.42% | 0 | 0 | 2419.75 | 2523.15 | 9.566%
Jan 2025 | 0 | 34000 | 0 | 26375.5657 | 7624.4343 | 22.42% | 0 | 0 | 7901.9564 | 10425.1064 | 39.53%
Feb 2025 | 0 | 34000 | 0 | 26375.5657 | 7624.4343 | 22.42% | 0 | 0 | 0 | 10425.1064 | 39.53%
Mar 2025 | 0 | 34000 | 0 | 26375.5657 | 7624.4343 | 22.42% | 0 | 0 | 2800.5 | 13225.6064 | 50.14%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2024 | 133.29 | 0 | 133.29 | 103.4
Dec 2024 | 3252.5217 | 0 | 3252.5217 | 2523.15
Jan 2025 | 13438.7114 | 0 | 13438.7114 | 10425.1064
Feb 2025 | 13438.7114 | 0 | 13438.7114 | 10425.1064
Mar 2025 | 17048.7572 | 0 | 17048.7572 | 13225.6064
Job Profitability Summary
| Beginning | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 103.4 | 2523.15 | 10425.1064 | 10425.1064 | 0
Construction Costs | 0 | 103.4 | 2419.75 | 7901.9564 | 0 | 2800.5 | #VALUE!
Closing WIP | Difference (GP Exc) | 103.4 | 2523.15 | 10425.1064 | 10425.1064 | 13225.6064 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0.392% | 9.566% | 39.53% | 39.53% | 50.14% | 50.14%

## J-2218
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Kiel & Co |  |  |  |  | Steel | 76497.9979 | 0 | 61275.5645 | 0
Estimate Code |  | E00014408 |  |  |  |  | Bolts | 5041.2095 | 0 | 242.1455 | 0
Contract Code |  | J-2218 |  |  |  |  | Purlin | 53492.5009 | 0 | 24037.3455 | 0
Contract Name |  | Lot 507-509, 9-13 Supertubes Drive, Torquay |  |  |  |  | Labour | 31784.84 | 0 | 7207.12 | 0
Customer |  | Kiel & Co |  |  |  |  | Processing | 15687.6543 | 0 | 12966.25 | 0
Start Date |  | 15 Jan 2025 |  |  |  |  | Rigging | 94417.625 | 0 | 0 | 0
Completion Date |  | 16 Sep 2024 |  |  |  |  | Freight | 4151.3063 | 0 | 620.2 | 0
Budgeted Revenue |  | 346999.99 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 282905.7075 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 18.47% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 38.7785 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 36.0235 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 18.47% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 1984.0273 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1169.4633 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 663.1129 | 0 | 0 | 0
[7 empty] | OH & Profit | 64094.2903 | 0 | 0 | 0
[7 empty] | Total | 347000.0004 | 0 | 108332.6527 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 347000 | 347000 | 282905.7075 | 282905.7075 | 64094.2925 | 18.47% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 347000 | 0 | 282905.7075 | 64094.2925 | 18.47% | 0 | 0 | 260.2 | 260.2 | 0.09197%
Jan 2025 | 0 | 347000 | 0 | 282905.7075 | 64094.2925 | 18.47% | 0 | 0 | 30437.4 | 30697.6 | 10.85%
Feb 2025 | 0 | 347000 | 0 | 282905.7075 | 64094.2925 | 18.47% | 0 | 0 | 20165.1418 | 50862.7418 | 17.98%
Mar 2025 | 0 | 347000 | 0 | 282905.7075 | 64094.2925 | 18.47% | 0 | 0 | 57469.9159 | 108332.6577 | 38.29%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 319.1502 | 0 | 319.1502 | 260.2
Jan 2025 | 37652.3588 | 0 | 37652.3588 | 30697.6
Feb 2025 | 62386.0563 | 0 | 62386.0563 | 50862.7418
Mar 2025 | 132876.1889 | 0 | 132876.1889 | 108332.6577
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 260.2 | 30697.6 | 50862.7418 | 0
Construction Costs | 0 | 260.2 | 30437.4 | 20165.1418 | 57469.9159 | #VALUE!
Closing WIP | Difference (GP Exc) | 260.2 | 30697.6 | 50862.7418 | 108332.6577 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0.09197% | 10.85% | 17.98% | 38.29% | 38.29%

## J-2219
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Pristine Building Services Pty Ltd |  |  |  |  | Steel | 7493.6851 | 0 | 6461.3727 | 0
Estimate Code |  | E00014551 |  |  |  |  | Bolts | 232.5064 | 0 | 219.2455 | 0
Contract Code |  | J-2219 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 2 Joseph Street, Bundoora |  |  |  |  | Labour | 3412.4979 | 0 | 3734.69 | 0
Customer |  | Pristine Building Services Pty Ltd |  |  |  |  | Processing | 1328.608 | 0 | 1035 | 0
Start Date |  | 29 Jan 2025 |  |  |  |  | Rigging | 5000 | 0 | 4837 | 0
Completion Date |  | 16 Oct 2024 |  |  |  |  | Freight | 400 | 0 | 635 | 0
Budgeted Revenue |  | 24000.01 |  |  |  |  | Shop Drawings | 1278.7852 | 0 | 1278 | 0
Budgeted Job Expenditure |  | 19237.4243 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 19.84% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 3.6537 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.014413 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 19.84% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 91.3418 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 4762.5754 | 0 | 0 | 0
[7 empty] | Total | 23999.9997 | 0 | 18200.3082 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 24000 | 24000 | 19237.4243 | 19237.4243 | 4762.5757 | 19.84% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 24000 | 0 | 19237.4243 | 4762.5757 | 19.84% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 24000 | 0 | 19237.4243 | 4762.5757 | 19.84% | 4800 | 4800 | 1800.75 | 1800.75 | 9.361%
Jan 2025 | 0 | 24000 | 0 | 19237.4243 | 4762.5757 | 19.84% | 0 | 4800 | 15764.5582 | 17565.3082 | 91.31%
Feb 2025 | 0 | 24000 | 0 | 19237.4243 | 4762.5757 | 19.84% | 0 | 4800 | 635 | 18200.3082 | 94.61%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 2246.5586 | 4800 | -2553.4414 | -2046.7349
Jan 2025 | 21913.921 | 4800 | 17113.921 | 13717.8233
Feb 2025 | 22706.1269 | 4800 | 17906.1269 | 14352.8233
Job Profitability Summary
| Beginning | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 4800 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | -2553.4414 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 2553.4414 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | -2046.7349 | 13717.8233 | 0
Construction Costs | 0 | 0 | 1800.75 | 15764.5582 | 635 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | -2046.7349 | 13717.8233 | 14352.8233 | 0
Total Costruction Cost | #VALUE! | 0 | 3847.4849 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 9.361% | 91.31% | 94.61% | 94.61%

## J-2220
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Asta Developments (Aust) P/L |  |  |  |  | Steel | 27340.6527 | 0 | 0 | 0
Estimate Code |  | E00014750 |  |  |  |  | Bolts | 1450.2776 | 0 | 0 | 0
Contract Code |  | J-2220 |  |  |  |  | Purlin | 12571.5036 | 0 | 0 | 0
Contract Name |  | Lot 9, 19 Stanley Drive, Somerton |  |  |  |  | Labour | 7648.2251 | 0 | 40 | 0
Customer |  | Asta Developments (Aust) P/L |  |  |  |  | Processing | 4128.2301 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 28500.0664 | 0 | 0 | 0
Completion Date |  | 25 Nov 2024 |  |  |  |  | Freight | 400 | 0 | 0 | 0
Budgeted Revenue |  | 102000.02 |  |  |  |  | Shop Drawings | 1396.5704 | 0 | 0 | 0
Budgeted Job Expenditure |  | 84263.3396 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.39% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 8.9051 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.39% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 222.6263 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 605.1874 | 0 | 0 | 0
[7 empty] | OH & Profit | 17736.6618 | 0 | 0 | 0
[7 empty] | Total | 102000.0014 | 0 | 40 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 102000 | 102000 | 84263.3396 | 84263.3396 | 17736.6604 | 17.39% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 102000 | 0 | 84263.3396 | 17736.6604 | 17.39% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 102000 | 0 | 84263.3396 | 17736.6604 | 17.39% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 102000 | 0 | 84263.3396 | 17736.6604 | 17.39% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 102000 | 0 | 84263.3396 | 17736.6604 | 17.39% | 0 | 0 | 40 | 40 | 0.04747%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 48.4196 | 0 | 48.4196 | 40
Job Profitability Summary
| Beginning | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 40 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 40 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0.04747% | 0.04747%

## J-2221
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arkit |  |  |  |  | Steel | 15785.2958 | 0 | 13497.6918 | 0
Estimate Code |  | E00014758.1 |  |  |  |  | Bolts | 916.7577 | 0 | 701.4545 | 0
Contract Code |  | J-2221 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 66 Walter St Seddon |  |  |  |  | Labour | 10110.9419 | 0 | 10667.5427 | 0
Customer |  | Arkit |  |  |  |  | Processing | 5140.3916 | 0 | 4858.75 | 0
Start Date | [6 empty] | Rigging | 5500 | 0 | 4745 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 800 | 0 | 2992.5 | 0
Budgeted Revenue |  | 52000.01 |  |  |  |  | Shop Drawings | 3500 | 0 | 3500 | 0
Budgeted Job Expenditure |  | 41933.4634 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 19.36% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 7.2031 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 6.554 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 19.36% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 180.0774 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 10066.5359 | 0 | 0 | 0
[7 empty] | Total | 52000.0004 | 0 | 40962.9391 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 52000 | 52000 | 41933.4634 | 41933.4634 | 10066.5366 | 19.36% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 52000 | 0 | 41933.4634 | 10066.5366 | 19.36% | 0 | 0 | 3500 | 3500 | 8.347%
Dec 2024 | 0 | 52000 | 0 | 41933.4634 | 10066.5366 | 19.36% | 0 | 0 | 24126.9191 | 27626.9191 | 65.88%
Jan 2025 | 0 | 52000 | 0 | 41933.4634 | 10066.5366 | 19.36% | 34600 | 34600 | 8357.86 | 35984.7791 | 85.81%
Feb 2025 | 0 | 52000 | 0 | 41933.4634 | 10066.5366 | 19.36% | 17400 | 52000 | 4978.16 | 40962.9391 | 97.69%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Nov 2024 | 4340.2091 | 0 | 4340.2091 | 3500
Dec 2024 | 34259.0303 | 0 | 34259.0303 | 27626.9191
Jan 2025 | 44623.2761 | 34600 | 10023.2761 | 8082.8977
Feb 2025 | 50796.4919 | 52000 | -1203.5081 | -970.5243
Job Profitability Summary
| Beginning | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 34600 | 17400 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | -1203.5081 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 3500 | 27626.9191 | 8082.8977 | 0
Construction Costs | 0 | 3500 | 24126.9191 | 8357.86 | 4978.16 | #VALUE!
Closing WIP | Difference (GP Exc) | 3500 | 27626.9191 | 8082.8977 | -970.5243 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 27901.8814 | 14031.582 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 8.347% | 65.88% | 85.81% | 97.69% | 97.69%

## J-2222
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Leone Constructions Pty Ltd |  |  |  |  | Steel | 5377.1871 | 0 | 0 | 0
Estimate Code |  | E00014199 |  |  |  |  | Bolts | 207.1003 | 0 | 0 | 0
Contract Code |  | J-2222 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 8 Miller Street, Brighton |  |  |  |  | Labour | 1495.5479 | 0 | 1272.5 | 0
Customer |  | Leone Constructions Pty Ltd |  |  |  |  | Processing | 2898.5194 | 0 | 1811.7227 | 0
Start Date |  | 21 Oct 2024 |  |  |  |  | Rigging | 4000 | 0 | 0 | 0
Completion Date |  | 2 Aug 2024 |  |  |  |  | Freight | 600 | 0 | 0 | 0
Budgeted Revenue |  | 20850.01 |  |  |  |  | Shop Drawings | 569.5259 | 0 | 569 | 0
Budgeted Job Expenditure |  | 16571.6951 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.52% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 1.6272 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.44683 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 20.52% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1383.1343 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 40.6804 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 4278.3053 | 0 | 0 | 0
[7 empty] | Total | 20850.0006 | 0 | 3653.2227 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 20850 | 20850 | 16571.6951 | 16571.6951 | 4278.3049 | 20.52% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 20850 | 0 | 16571.6951 | 4278.3049 | 20.52% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 20850 | 0 | 16571.6951 | 4278.3049 | 20.52% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 20850 | 0 | 16571.6951 | 4278.3049 | 20.52% | 0 | 0 | 240 | 240 | 1.448%
Jan 2025 | 0 | 20850 | 0 | 16571.6951 | 4278.3049 | 20.52% | 0 | 0 | 1287.4727 | 1527.4727 | 9.217%
Feb 2025 | 0 | 20850 | 0 | 16571.6951 | 4278.3049 | 20.52% | 0 | 0 | 329 | 1856.4727 | 11.2%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 301.9607 | 0 | 301.9607 | 240
Jan 2025 | 1921.8195 | 0 | 1921.8195 | 1527.4727
Feb 2025 | 2335.7572 | 0 | 2335.7572 | 1856.4727
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 240 | 1527.4727 | 0
Construction Costs | 0 | 0 | 0 | 240 | 1287.4727 | 329 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 240 | 1527.4727 | 1856.4727 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 1.448% | 9.217% | 11.2% | 11.2%

## J-2224
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Gravcon |  |  |  |  | Steel | 34292.0804 | 0 | 36422.8455 | 0
Estimate Code |  | E00014643 |  |  |  |  | Bolts | 2500.2859 | 0 | 2753.0818 | 0
Contract Code |  | J-2224 |  |  |  |  | Purlin | 20594.9945 | 0 | 20211.5636 | 0
Contract Name |  | 61 Slater Parade, Keior East |  |  |  |  | Labour | 13697.4182 | 0 | 12554.5 | 0
Customer |  | Gravcon |  |  |  |  | Processing | 7693.8915 | 0 | 12045 | 0
Start Date |  | 20 Feb 2025 |  |  |  |  | Rigging | 32747.875 | 0 | 17040 | 0
Completion Date |  | 6 Nov 2024 |  |  |  |  | Freight | 1500 | 0 | 1732.5 | 0
Budgeted Revenue |  | 160399.99 |  |  |  |  | Shop Drawings | 2500.3628 | 0 | 2600 | 0
Budgeted Job Expenditure |  | 132631.6218 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.31% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 19.233 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 21.5555 |  |  |  |  | Stairs | 14100 | 0 | 0 | 0
Current GP% |  | 17.31% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 669.24 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1720 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 615.4742 | 0 | 0 | 0
[7 empty] | OH & Profit | 27768.3766 | 0 | 0 | 0
[7 empty] | Total | 160399.999 | 0 | 105359.4909 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 160400 | 160400 | 132631.6218 | 132631.6218 | 27768.3782 | 17.31% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 160400 | 0 | 132631.6218 | 27768.3782 | 17.31% | 0 | 0 | 96 | 96 | 0.07238%
Jan 2025 | 0 | 160400 | 0 | 132631.6218 | 27768.3782 | 17.31% | 0 | 0 | 35457.4545 | 35553.4545 | 26.81%
Feb 2025 | 0 | 160400 | 0 | 132631.6218 | 27768.3782 | 17.31% | 86200 | 86200 | 48215.9336 | 83769.3882 | 63.16%
Mar 2025 | 0 | 160400 | 0 | 132631.6218 | 27768.3782 | 17.31% | 0 | 86200 | 21590.0977 | 105359.4859 | 79.44%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 116.099 | 0 | 116.099 | 96
Jan 2025 | 42997.0925 | 0 | 42997.0925 | 35553.4545
Feb 2025 | 101307.74 | 86200 | 15107.74 | 12492.2947
Mar 2025 | 127418.0418 | 86200 | 41218.0418 | 34082.3924
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 86200 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 96 | 35553.4545 | 12492.2947 | 0
Construction Costs | 0 | 96 | 35457.4545 | 48215.9336 | 21590.0977 | #VALUE!
Closing WIP | Difference (GP Exc) | 96 | 35553.4545 | 12492.2947 | 34082.3924 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 71277.0935 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0.07238% | 26.81% | 63.16% | 79.44% | 79.44%

## J-2227
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Davies Henderson Pty Ltd |  |  |  |  | Steel | 8464.4838 | 0 | 5185.8636 | 0
Estimate Code |  | E00014677 |  |  |  |  | Bolts | 456.239 | 0 | 125.5545 | 0
Contract Code |  | J-2227 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 29-31 St Georges Road Toorak |  |  |  |  | Labour | 2998.0781 | 0 | 2685.1345 | 0
Customer |  | Davies Henderson Pty Ltd |  |  |  |  | Processing | 2441.2503 | 0 | 4054.35 | 0
Start Date |  | 1 Feb 2025 |  |  |  |  | Rigging | 2500 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 700 | 0 | 112.5 | 0
Budgeted Revenue |  | 29000.01 |  |  |  |  | Shop Drawings | 1254.6572 | 0 | 1640 | 0
Budgeted Job Expenditure |  | 22163.1761 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 23.58% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 3.5847 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 2.6144 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 23.58% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 3258.85 | 0 | 1215.9727 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 89.6184 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 6836.8229 | 0 | 0 | 0
[7 empty] | Total | 28999.9998 | 0 | 15019.3755 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 29000 | 29000 | 22163.1761 | 22163.1761 | 6836.8239 | 23.58% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 29000 | 0 | 22163.1761 | 6836.8239 | 23.58% | 0 | 0 | 640 | 640 | 2.888%
Jan 2025 | 0 | 29000 | 0 | 22163.1761 | 6836.8239 | 23.58% | 0 | 0 | 172.5 | 812.5 | 3.666%
Feb 2025 | 0 | 29000 | 0 | 22163.1761 | 6836.8239 | 23.58% | 0 | 0 | 3434.58 | 4247.08 | 19.16%
Mar 2025 | 0 | 29000 | 0 | 22163.1761 | 6836.8239 | 23.58% | 0 | 0 | 10772.2955 | 15019.3755 | 67.77%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 837.4251 | 0 | 837.4251 | 640
Jan 2025 | 1063.1373 | 0 | 1063.1373 | 812.5
Feb 2025 | 5557.2053 | 0 | 5557.2053 | 4247.08
Mar 2025 | 19652.5032 | 0 | 19652.5032 | 15019.3755
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 640 | 812.5 | 4247.08 | 0
Construction Costs | 0 | 640 | 172.5 | 3434.58 | 10772.2955 | #VALUE!
Closing WIP | Difference (GP Exc) | 640 | 812.5 | 4247.08 | 15019.3755 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 2.888% | 3.666% | 19.16% | 67.77% | 67.77%

## J-2228
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Genis Steel |  |  |  |  | Steel | 0 | 0 | 701.9545 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2228 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Factory 19, 365-455 Melbourne Rd, Norlane |  |  |  |  | Labour | 0 | 0 | 15701.65 | 0
Customer |  | Genis Steel |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 4150 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 135 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 74728.42 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 95417.0245 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 72982.1155 | 72982.1155 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 7591.6282 | 80573.7436 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 14710.6809 | 95284.4245 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 132.6 | 95417.0245 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72982.1155 | 7591.6282 | 14710.6809 | 132.6 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2229
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Ducon Building Solutions |  |  |  |  | Steel | 75632.9915 | 0 | 64284.1027 | 0
Estimate Code |  | E00014178 |  |  |  |  | Bolts | 4257.7202 | 0 | 3605.9909 | 0
Contract Code |  | J-2229 |  |  |  |  | Purlin | 17576.0043 | 0 | 0 | 0
Contract Name |  | Eramosa Road E, Somerville- Somerville PS Cola |  |  |  |  | Labour | 19880.1013 | 0 | 1802.41 | 0
Customer |  | Ducon Building Solutions |  |  |  |  | Processing | 15366.0737 | 0 | 4062.5 | 0
Start Date |  | 16 Oct 2024 |  |  |  |  | Rigging | 51312.7461 | 0 | 162.5 | 0
Completion Date |  | 26 Jul 2024 |  |  |  |  | Freight | 2400 | 0 | 922.5 | 0
Budgeted Revenue |  | 280000 |  |  |  |  | Shop Drawings | 4683.5776 | 0 | 4500 | 0
Budgeted Job Expenditure |  | 232154.8872 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.09% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 42.5772 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 39.885 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.09% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 38319.8984 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2300 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 425.772 | 0 | 879 | 0
[7 empty] | OH & Profit | 47845.1104 | 0 | 0 | 0
[7 empty] | Total | 279999.9956 | 0 | 80219.0036 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 280000 | 280000 | 232154.8872 | 232154.8872 | 47845.1128 | 17.09% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 280000 | 0 | 232154.8872 | 47845.1128 | 17.09% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 280000 | 0 | 232154.8872 | 47845.1128 | 17.09% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 280000 | 0 | 232154.8872 | 47845.1128 | 17.09% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 280000 | 0 | 232154.8872 | 47845.1128 | 17.09% | 0 | 0 | 18872.8 | 18872.8 | 8.129%
Feb 2025 | 0 | 280000 | 0 | 232154.8872 | 47845.1128 | 17.09% | 0 | 0 | 60467.2036 | 79340.0036 | 34.18%
Mar 2025 | 0 | 280000 | 0 | 232154.8872 | 47845.1128 | 17.09% | 0 | 0 | 879 | 80219.0036 | 34.55%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 22762.3207 | 0 | 22762.3207 | 18872.8
Feb 2025 | 95691.2916 | 0 | 95691.2916 | 79340.0036
Mar 2025 | 96751.4459 | 0 | 96751.4459 | 80219.0036
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 18872.8 | 79340.0036 | 0
Construction Costs | 0 | 0 | 0 | 0 | 18872.8 | 60467.2036 | 879 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 18872.8 | 79340.0036 | 80219.0036 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 8.129% | 34.18% | 34.55% | 34.55%

## J-2230
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Ducon Building Solutions |  |  |  |  | Steel | 61770.0643 | 0 | 44790.5718 | 0
Estimate Code |  | E00014163 |  |  |  |  | Bolts | 3477.3701 | 0 | 3162.7909 | 0
Contract Code |  | J-2230 |  |  |  |  | Purlin | 10110.0032 | 0 | 10312.4455 | 0
Contract Name |  | Somers & Somerville Primary School Cola |  |  |  |  | Labour | 13585.9457 | 0 | 4234.4 | 0
Customer |  | Ducon Building Solutions |  |  |  |  | Processing | 12550.1416 | 0 | 26827.5 | 0
Start Date |  | 16 Oct 2024 |  |  |  |  | Rigging | 44635.4414 | 0 | 0 | 0
Completion Date |  | 26 Jul 2024 |  |  |  |  | Freight | 2400 | 0 | 2986.0545 | 0
Budgeted Revenue |  | 224999.99 |  |  |  |  | Shop Drawings | 3825.0029 | 0 | 3721 | 0
Budgeted Job Expenditure |  | 186097.6065 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.29% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 34.7737 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 32.1859 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.29% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 31295.9004 | 0 | 25537.9 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2100 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 347.737 | 0 | 0 | 0
[7 empty] | OH & Profit | 38902.3921 | 0 | 0 | 0
[7 empty] | Total | 224999.9987 | 0 | 121572.6627 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 225000 | 225000 | 186097.6065 | 186097.6065 | 38902.3935 | 17.29% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 225000 | 0 | 186097.6065 | 38902.3935 | 17.29% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 225000 | 0 | 186097.6065 | 38902.3935 | 17.29% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 225000 | 0 | 186097.6065 | 38902.3935 | 17.29% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 225000 | 0 | 186097.6065 | 38902.3935 | 17.29% | 0 | 0 | 9400.7545 | 9400.7545 | 5.052%
Feb 2025 | 0 | 225000 | 0 | 186097.6065 | 38902.3935 | 17.29% | 0 | 0 | 110436.9082 | 119837.6627 | 64.4%
Mar 2025 | 0 | 225000 | 0 | 186097.6065 | 38902.3935 | 17.29% | 0 | 0 | 1735 | 121572.6627 | 65.33%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 11365.9161 | 0 | 11365.9161 | 9400.7545
Feb 2025 | 144888.8818 | 0 | 144888.8818 | 119837.6627
Mar 2025 | 146986.5713 | 0 | 146986.5713 | 121572.6627
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 9400.7545 | 119837.6627 | 0
Construction Costs | 0 | 0 | 0 | 0 | 9400.7545 | 110436.9082 | 1735 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 9400.7545 | 119837.6627 | 121572.6627 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 5.052% | 64.4% | 65.33% | 65.33%

## J-2232
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | PreBuilt |  |  |  |  | Steel | 98500 | 0 | 76690.2455 | 0
Estimate Code |  | E00014839 |  |  |  |  | Bolts | 2000 | 0 | 1626.4727 | 0
Contract Code |  | J-2232 |  |  |  |  | Purlin | 2900 | 0 | 27911.6636 | 0
Contract Name |  | Point Cook SL 1.1 |  |  |  |  | Labour | 148200 | 0 | 97858.54 | 0
Customer |  | PreBuilt |  |  |  |  | Processing | 10000 | 0 | 5920 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 11 Dec 2024 |  |  |  |  | Freight | 15000 | 0 | 17058.75 | 0
Budgeted Revenue |  | 341400 |  |  |  |  | Shop Drawings | 7800 | 0 | 0 | 0
Budgeted Job Expenditure |  | 286400 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.11% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 36.6336 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 33.49% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2000 | 0 | 0 | 0
[7 empty] | OH & Profit | 55000 | 0 | 0 | 59334.33
[7 empty] | Total | 341400 | 0 | 227065.6718 | 59334.33
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 341400 | 341400 | 286400 | 286400 | 55000 | 16.11% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 341400 | 0 | 286400 | 55000 | 16.11% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 341400 | 0 | 286400 | 55000 | 16.11% | 197400 | 197400 | 187439.8018 | 187439.8018 | 65.45%
Feb 2025 | 0 | 341400 | -59334.33 | 227065.67 | 114334.33 | 33.49% | 170100 | 367500 | 39625.87 | 227065.6718 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 223435.5738 | 197400 | 26035.5738 | 21841.2078
Feb 2025 | 341400.0027 | 367500 | -26099.9973 | -17359.1487
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 197400 | 170100 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | -26099.9973 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 21841.2078 | 0
Construction Costs | 0 | 0 | 187439.8018 | 39625.87 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 21841.2078 | -17359.1487 | 0
Total Costruction Cost | #VALUE! | 0 | 165598.594 | 78826.2265 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 65.45% | 100% | 100%

## J-2235
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | PreBuilt |  |  |  |  | Steel | 98500 | 0 | 82410.6845 | 0
Estimate Code |  | E00014842 |  |  |  |  | Bolts | 2000 | 0 | 1618.9091 | 0
Contract Code |  | J-2235 |  |  |  |  | Purlin | 2900 | 0 | 24783.6273 | 0
Contract Name |  | Point Cook SL 2.2 |  |  |  |  | Labour | 148200 | 0 | 67197 | 0
Customer |  | PreBuilt |  |  |  |  | Processing | 10000 | 0 | 7717.5 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 11 Dec 2024 |  |  |  |  | Freight | 15000 | 0 | 11078.75 | 0
Budgeted Revenue |  | 341400 |  |  |  |  | Shop Drawings | 7800 | 0 | 0 | 0
Budgeted Job Expenditure |  | 286400 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.11% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 35.1223 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 39.6926 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 42.46% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 929.6 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2000 | 0 | 690 | 0
[7 empty] | OH & Profit | 55000 | 0 | 0 | 89973.93
[7 empty] | Total | 341400 | 0 | 196426.0709 | 89973.93
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 341400 | 341400 | 286400 | 286400 | 55000 | 16.11% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 341400 | 0 | 286400 | 55000 | 16.11% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 341400 | 0 | 286400 | 55000 | 16.11% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 341400 | -89973.93 | 196426.07 | 144973.93 | 42.46% | 368930 | 368930 | 194158.2477 | 194158.2477 | 98.85%
Mar 2025 | 0 | 341400 | 0 | 196426.07 | 144973.93 | 42.46% | 0 | 368930 | 2267.8182 | 196426.0659 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 337458.3922 | 368930 | -31471.6078 | -18107.3352
Mar 2025 | 341399.9929 | 368930 | -27530.0071 | -15839.517
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 368930 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | -31471.6078 | -27530.0071 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 31471.6078
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | -18107.3352 | 0
Construction Costs | 0 | 0 | 0 | 194158.2477 | 2267.8182 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | -18107.3352 | -15839.517 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 212265.5829 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 98.85% | 100% | 100%

## J-2236
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arkit |  |  |  |  | Steel | 29000 | 0 | 13252.6909 | 0
Estimate Code |  | E00014844 |  |  |  |  | Bolts | 500 | 0 | 365.8455 | 0
Contract Code |  | J-2236 |  |  |  |  | Purlin | 5000 | 0 | 4679.2182 | 0
Contract Name |  | Neometro Display Suit |  |  |  |  | Labour | 25000 | 0 | 30061.65 | 0
Customer |  | Arkit |  |  |  |  | Processing | 1000 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 12 Dec 2024 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 75100 |  |  |  |  | Shop Drawings | 2600 | 0 | 0 | 0
Budgeted Job Expenditure |  | 64100 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 14.65% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 14.65% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1000 | 0 | 0 | 0
[7 empty] | OH & Profit | 11000 | 0 | 0 | 0
[7 empty] | Total | 75100 | 0 | 48359.4045 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 75100 | 75100 | 64100 | 64100 | 11000 | 14.65% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 75100 | 0 | 64100 | 11000 | 14.65% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 75100 | 0 | 64100 | 11000 | 14.65% | 0 | 0 | 28384.5045 | 28384.5045 | 44.28%
Feb 2025 | 0 | 75100 | 0 | 64100 | 11000 | 14.65% | 71000 | 71000 | 19974.9 | 48359.4045 | 75.44%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 33255.4804 | 0 | 33255.4804 | 28384.5045
Feb 2025 | 56658.2103 | 71000 | -14341.7897 | -12241.1281
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 71000 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | -14341.7897 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 28384.5045 | 0
Construction Costs | 0 | 0 | 28384.5045 | 19974.9 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 28384.5045 | -12241.1281 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 60600.5326 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 44.28% | 75.44% | 75.44%

## J-2237
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Remington |  |  |  |  | Steel | 0 | 0 | 14602.4455 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2237 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Storage Racks |  |  |  |  | Labour | 0 | 0 | 528.02 | 0
Customer |  | Remington |  |  |  |  | Processing | 0 | 0 | 3477.5 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 2.1285 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 18607.9655 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 15427 | 15427 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 3180.9655 | 18607.9655 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 15427 | 3180.9655 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2238
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 946 | 0 | 893.2909 | 0
Estimate Code |  | E00014823 |  |  |  |  | Bolts | 0 | 0 | 150.6182 | 0
Contract Code |  | J-2238 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 20 Wright Road, Keilor Park |  |  |  |  | Labour | 2592.5 | 0 | 1800.15 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 687.5 | 0 | 1020 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 9 Dec 2024 |  |  |  |  | Freight | 400 | 0 | 0 | 0
Budgeted Revenue |  | 6100 |  |  |  |  | Shop Drawings | 165 | 0 | 0 | 0
Budgeted Job Expenditure |  | 4821 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.97% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.66491 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 20.97% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 30 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 1279 | 0 | 0 | 0
[7 empty] | Total | 6100 | 0 | 3864.0591 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 6100 | 6100 | 4821 | 4821 | 1279 | 20.97% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 6100 | 0 | 4821 | 1279 | 20.97% | 0 | 0 | 230 | 230 | 4.771%
Jan 2025 | 0 | 6100 | 0 | 4821 | 1279 | 20.97% | 0 | 0 | 2785.3027 | 3015.3027 | 62.55%
Feb 2025 | 0 | 6100 | 0 | 4821 | 1279 | 20.97% | 6100 | 6100 | 524.12 | 3539.4227 | 73.42%
Mar 2025 | 0 | 6100 | 0 | 4821 | 1279 | 20.97% | 0 | 6100 | 324.6364 | 3864.0591 | 80.15%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 291.0185 | 0 | 291.0185 | 230
Jan 2025 | 3815.2555 | 0 | 3815.2555 | 3015.3027
Feb 2025 | 4478.4233 | 6100 | -1621.5767 | -1281.5773
Mar 2025 | 4889.1849 | 6100 | -1210.8151 | -956.9409
Job Profitability Summary
| Beginning | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 6100 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | -1621.5767 | -1210.8151 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 1621.5767
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 230 | 3015.3027 | -1281.5773 | 0
Construction Costs | 0 | 230 | 2785.3027 | 524.12 | 324.6364 | #VALUE!
Closing WIP | Difference (GP Exc) | 230 | 3015.3027 | -1281.5773 | -956.9409 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 4821 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 4.771% | 62.55% | 73.42% | 80.15% | 80.15%

## J-2239
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 20907.556 | 0 | 0 | 0
Estimate Code |  | E00014766 |  |  |  |  | Bolts | 1128.5531 | 0 | 0 | 0
Contract Code |  | J-2239 |  |  |  |  | Purlin | 16015.2454 | 0 | 0 | 0
Contract Name |  | 449-459 Kororoit Creek Road, Altona- Service Stati |  |  |  |  | Labour | 13860.3661 | 0 | 0 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 4400.4746 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 22000.6094 | 0 | 0 | 0
Completion Date |  | 26 Nov 2024 |  |  |  |  | Freight | 1000 | 0 | 0 | 0
Budgeted Revenue |  | 99999.98 |  |  |  |  | Shop Drawings | 1065.9362 | 0 | 0 | 0
Budgeted Job Expenditure |  | 85938.5953 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 14.06% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 12.3965 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 14.06% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 3757.242 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1739.912 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 62.7014 | 0 | 0 | 0
[7 empty] | OH & Profit | 14061.4034 | 0 | 0 | 0
[7 empty] | Total | 99999.9996 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 100000 | 100000 | 85938.5953 | 85938.5953 | 14061.4047 | 14.06% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 100000 | 0 | 85938.5953 | 14061.4047 | 14.06% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Dec 2024 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-2241
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Protilt Constructions |  |  |  |  | Steel | 6774.3265 | 0 | 0 | 0
Estimate Code |  | E00014488 |  |  |  |  | Bolts | 485.3682 | 0 | 0 | 0
Contract Code |  | J-2241 |  |  |  |  | Purlin | 3314.9994 | 0 | 0 | 0
Contract Name |  | 1 Carson Road, Deer Park |  |  |  |  | Labour | 2475.3404 | 0 | 0 | 0
Customer |  | Protilt Constructions |  |  |  |  | Processing | 1510.2693 | 0 | 1092.5 | 0
Start Date |  | 24 Jan 2025 |  |  |  |  | Rigging | 11000.2764 | 0 | 0 | 0
Completion Date |  | 4 Oct 2024 |  |  |  |  | Freight | 500 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 560.025 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 3.8271 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 3.5865 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1661.95 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 300 | 0 | 0 | 0
[7 empty] | Other Materials | 245.6778 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 5971.7677 | 0 | 0 | 0
[7 empty] | Total | 34800.0006 | 0 | 1092.5 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2242
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Genis Steel Internal |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2242 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Wine Cellar |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Genis Steel Internal |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.77693 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2243
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arkit |  |  |  |  | Steel | 29000 | 0 | 0 | 0
Estimate Code |  | E00014844 |  |  |  |  | Bolts | 500 | 0 | 0 | 0
Contract Code |  | J-2243 |  |  |  |  | Purlin | 5000 | 0 | 0 | 0
Contract Name |  | Neometro Display Suit |  |  |  |  | Labour | 25000 | 0 | 0 | 0
Customer |  | Arkit |  |  |  |  | Processing | 1000 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 12 Dec 2024 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 2600 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1000 | 0 | 0 | 0
[7 empty] | OH & Profit | 11000 | 0 | 0 | 0
[7 empty] | Total | 75100 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Dec 2024 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-2244
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | EAZ Crane Hire Pty Ltd |  |  |  |  | Steel | 17762.4431 | 0 | 18050.9955 | 0
Estimate Code |  | E00014213 |  |  |  |  | Bolts | 1497.4132 | 0 | 1602.1455 | 0
Contract Code |  | J-2244 |  |  |  |  | Purlin | 15142.5001 | 0 | 13613.8545 | 0
Contract Name |  | 1-2 Wandarri Court, Cheltenham |  |  |  |  | Labour | 9856.2573 | 0 | 7747.62 | 0
Customer |  | EAZ Crane Hire Pty Ltd |  |  |  |  | Processing | 3917.6558 | 0 | 6047.5 | 0
Start Date |  | 25 Oct 2024 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 8 Aug 2024 |  |  |  |  | Freight | 600 | 0 | 0 | 0
Budgeted Revenue |  | 77900 |  |  |  |  | Shop Drawings | 1958.9108 | 0 | 1350 | 0
Budgeted Job Expenditure |  | 65774.7271 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.57% |  |  |  |  | Box Frame | 13500 | 0 | 0 | 0
Estimated Weight |  | 11.7462 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 12.1798 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.57% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1343.6545 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 195.8911 | 0 | 0 | 0
[7 empty] | OH & Profit | 12125.2739 | 0 | 0 | 0
[7 empty] | Total | 77899.9999 | 0 | 48412.1155 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 77900 | 77900 | 65774.7271 | 65774.7271 | 12125.2729 | 15.57% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 77900 | 0 | 65774.7271 | 12125.2729 | 15.57% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 77900 | 0 | 65774.7271 | 12125.2729 | 15.57% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 77900 | 0 | 65774.7271 | 12125.2729 | 15.57% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 77900 | 0 | 65774.7271 | 12125.2729 | 15.57% | 15580 | 15580 | 1350 | 1350 | 2.052%
Feb 2025 | 0 | 77900 | 0 | 65774.7271 | 12125.2729 | 15.57% | 0 | 15580 | 22052.9091 | 23402.9091 | 35.58%
Mar 2025 | 0 | 77900 | 0 | 65774.7271 | 12125.2729 | 15.57% | 0 | 15580 | 25009.2114 | 48412.1205 | 73.6%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 1598.8664 | 15580 | -13981.1336 | -11804.9454
Feb 2025 | 27717.1293 | 15580 | 12137.1293 | 10247.9637
Mar 2025 | 57336.6755 | 15580 | 41756.6755 | 35257.175
Job Profitability Summary
| Beginning | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 15580 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | -13981.1336 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 13981.1336 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | -11804.9454 | 10247.9637 | 0
Construction Costs | 0 | 0 | 0 | 0 | 1350 | 22052.9091 | 25009.2114 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | -11804.9454 | 10247.9637 | 35257.175 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 13154.9454 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 2.052% | 35.58% | 73.6% | 73.6%

## J-2245
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Total Construction |  |  |  |  | Steel | 76311.0364 | 0 | 0 | 0
Estimate Code |  | E00013875 |  |  |  |  | Bolts | 16990.2407 | 0 | 0 | 0
Contract Code |  | J-2245 |  |  |  |  | Purlin | 52577.5331 | 0 | 0 | 0
Contract Name |  | 130-140 Parraweena Road, Miranda NSW- Storhub |  |  |  |  | Labour | 32082.9365 | 0 | 0 | 0
Customer |  | Total Construction |  |  |  |  | Processing | 19864.5273 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 190018.5 | 0 | 0 | 0
Completion Date |  | 30 May 2024 |  |  |  |  | Freight | 15999.9605 | 0 | 0 | 0
Budgeted Revenue |  | 510989.99 |  |  |  |  | Shop Drawings | 6368.7002 | 0 | 0 | 0
Budgeted Job Expenditure |  | 421498.839 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.51% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 67.257 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 14.3246 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.51% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 8330.2702 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1681.4251 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1273.7131 | 0 | 0 | 0
[7 empty] | OH & Profit | 89491.1632 | 0 | 0 | 0
[7 empty] | Total | 510990.0064 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 510990 | 510990 | 421498.839 | 421498.839 | 89491.161 | 17.51% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 510990 | 0 | 421498.839 | 89491.161 | 17.51% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 510990 | 0 | 421498.839 | 89491.161 | 17.51% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0%

## J-2246
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | North |  |  |  |  | Steel | 434543.1966 | 0 | 0 | 0
Estimate Code |  | E00014489 |  |  |  |  | Bolts | 25113.1777 | 0 | 2908 | 0
Contract Code |  | J-2246 |  |  |  |  | Purlin | 13727.3957 | 0 | 0 | 0
Contract Name |  | Sanitarium Berkeley Vale- Pallet Bridge |  |  |  |  | Labour | 362566.1914 | 0 | 1232.25 | 0
Customer |  | North |  |  |  |  | Processing | 124589.4316 | 0 | 337.5 | 0
Start Date | [6 empty] | Rigging | 298673.9688 | 0 | 14614 | 0
Completion Date |  | 4 Oct 2024 |  |  |  |  | Freight | 154000 | 0 | 0 | 0
Budgeted Revenue |  | 1798999.97 |  |  |  |  | Shop Drawings | 62182.9609 | 0 | 0 | 0
Budgeted Job Expenditure |  | 1487100.2647 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.34% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 207.1447 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 20.5859 |  |  |  |  | Stairs | 61442.7341 | 0 | 0 | 0
Current GP% |  | 17.34% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 191363.3284 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 21260 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 12436.5508 | 0 | 0 | 0
[7 empty] | OH & Profit | 398701.0644 | 0 | 0 | 0
[7 empty] | Total | 2160600.0004 | 0 | 19091.75 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1798999.97 | 1798999.97 | 1487100.2647 | 1487100.2647 | 311899.7054 | 17.34% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 1798999.97 | 0 | 1487100.2647 | 311899.7054 | 17.34% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 1798999.97 | 0 | 1487100.2647 | 311899.7054 | 17.34% | 0 | 0 | 19028.75 | 19028.75 | 1.28%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 23019.7798 | 0 | 23019.7798 | 19028.75
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 19028.75 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 19028.75 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 1.28% | 1.28%

## J-2247
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Aliya Homes |  |  |  |  | Steel | 28992.5828 | 0 | 16244.3455 | 0
Estimate Code |  | E00013666 |  |  |  |  | Bolts | 1594.177 | 0 | 464.7636 | 0
Contract Code |  | J-2247 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 17 Little John Road Warranwood |  |  |  |  | Labour | 12378.362 | 0 | 4160.75 | 0
Customer |  | Aliya Homes |  |  |  |  | Processing | 6928.5383 | 0 | 2932.5 | 0
Start Date |  | 1 Jul 2024 |  |  |  |  | Rigging | 16000 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 1500 | 0 | 0 | 0
Budgeted Revenue |  | 93500.01 |  |  |  |  | Shop Drawings | 6721.2202 | 0 | 6718 | 0
Budgeted Job Expenditure |  | 74452.1108 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.37% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 13.4892 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 14.4402 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 20.37% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 337.2297 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 19047.8949 | 0 | 0 | 0
[7 empty] | Total | 93500.0049 | 0 | 30520.3591 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 93500.01 | 93500.01 | 74452.1108 | 74452.1108 | 19047.8992 | 20.37% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 93500.01 | 0 | 74452.1108 | 19047.8992 | 20.37% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 93500.01 | 0 | 74452.1108 | 19047.8992 | 20.37% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 93500.01 | 0 | 74452.1108 | 19047.8992 | 20.37% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 93500.01 | 0 | 74452.1108 | 19047.8992 | 20.37% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 93500.01 | 0 | 74452.1108 | 19047.8992 | 20.37% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 93500.01 | 0 | 74452.1108 | 19047.8992 | 20.37% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 93500.01 | 0 | 74452.1108 | 19047.8992 | 20.37% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 93500.01 | 0 | 74452.1108 | 19047.8992 | 20.37% | 18700 | 18700 | 5268 | 5268 | 7.076%
Mar 2025 | 0 | 93500.01 | 0 | 74452.1108 | 19047.8992 | 20.37% | 56100 | 74800 | 25252.3591 | 30520.3591 | 40.99%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 6615.7702 | 18700 | -12084.2298 | -9622.4206
Mar 2025 | 38328.7169 | 74800 | -36471.2831 | -29041.3232
Job Profitability Summary
| Beginning | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18700 | 56100 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12084.2298 | -36471.2831 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12084.2298
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9622.4206 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5268 | 25252.3591 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9622.4206 | -29041.3232 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14890.4206 | 44671.2617 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.076% | 40.99% | 40.99%

## J-2248
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Gama Homes Pty Ltd |  |  |  |  | Steel | 4683.2312 | 0 | 822.5 | 0
Estimate Code |  | E00013134 |  |  |  |  | Bolts | 235.711 | 0 | 61.1182 | 0
Contract Code |  | J-2248 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 17 Monash Street Reservoir |  |  |  |  | Labour | 1686.4936 | 0 | 1159.75 | 0
Customer |  | Gama Homes Pty Ltd |  |  |  |  | Processing | 580.8593 | 0 | 833.75 | 0
Start Date |  | 1 Feb 2024 |  |  |  |  | Rigging | 3500 | 0 | 1080 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 250 | 0 | 0 | 0
Budgeted Revenue |  | 15500 |  |  |  |  | Shop Drawings | 648.2053 | 0 | 648 | 0
Budgeted Job Expenditure |  | 11937.7013 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 22.98% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 1.852 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 2.0348 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 22.98% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 306.9 | 0 | 244.8 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 46.3004 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 3562.2997 | 0 | 0 | 0
[7 empty] | Total | 15500.0004 | 0 | 4849.9182 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 15500 | 15500 | 11937.7013 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 2166.3682 | 2166.3682 | 18.15%
Mar 2025 | 0 | 15500 | 0 | 11937.7013 | 3562.2987 | 22.98% | 0 | 0 | 2683.55 | 4849.9182 | 40.63%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 2812.8285 | 0 | 2812.8285 | 2166.3682
Mar 2025 | 6297.1698 | 0 | 6297.1698 | 4849.9182
Job Profitability Summary
| Beginning | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166.3682 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166.3682 | 2683.55 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166.3682 | 4849.9182 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.15% | 40.63% | 40.63%

## J-2249
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Mainbrace Constructions (NSW) |  |  |  |  | Steel | 198736.6095 | 0 | 0 | 0
Estimate Code |  | E00014797 |  |  |  |  | Bolts | 15654.6963 | 0 | 165.5 | 0
Contract Code |  | J-2249 |  |  |  |  | Purlin | 96156.7203 | 0 | 0 | 0
Contract Name |  | 4-6 Messenger Avenue, Boorooma- Coles Boorooma Sho |  |  |  |  | Labour | 118777.0643 | 0 | 7215.06 | 0
Customer |  | Mainbrace Constructions (NSW) |  |  |  |  | Processing | 59894.2109 | 0 | 4872.5 | 0
Start Date |  | 26 Mar 2025 |  |  |  |  | Rigging | 259998.5469 | 0 | 0 | 0
Completion Date |  | 29 Nov 2024 |  |  |  |  | Freight | 32400.0205 | 0 | 406.7818 | 0
Budgeted Revenue |  | 1075000 |  |  |  |  | Shop Drawings | 17901.7949 | 0 | 0 | 0
Budgeted Job Expenditure |  | 880412.4677 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 18.1% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 114.1565 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 111.7695 |  |  |  |  | Stairs | 40000 | 0 | 0 | 0
Current GP% |  | 18.1% |  |  |  |  | Handrails | 37000 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 5446 | 0
[7 empty] | Grates | 63000 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1800 | 0 | 0 | 0
[7 empty] | Special Paint | 57299.3984 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1193.5062 | 0 | 0 | 0
[7 empty] | OH & Profit | 210187.4296 | 0 | 0 | 0
[7 empty] | Total | 1209999.9978 | 0 | 18105.8418 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1075000 | 1075000 | 880412.4677 | 880412.4677 | 194587.5323 | 18.1% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 1075000 | 0 | 880412.4677 | 194587.5323 | 18.1% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 1075000 | 0 | 880412.4677 | 194587.5323 | 18.1% | 0 | 0 | 8334.0918 | 8334.0918 | 0.9466%
Mar 2025 | 0 | 1075000 | 0 | 880412.4677 | 194587.5323 | 18.1% | 0 | 0 | 9771.75 | 18105.8418 | 2.057%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 10176.0811 | 0 | 10176.0811 | 8334.0918
Mar 2025 | 22107.5697 | 0 | 22107.5697 | 18105.8418
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 8334.0918 | 0
Construction Costs | 0 | 0 | 8334.0918 | 9771.75 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 8334.0918 | 18105.8418 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0.9466% | 2.057% | 2.057%

## J-2250
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 2073.0494 | 0 | 2056.0527 | 0
Estimate Code |  | E00014828 |  |  |  |  | Bolts | 349.5449 | 0 | 50.4182 | 0
Contract Code |  | J-2250 |  |  |  |  | Purlin | 58.496 | 0 | 370.6909 | 0
Contract Name |  | 23 Westwood Drive, Ravenhall- Wern Lift |  |  |  |  | Labour | 1292.572 | 0 | 1082 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 510.1535 | 0 | 891.25 | 0
Start Date |  | 31 Mar 2025 |  |  |  |  | Rigging | 12000 | 0 | 10904 | 0
Completion Date |  | 8 Dec 2024 |  |  |  |  | Freight | 400 | 0 | 187.5 | 0
Budgeted Revenue |  | 20599.99 |  |  |  |  | Shop Drawings | 345.104 | 0 | 540 | 0
Budgeted Job Expenditure |  | 17065.506 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.16% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 1.4634 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.96971 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.16% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 36.586 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 3534.4941 | 0 | 0 | 0
[7 empty] | Total | 20600 | 0 | 16081.9118 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 20600 | 20600 | 17065.506 | 17065.506 | 3534.494 | 17.16% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 20600 | 0 | 17065.506 | 3534.494 | 17.16% | 0 | 0 | 16081.9118 | 16081.9118 | 94.24%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | 19412.6903 | 0 | 19412.6903 | 16081.9118
Job Profitability Summary
| Beginning | Feb 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 16081.9118 | #VALUE!
Closing WIP | Difference (GP Exc) | 16081.9118 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 94.24% | 94.24%

## J-2251
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Diggers Rest Construction Pty Ltd |  |  |  |  | Steel | 29412.9877 | 0 | 0 | 0
Estimate Code |  | E00012700 |  |  |  |  | Bolts | 1919.6357 | 0 | 0 | 0
Contract Code |  | J-2251 |  |  |  |  | Purlin | 13500.0032 | 0 | 0 | 0
Contract Name |  | Lot 209 Craftsman Drive, Diggers Rest |  |  |  |  | Labour | 17221.4482 | 0 | 0 | 0
Customer |  | Diggers Rest Construction Pty Ltd |  |  |  |  | Processing | 6896.2587 | 0 | 897.5 | 0
Start Date |  | 1 Sep 2023 |  |  |  |  | Rigging | 20000.0605 | 0 | 0 | 0
Completion Date |  | 12 Jul 2023 |  |  |  |  | Freight | 1999.9949 | 0 | 0 | 0
Budgeted Revenue |  | 137000.01 |  |  |  |  | Shop Drawings | 2481.3162 | 0 | 2100 | 0
Budgeted Job Expenditure |  | 113042.4959 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.49% |  |  |  |  | Box Frame | 10482.164 | 0 | 0 | 0
Estimated Weight |  | 17.0161 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 12.2388 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 19.25% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 3045 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 3587.3696 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2496.2564 | 0 | 0 | 0
[7 empty] | OH & Profit | 23957.5039 | 0 | 0 | 0
[7 empty] | Total | 136999.999 | 0 | 2997.5 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 137000 | 137000 | 110630.5278 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 137000 | 0 | 110630.5278 | 26369.4722 | 19.25% | 0 | 0 | 2100 | 2100 | 1.898%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 2600.548 | 0 | 2600.548 | 2100
Job Profitability Summary
| Beginning | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.898% | 1.898%

## J-2252
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Comfy Pod Pty Ltd |  |  |  |  | Steel | 3760 | 0 | 2341.7 | 0
Estimate Code |  | E00014943 |  |  |  |  | Bolts | 200 | 0 | 109.9455 | 0
Contract Code |  | J-2252 |  |  |  |  | Purlin | 1500 | 0 | 1440.8 | 0
Contract Name |  | 1 Base 12180 x 4650 |  |  |  |  | Labour | 3040 | 0 | 2019.71 | 0
Customer |  | Comfy Pod Pty Ltd |  |  |  |  | Processing | 250 | 0 | 460 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 22 Jan 2025 |  |  |  |  | Freight | 0 | 0 | 218.75 | 0
Budgeted Revenue |  | 10850 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 9150 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.67% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 1.1156 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 44.03% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 400 | 0 | 0 | 0
[7 empty] | OH & Profit | 1700 | 0 | 0 | 3077.59
[7 empty] | Total | 10850 | 0 | 6590.9055 | 3077.59
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 10850 | 10850 | 9150 | 9150 | 1700 | 15.67% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 10850 | 0 | 9150 | 1700 | 15.67% | 0 | 0 | 583.9455 | 583.9455 | 6.382%
Feb 2025 | 0 | 10850 | -3077.59 | 6072.41 | 4777.59 | 44.03% | 13700 | 13700 | 5488.46 | 6072.4055 | 100%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 692.4381 | 0 | 692.4381 | 583.9455
Feb 2025 | 10849.9919 | 13700 | -2850.0081 | -1595.0616
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 13700 | #VALUE!
Less Current Period Overbills | 0 | 0 | -2850.0081 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 583.9455 | 0
Construction Costs | 0 | 583.9455 | 5488.46 | #VALUE!
Closing WIP | Difference (GP Exc) | 583.9455 | -1595.0616 | 0
Total Costruction Cost | #VALUE! | 0 | 7667.467 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 6.382% | 100% | 100%

## J-2253
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Comfy Pod Pty Ltd |  |  |  |  | Steel | 4050 | 0 | 3029.3818 | 0
Estimate Code |  | E00014944 |  |  |  |  | Bolts | 200 | 0 | 121.9455 | 0
Contract Code |  | J-2253 |  |  |  |  | Purlin | 1600 | 0 | 1505.2 | 0
Contract Name |  | 1 Base 15110 x 4110 |  |  |  |  | Labour | 4000 | 0 | 9770 | 0
Customer |  | Comfy Pod Pty Ltd |  |  |  |  | Processing | 250 | 0 | 345 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 22 Jan 2025 |  |  |  |  | Freight | 0 | 0 | 187.5 | 0
Budgeted Revenue |  | 12400 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 10500 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.32% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 1.3917 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.32% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 400 | 0 | 0 | 0
[7 empty] | OH & Profit | 1900 | 0 | 0 | 0
[7 empty] | Total | 12400 | 0 | 14959.0273 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 12400 | 12400 | 10500 | 10500 | 1900 | 15.32% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 12400 | 0 | 10500 | 1900 | 15.32% | 0 | 0 | 629.9455 | 629.9455 | 5.999%
Feb 2025 | 0 | 12400 | 0 | 10500 | 1900 | 15.32% | 15550 | 15550 | 13241.0818 | 13871.0273 | 132.1%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 743.9356 | 0 | 743.9356 | 629.9455
Feb 2025 | 16381.0227 | 15550 | 831.0227 | 703.6886
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 15550 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 629.9455 | 0
Construction Costs | 0 | 629.9455 | 13241.0818 | #VALUE!
Closing WIP | Difference (GP Exc) | 629.9455 | 703.6886 | 0
Total Costruction Cost | #VALUE! | 0 | 13167.3387 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 5.999% | 132.1% | 132.1%

## J-2254
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Pino Tilt Constructions Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00014945 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2254 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Carport |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Pino Tilt Constructions Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 22 Jan 2025 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Jan 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-2256
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Bayston Pty Ltd |  |  |  |  | Steel | 157427.7707 | 0 | 0 | 0
Estimate Code |  | E00013554 |  |  |  |  | Bolts | 14005.5703 | 0 | 0 | 0
Contract Code |  | J-2256 |  |  |  |  | Purlin | 90496.2006 | 0 | 0 | 0
Contract Name |  | 77-81 Forsyth Road, Hoppers Crossing |  |  |  |  | Labour | 60463.857 | 0 | 0 | 0
Customer |  | Bayston Pty Ltd |  |  |  |  | Processing | 27614.8794 | 0 | 0 | 0
Start Date |  | 8 May 2024 |  |  |  |  | Rigging | 127990.6094 | 0 | 0 | 0
Completion Date |  | 20 Mar 2024 |  |  |  |  | Freight | 4199.9756 | 0 | 0 | 0
Budgeted Revenue |  | 615000.01 |  |  |  |  | Shop Drawings | 14839.3613 | 0 | 0 | 0
Budgeted Job Expenditure |  | 517822.1443 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 15.8% |  |  |  |  | Box Frame | 10999.9985 | 0 | 0 | 0
Estimated Weight |  | 75.2935 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 15.8% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 2121.6001 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 2099.9999 | 0 | 0 | 0
[7 empty] | Other Materials | 3162.3363 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2399.9788 | 0 | 0 | 0
[7 empty] | OH & Profit | 97177.8654 | 0 | 0 | 0
[7 empty] | Total | 615000.0033 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 615000.01 | 615000.01 | 517822.1443 | 517822.1443 | 97177.8657 | 15.8% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 615000.01 | 0 | 517822.1443 | 97177.8657 | 15.8% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 615000.01 | 0 | 517822.1443 | 97177.8657 | 15.8% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 615000.01 | 0 | 517822.1443 | 97177.8657 | 15.8% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 615000.01 | 0 | 517822.1443 | 97177.8657 | 15.8% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 615000.01 | 0 | 517822.1443 | 97177.8657 | 15.8% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 615000.01 | 0 | 517822.1443 | 97177.8657 | 15.8% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 615000.01 | 0 | 517822.1443 | 97177.8657 | 15.8% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 615000.01 | 0 | 517822.1443 | 97177.8657 | 15.8% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 615000.01 | 0 | 517822.1443 | 97177.8657 | 15.8% | 123000 | 123000 | 0 | 0 | 0%
Feb 2025 | 0 | 615000.01 | 0 | 517822.1443 | 97177.8657 | 15.8% | 0 | 123000 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 123000 | -123000 | -103564.4272
Feb 2025 | 0 | 123000 | -123000 | -103564.4272
Job Profitability Summary
| Beginning | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123000 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -123000 | -123000 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123000
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -103564.4272 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -103564.4272 | -103564.4272 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103564.4272 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## J-2257
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | ISG Frames |  |  |  |  | Steel | 24334.2259 | 0 | 31209.6273 | 0
Estimate Code |  | E00014759 |  |  |  |  | Bolts | 1684.1075 | 0 | 850.3273 | 0
Contract Code |  | J-2257 |  |  |  |  | Purlin | 2241.363 | 0 | 2520.2909 | 0
Contract Name |  | Ballarto Road, Clyde VIC- Evergreen Land Lease |  |  |  |  | Labour | 18102.8606 | 0 | 10567 | 0
Customer |  | ISG Frames |  |  |  |  | Processing | 12089.4868 | 0 | 5426.75 | 0
Start Date |  | 20 Feb 2025 |  |  |  |  | Rigging | 21500 | 0 | 8552.2 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 1500 | 0 | 1642.5 | 0
Budgeted Revenue |  | 110000 |  |  |  |  | Shop Drawings | 4631.2959 | 0 | 6063 | 0
Budgeted Job Expenditure |  | 86414.1465 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 21.44% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 14.3302 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 14.3815 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 21.44% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 330.8068 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 23585.8539 | 0 | 0 | 0
[7 empty] | Total | 110000.0005 | 0 | 66831.6955 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 110000 | 110000 | 86414.1465 | 86414.1465 | 23585.8535 | 21.44% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 110000 | 0 | 86414.1465 | 23585.8535 | 21.44% | 0 | 0 | 1430 | 1430 | 1.655%
Feb 2025 | 0 | 110000 | 0 | 86414.1465 | 23585.8535 | 21.44% | 57000 | 57000 | 37727.2318 | 39157.2318 | 45.31%
Mar 2025 | 0 | 110000 | 0 | 86414.1465 | 23585.8535 | 21.44% | 0 | 57000 | 27674.4636 | 66831.6955 | 77.34%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 1820.3038 | 0 | 1820.3038 | 1430
Feb 2025 | 49844.796 | 57000 | -7155.204 | -5621.0077
Mar 2025 | 85072.7201 | 57000 | 28072.7201 | 22053.4559
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 57000 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | -7155.204 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 7155.204
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 1430 | -5621.0077 | 0
Construction Costs | 0 | 1430 | 37727.2318 | 27674.4636 | #VALUE!
Closing WIP | Difference (GP Exc) | 1430 | -5621.0077 | 22053.4559 | 0
Total Costruction Cost | #VALUE! | 0 | 44778.2395 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 1.655% | 45.31% | 77.34% | 77.34%

## J-2258
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Bellafia Homes |  |  |  |  | Steel | 98849.0401 | 0 | 0 | 0
Estimate Code |  | E00013202 |  |  |  |  | Bolts | 3557.8762 | 0 | 4295.8818 | 0
Contract Code |  | J-2258 |  |  |  |  | Purlin | 31452.408 | 0 | 0 | 0
Contract Name |  | Lot 11, 37 Launceston Street, Williamstown |  |  |  |  | Labour | 46940.0342 | 0 | 3665.72 | 0
Customer |  | Bellafia Homes |  |  |  |  | Processing | 19283.5024 | 0 | 345 | 0
Start Date |  | 9 Feb 2024 |  |  |  |  | Rigging | 55393.3203 | 0 | 0 | 0
Completion Date |  | 11 Dec 2023 |  |  |  |  | Freight | 3803.7637 | 0 | 0 | 0
Budgeted Revenue |  | 408000 |  |  |  |  | Shop Drawings | 6986.0478 | 0 | 0 | 0
Budgeted Job Expenditure |  | 323299.0311 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.76% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 49.4318 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 54006.6001 | 0 | 0 | 0
Current GP% |  | 20.76% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 392.02 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1235.795 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1398.6233 | 0 | 0 | 0
[7 empty] | OH & Profit | 84700.97 | 0 | 0 | 0
[7 empty] | Total | 408000.0011 | 0 | 8306.6018 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 408000 | 408000 | 323299.0311 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 81600 | 81600 | 4010.72 | 4010.72 | 1.241%
Mar 2025 | 0 | 408000 | 0 | 323299.0311 | 84700.9689 | 20.76% | 0 | 81600 | 4295.8818 | 8306.6018 | 2.569%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 5061.4867 | 81600 | -76538.5133 | -60649.0862
Mar 2025 | 10482.8447 | 81600 | -71117.1553 | -56353.2044
Job Profitability Summary
| Beginning | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81600 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76538.5133 | -71117.1553 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76538.5133
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60649.0862 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4010.72 | 4295.8818 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60649.0862 | -56353.2044 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64659.8062 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.241% | 2.569% | 2.569%

## J-2259
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Bellafia Homes |  |  |  |  | Steel | 162620.9782 | 0 | 43038.1727 | 0
Estimate Code |  | E00013238 |  |  |  |  | Bolts | 8263.7012 | 0 | 5908.5909 | 0
Contract Code |  | J-2259 |  |  |  |  | Purlin | 56567.0375 | 0 | 0 | 0
Contract Name |  | 7 Kelly Court, Bell Park |  |  |  |  | Labour | 49427.9239 | 0 | 9391.47 | 0
Customer |  | Bellafia Homes |  |  |  |  | Processing | 25637.438 | 0 | 1361.1955 | 0
Start Date |  | 13 Feb 2024 |  |  |  |  | Rigging | 115299.8555 | 0 | 40000 | 0
Completion Date |  | 22 Dec 2023 |  |  |  |  | Freight | 5599.9839 | 0 | 0 | 0
Budgeted Revenue |  | 660000.01 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 563649.29 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 14.6% |  |  |  |  | Box Frame | 52500 | 0 | 0 | 0
Estimated Weight |  | 70.6408 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 78000 | 0 | 0 | 0
Current GP% |  | 14.6% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 9100 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 632.3765 | 0 | 0 | 0
[7 empty] | OH & Profit | 96350.7096 | 0 | 0 | 0
[7 empty] | Total | 660000.0042 | 0 | 99699.4291 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 660000 | 660000 | 563649.29 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 100000 | 100000 | 3637.8518 | 3637.8518 | 0.6454%
Mar 2025 | 0 | 660000 | 0 | 563649.29 | 96350.71 | 14.6% | 0 | 100000 | 96061.5773 | 99699.4291 | 17.69%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 4259.7094 | 100000 | -95740.2906 | -81763.5558
Mar 2025 | 116742.138 | 100000 | 16742.138 | 14298.0215
Job Profitability Summary
| Beginning | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -95740.2906 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95740.2906
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -81763.5558 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3637.8518 | 96061.5773 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -81763.5558 | 14298.0215 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85401.4076 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.6454% | 17.69% | 17.69%

## J-2260
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Alpha Truss |  |  |  |  | Steel | 2511.8063 | 0 | 1839.2 | 0
Estimate Code |  | E00014683 |  |  |  |  | Bolts | 112.525 | 0 | 0 | 0
Contract Code |  | J-2260 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 20 Begonia Street, Box Hill |  |  |  |  | Labour | 937.6774 | 0 | 418 | 0
Customer |  | Alpha Truss |  |  |  |  | Processing | 454.1187 | 0 | 0 | 0
Start Date |  | 27 Feb 2025 |  |  |  |  | Rigging | 2300 | 0 | 560 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 300 | 0 | 0 | 0
Budgeted Revenue |  | 8999.98 |  |  |  |  | Shop Drawings | 309.4438 | 0 | 0 | 0
Budgeted Job Expenditure |  | 7217.4749 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 19.81% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0.88413 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 19.81% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 269.8 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 22.1031 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 1782.5255 | 0 | 0 | 0
[7 empty] | Total | 8999.9998 | 0 | 2817.2 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 9000 | 9000 | 7217.475 | 7217.475 | 1782.525 | 19.81% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 9000 | 0 | 7217.475 | 1782.525 | 19.81% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 9000 | 0 | 7217.475 | 1782.525 | 19.81% | 0 | 0 | 2817.2 | 2817.2 | 39.03%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 3512.9737 | 0 | 3512.9737 | 2817.2
Job Profitability Summary
| Beginning | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 2817.2 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 2817.2 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 39.03% | 39.03%

## J-2261
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Leone Constructions Pty Ltd |  |  |  |  | Steel | 6719.5922 | 0 | 0 | 0
Estimate Code |  | E00013825 |  |  |  |  | Bolts | 294.9488 | 0 | 0 | 0
Contract Code |  | J-2261 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 175 Bulla- Diggers Rest Road, Diggers Rest |  |  |  |  | Labour | 3291.7944 | 0 | 63 | 0
Customer |  | Leone Constructions Pty Ltd |  |  |  |  | Processing | 1190.3291 | 0 | 0 | 0
Start Date |  | 30 Jul 2024 |  |  |  |  | Rigging | 8000 | 0 | 1365 | 0
Completion Date |  | 21 May 2024 |  |  |  |  | Freight | 700 | 0 | 0 | 0
Budgeted Revenue |  | 33880.02 |  |  |  |  | Shop Drawings | 1158.7274 | 0 | 690 | 0
Budgeted Job Expenditure |  | 25134.0962 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 25.81% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 2.3175 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 25.81% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1170.7681 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2607.9364 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 8745.9036 | 0 | 0 | 0
[7 empty] | Total | 33880 | 0 | 2118 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 33880 | 33880 | 25134.0962 | 25134.0962 | 8745.9038 | 25.81% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 33880 | 0 | 25134.0962 | 8745.9038 | 25.81% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 33880 | 0 | 25134.0962 | 8745.9038 | 25.81% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 33880 | 0 | 25134.0962 | 8745.9038 | 25.81% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 33880 | 0 | 25134.0962 | 8745.9038 | 25.81% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 33880 | 0 | 25134.0962 | 8745.9038 | 25.81% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 33880 | 0 | 25134.0962 | 8745.9038 | 25.81% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 33880 | 0 | 25134.0962 | 8745.9038 | 25.81% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 33880 | 0 | 25134.0962 | 8745.9038 | 25.81% | 6000 | 6000 | 0 | 0 | 0%
Mar 2025 | 0 | 33880 | 0 | 25134.0962 | 8745.9038 | 25.81% | 0 | 6000 | 2118 | 2118 | 8.427%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 6000 | -6000 | -4451.1386
Mar 2025 | 2854.9998 | 6000 | -3145.0002 | -2333.1386
Job Profitability Summary
| Beginning | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6000 | -3145.0002 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4451.1386 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2118 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4451.1386 | -2333.1386 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4451.1386 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.427% | 8.427%

## J-2262
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Taylors Construction Group |  |  |  |  | Steel | 221295.4946 | 0 | 0 | 0
Estimate Code |  | E00013354 |  |  |  |  | Bolts | 13971.7031 | 0 | 0 | 0
Contract Code |  | J-2262 |  |  |  |  | Purlin | 80617.0489 | 0 | 0 | 0
Contract Name |  | Astra Aerolab, Lot 109-1 Cabbage Tree Road, Willia |  |  |  |  | Labour | 88703.8413 | 0 | 0 | 0
Customer |  | Taylors Construction Group |  |  |  |  | Processing | 38207.5225 | 0 | 100 | 0
Start Date | [6 empty] | Rigging | 165387.1035 | 0 | 0 | 0
Completion Date |  | 7 Feb 2024 |  |  |  |  | Freight | 50276.458 | 0 | 0 | 0
Budgeted Revenue |  | 830000.01 |  |  |  |  | Shop Drawings | 18161.7422 | 0 | 0 | 0
Budgeted Job Expenditure |  | 683889.4174 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.6% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 97.1382 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.6% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 3840.5801 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2428.456 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 999.4554 | 0 | 0 | 0
[7 empty] | OH & Profit | 146110.5881 | 0 | 0 | 0
[7 empty] | Total | 829999.9937 | 0 | 100 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 830000 | 830000 | 683889.4174 | 683889.4174 | 146110.5826 | 17.6% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 830000 | 0 | 683889.4174 | 146110.5826 | 17.6% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Feb 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-2264
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Vaughan Constructions Pty Ltd |  |  |  |  | Steel | 115087.5521 | 0 | 0 | 0
Estimate Code |  | E00014558 |  |  |  |  | Bolts | 7954.7129 | 0 | 0 | 0
Contract Code |  | J-2264 |  |  |  |  | Purlin | 91409.8285 | 0 | 0 | 0
Contract Name |  | Link Road, Melbourne Airport |  |  |  |  | Labour | 47818.5366 | 0 | 1680 | 0
Customer |  | Vaughan Constructions Pty Ltd |  |  |  |  | Processing | 30002.4414 | 0 | 143.75 | 0
Start Date |  | 31 Jan 2025 |  |  |  |  | Rigging | 78999.8477 | 0 | 0 | 0
Completion Date |  | 18 Oct 2024 |  |  |  |  | Freight | 2400.0206 | 0 | 0 | 0
Budgeted Revenue |  | 488499.98 |  |  |  |  | Shop Drawings | 7954.6631 | 0 | 0 | 0
Budgeted Job Expenditure |  | 420781.6089 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 13.86% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 91.3867 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 14599.9962 | 0 | 0 | 0
Current GP% |  | 13.86% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 11554.6839 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 7149.9997 | 0 | 0 | 0
[7 empty] | Other Materials | 4620 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1229.3337 | 0 | 0 | 0
[7 empty] | OH & Profit | 67718.3837 | 0 | 0 | 0
[7 empty] | Total | 488500.0001 | 0 | 1823.75 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 488499.99 | 488499.99 | 420781.6089 | 420781.6089 | 67718.3811 | 13.86% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 488499.99 | 0 | 420781.6089 | 67718.3811 | 13.86% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 488499.99 | 0 | 420781.6089 | 67718.3811 | 13.86% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0%

## J-2265
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Impact Designer Homes |  |  |  |  | Steel | 3800 | 0 | 2800.2909 | 0
Estimate Code |  | E00015049 |  |  |  |  | Bolts | 250 | 0 | 264.5455 | 0
Contract Code |  | J-2265 |  |  |  |  | Purlin | 4350 | 0 | 0 | 0
Contract Name |  | 40 McKellar Way, Epping- Factory 5 Mezzanine |  |  |  |  | Labour | 0 | 0 | 204 | 0
Customer |  | Impact Designer Homes |  |  |  |  | Processing | 2850 | 0 | 1307.5 | 0
Start Date | [6 empty] | Rigging | 8752 | 0 | 0 | 0
Completion Date |  | 12 Feb 2025 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 23000 |  |  |  |  | Shop Drawings | 400 | 0 | 0 | 0
Budgeted Job Expenditure |  | 20402 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 11.3% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 1.8266 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 11.3% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 2598 | 0 | 0 | 0
[7 empty] | Total | 23000 | 0 | 4576.3364 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 23000 | 23000 | 20402 | 20402 | 2598 | 11.3% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 23000 | 0 | 20402 | 2598 | 11.3% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 23000 | 0 | 20402 | 2598 | 11.3% | 0 | 0 | 4576.3364 | 4576.3364 | 22.43%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 5159.0891 | 0 | 5159.0891 | 4576.3364
Job Profitability Summary
| Beginning | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 4576.3364 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 4576.3364 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 22.43% | 22.43%

## J-2267
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Marven Construction |  |  |  |  | Steel | 1829.9405 | 0 | 0 | 0
Estimate Code |  | E00012154 |  |  |  |  | Bolts | 47.6854 | 0 | 38.2 | 0
Contract Code |  | J-2267 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 51 Ewart Street, Malvern |  |  |  |  | Labour | 705.4936 | 0 | 1726 | 0
Customer |  | Marven Construction |  |  |  |  | Processing | 384.8893 | 0 | 1092.5 | 0
Start Date |  | 28 Apr 2023 |  |  |  |  | Rigging | 2800 | 0 | 0 | 0
Completion Date |  | 17 Feb 2023 |  |  |  |  | Freight | 400 | 0 | 0 | 0
Budgeted Revenue |  | 8499.98 |  |  |  |  | Shop Drawings | 262.2697 | 0 | 0 | 0
Budgeted Job Expenditure |  | 6532.202 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 23.15% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0.74934 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.69848 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 23.15% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 83.19 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 18.7336 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 1967.7979 | 0 | 0 | 0
[7 empty] | Total | 8500 | 0 | 2856.7 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 8500 | 8500 | 6532.202 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 8500 | 0 | 6532.202 | 1967.798 | 23.15% | 0 | 0 | 2856.7 | 2856.7 | 43.73%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 3717.2687 | 0 | 3717.2687 | 2856.7
Job Profitability Summary
| Beginning | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2856.7 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2856.7 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 43.73% | 43.73%

## J-2268
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Impact Designer Homes |  |  |  |  | Steel | 103628.2422 | 0 | 0 | 0
Estimate Code |  | E00014516 |  |  |  |  | Bolts | 6370.1206 | 0 | 802 | 0
Contract Code |  | J-2268 |  |  |  |  | Purlin | 42475.4951 | 0 | 0 | 0
Contract Name |  | 44 Freight Drive, Somerton |  |  |  |  | Labour | 41396.8573 | 0 | 0 | 0
Customer |  | Impact Designer Homes |  |  |  |  | Processing | 22735.0488 | 0 | 0 | 0
Start Date |  | 29 Jan 2025 |  |  |  |  | Rigging | 61599.9062 | 0 | 0 | 0
Completion Date |  | 8 Oct 2024 |  |  |  |  | Freight | 2000.0035 | 0 | 0 | 0
Budgeted Revenue |  | 370500.01 |  |  |  |  | Shop Drawings | 6370.1733 | 0 | 0 | 0
Budgeted Job Expenditure |  | 309178.5869 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.55% |  |  |  |  | Box Frame | 17400 | 0 | 0 | 0
Estimated Weight |  | 58.4259 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.55% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1365.08 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 1649.9999 | 0 | 0 | 0
[7 empty] | Other Materials | 1550 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 637.66 | 0 | 0 | 0
[7 empty] | OH & Profit | 61321.4119 | 0 | 0 | 0
[7 empty] | Total | 370499.9991 | 0 | 802 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 370500 | 370500 | 309178.5869 | 309178.5869 | 61321.4131 | 16.55% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 370500 | 0 | 309178.5869 | 61321.4131 | 16.55% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 370500 | 0 | 309178.5869 | 61321.4131 | 16.55% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 370500 | 0 | 309178.5869 | 61321.4131 | 16.55% | 0 | 0 | 802 | 802 | 0.2594%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 961.0659 | 0 | 961.0659 | 802
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 802 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 802 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0.2594% | 0.2594%

## J-2269
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | A Grade Concrete Pty Ltd |  |  |  |  | Steel | 47400.0918 | 0 | 0 | 0
Estimate Code |  | E00014821 |  |  |  |  | Bolts | 2341.064 | 0 | 0 | 0
Contract Code |  | J-2269 |  |  |  |  | Purlin | 16914.624 | 0 | 0 | 0
Contract Name |  | 29 Woodberry Way, Epping |  |  |  |  | Labour | 17285.4229 | 0 | 1386 | 0
Customer |  | A Grade Concrete Pty Ltd |  |  |  |  | Processing | 8221.488 | 0 | 345 | 0
Start Date |  | 28 Mar 2025 |  |  |  |  | Rigging | 33270.6269 | 0 | 0 | 0
Completion Date |  | 6 Dec 2024 |  |  |  |  | Freight | 800 | 0 | 0 | 0
Budgeted Revenue |  | 171200 |  |  |  |  | Shop Drawings | 2261.023 | 0 | 0 | 0
Budgeted Job Expenditure |  | 141758.218 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.2% |  |  |  |  | Box Frame | 12600 | 0 | 0 | 0
Estimated Weight |  | 20.5551 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 18.2192 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.2% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 150 | 0 | 0 | 0
[7 empty] | Other Materials | 513.8782 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 29441.7805 | 0 | 0 | 0
[7 empty] | Total | 171199.9993 | 0 | 1731 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 171200 | 171200 | 141758.218 | 141758.218 | 29441.782 | 17.2% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 171200 | 0 | 141758.218 | 29441.782 | 17.2% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Feb 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-2270
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Rousson Constructions |  |  |  |  | Steel | 15363.1529 | 0 | 0 | 0
Estimate Code |  | E00013831 |  |  |  |  | Bolts | 899.8143 | 0 | 0 | 0
Contract Code |  | J-2270 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 40 Petrik Drive Keilor |  |  |  |  | Labour | 6373.3322 | 0 | 0 | 0
Customer |  | Rousson Constructions |  |  |  |  | Processing | 3631.3934 | 0 | 0 | 0
Start Date |  | 1 Aug 2024 |  |  |  |  | Rigging | 9000 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 1000 | 0 | 0 | 0
Budgeted Revenue |  | 49500.01 |  |  |  |  | Shop Drawings | 2474.4893 | 0 | 1260 | 0
Budgeted Job Expenditure |  | 38918.9288 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 21.38% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 7.07 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 21.38% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 176.7492 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 10581.0724 | 0 | 0 | 0
[7 empty] | Total | 49500.0037 | 0 | 1260 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 49500 | 49500 | 38918.9288 | 38918.9288 | 10581.0712 | 21.38% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 49500 | 0 | 38918.9288 | 10581.0712 | 21.38% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 49500 | 0 | 38918.9288 | 10581.0712 | 21.38% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 49500 | 0 | 38918.9288 | 10581.0712 | 21.38% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 49500 | 0 | 38918.9288 | 10581.0712 | 21.38% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 49500 | 0 | 38918.9288 | 10581.0712 | 21.38% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 49500 | 0 | 38918.9288 | 10581.0712 | 21.38% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 49500 | 0 | 38918.9288 | 10581.0712 | 21.38% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 49500 | 0 | 38918.9288 | 10581.0712 | 21.38% | 0 | 0 | 1260 | 1260 | 3.237%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 1602.5621 | 0 | 1602.5621 | 1260
Job Profitability Summary
| Beginning | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.237% | 3.237%

## J-2271
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | WB Built |  |  |  |  | Steel | 3825.9 | 0 | 0 | 0
Estimate Code |  | E00014969 |  |  |  |  | Bolts | 201.6 | 0 | 181.5091 | 0
Contract Code |  | J-2271 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 1689 Malvern Road, Glen Iris - Basement |  |  |  |  | Labour | 1369.599 | 0 | 745 | 0
Customer |  | WB Built |  |  |  |  | Processing | 496.8 | 0 | 460 | 0
Start Date |  | 1 Mar 2025 |  |  |  |  | Rigging | 3000 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 300 | 0 | 0 | 0
Budgeted Revenue |  | 13500 |  |  |  |  | Shop Drawings | 554.4 | 0 | 200 | 0
Budgeted Job Expenditure |  | 11227.899 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.83% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 1.584 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.83% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1440 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 39.6 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 2272.1008 | 0 | 0 | 0
[7 empty] | Total | 13499.9999 | 0 | 1586.5091 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 13500 | 13500 | 11227.899 | 11227.899 | 2272.101 | 16.83% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 13500 | 0 | 11227.899 | 2272.101 | 16.83% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 13500 | 0 | 11227.899 | 2272.101 | 16.83% | 0 | 0 | 1586.5091 | 1586.5091 | 14.13%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 1907.5584 | 0 | 1907.5584 | 1586.5091
Job Profitability Summary
| Beginning | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 1586.5091 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 1586.5091 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 14.13% | 14.13%

## J-2272
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Davies Henderson Pty Ltd |  |  |  |  | Steel | 32444.4937 | 0 | 0 | 0
Estimate Code |  | E00012670 |  |  |  |  | Bolts | 1241.723 | 0 | 0 | 0
Contract Code |  | J-2272 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 9 North Road, Brighton |  |  |  |  | Labour | 8487.4301 | 0 | 0 | 0
Customer |  | Davies Henderson Pty Ltd |  |  |  |  | Processing | 4035.5997 | 0 | 0 | 0
Start Date |  | 24 Aug 2023 |  |  |  |  | Rigging | 14000 | 0 | 0 | 0
Completion Date |  | 5 Jul 2023 |  |  |  |  | Freight | 2000 | 0 | 0 | 0
Budgeted Revenue |  | 83000 |  |  |  |  | Shop Drawings | 3414.7383 | 0 | 1750 | 0
Budgeted Job Expenditure |  | 66455.8953 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 19.93% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 9.7564 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 19.93% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 588 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 243.9099 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 16544.1047 | 0 | 0 | 0
[7 empty] | Total | 82999.9994 | 0 | 1750 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 83000 | 83000 | 66455.8953 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 83000 | 0 | 66455.8953 | 16544.1047 | 19.93% | 0 | 0 | 1750 | 1750 | 2.633%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 2185.6601 | 0 | 2185.6601 | 1750
Job Profitability Summary
| Beginning | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.633% | 2.633%

## J-2273
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arch 10 Pty Ltd |  |  |  |  | Steel | 9702.3139 | 0 | 0 | 0
Estimate Code |  | E00014397 |  |  |  |  | Bolts | 675.0747 | 0 | 0 | 0
Contract Code |  | J-2273 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 10 Leyland Street, Mount Waverley |  |  |  |  | Labour | 5246.7548 | 0 | 0 | 0
Customer |  | Arch 10 Pty Ltd |  |  |  |  | Processing | 1663.5769 | 0 | 0 | 0
Start Date |  | 13 Jan 2025 |  |  |  |  | Rigging | 4000 | 0 | 0 | 0
Completion Date |  | 13 Sep 2024 |  |  |  |  | Freight | 200 | 0 | 0 | 0
Budgeted Revenue |  | 28399.99 |  |  |  |  | Shop Drawings | 1856.4553 | 0 | 795 | 0
Budgeted Job Expenditure |  | 24626.7592 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 13.29% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 5.3042 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 13.29% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1149.98 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 132.604 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 3773.24 | 0 | 0 | 0
[7 empty] | Total | 28399.9996 | 0 | 795 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 28400 | 28400 | 24626.7592 | 24626.7592 | 3773.2408 | 13.29% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 28400 | 0 | 24626.7592 | 3773.2408 | 13.29% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 28400 | 0 | 24626.7592 | 3773.2408 | 13.29% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 28400 | 0 | 24626.7592 | 3773.2408 | 13.29% | 0 | 0 | 795 | 795 | 3.228%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 916.8076 | 0 | 916.8076 | 795
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 795 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 795 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 3.228% | 3.228%

## J-2274
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | LSR Construction Group Pty Ltd |  |  |  |  | Steel | 63055.5402 | 0 | 0 | 0
Estimate Code |  | E00014958 |  |  |  |  | Bolts | 7543.0303 | 0 | 0 | 0
Contract Code |  | J-2274 |  |  |  |  | Purlin | 44221.0527 | 0 | 0 | 0
Contract Name |  | 50 Wirraway Drive, Port Melbourne |  |  |  |  | Labour | 24275.6035 | 0 | 0 | 0
Customer |  | LSR Construction Group Pty Ltd |  |  |  |  | Processing | 14500.7773 | 0 | 0 | 0
Start Date |  | 20 Mar 2025 |  |  |  |  | Rigging | 51918.3711 | 0 | 0 | 0
Completion Date |  | 23 Jan 2025 |  |  |  |  | Freight | 2399.9883 | 0 | 0 | 0
Budgeted Revenue |  | 261899.99 |  |  |  |  | Shop Drawings | 3943.0303 | 0 | 0 | 0
Budgeted Job Expenditure |  | 216602.8957 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.3% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 35.8457 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.3% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 3190.898 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1196.1433 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 358.4573 | 0 | 0 | 0
[7 empty] | OH & Profit | 45297.107 | 0 | 0 | 0
[7 empty] | Total | 261899.9992 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 261900 | 261900 | 216602.8957 | 216602.8957 | 45297.1043 | 17.3% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 261900 | 0 | 216602.8957 | 45297.1043 | 17.3% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Feb 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-2275
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Rosemont Property Developments |  |  |  |  | Steel | 35306.005 | 0 | 0 | 0
Estimate Code |  | E00014789 |  |  |  |  | Bolts | 1958.0406 | 0 | 0 | 0
Contract Code |  | J-2275 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 21 Two Bays Crescent Mount Martha |  |  |  |  | Labour | 16370.2357 | 0 | 0 | 0
Customer |  | Rosemont Property Developments |  |  |  |  | Processing | 11940.5533 | 0 | 0 | 0
Start Date |  | 1 Mar 2025 |  |  |  |  | Rigging | 19500 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 2000 | 0 | 0 | 0
Budgeted Revenue |  | 108000 |  |  |  |  | Shop Drawings | 7692.3027 | 0 | 2800 | 0
Budgeted Job Expenditure |  | 92553.7071 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 14.3% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 15.3846 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 14.3% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 22.9 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 384.6151 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 15825.3481 | 0 | 0 | 0
[7 empty] | Total | 111000.0007 | 0 | 2800 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 108000 | 108000 | 92553.7071 | 92553.7071 | 15446.2929 | 14.3% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 108000 | 0 | 92553.7071 | 15446.2929 | 14.3% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 108000 | 0 | 92553.7071 | 15446.2929 | 14.3% | 0 | 0 | 2800 | 2800 | 3.025%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 3267.2921 | 0 | 3267.2921 | 2800
Job Profitability Summary
| Beginning | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 2800 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 2800 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 3.025% | 3.025%

## J-2276
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | VP Homes |  |  |  |  | Steel | 2005.0537 | 0 | 0 | 0
Estimate Code |  | E00014805 |  |  |  |  | Bolts | 143.577 | 0 | 66.5091 | 0
Contract Code |  | J-2276 |  |  |  |  | Purlin | 334.89 | 0 | 449.6909 | 0
Contract Name |  | 196 Brooklyn Road Brookfield |  |  |  |  | Labour | 922.9176 | 0 | 398 | 0
Customer |  | VP Homes |  |  |  |  | Processing | 579.4358 | 0 | 805 | 0
Start Date | [6 empty] | Rigging | 2600 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 300 | 0 | 0 | 0
Budgeted Revenue |  | 10000.01 |  |  |  |  | Shop Drawings | 394.8368 | 0 | 0 | 0
Budgeted Job Expenditure |  | 8334.4641 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.66% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 1.2456 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.91951 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.66% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1025.55 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 28.2026 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 1665.5368 | 0 | 0 | 0
[7 empty] | Total | 10000.0003 | 0 | 1719.2 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 10000 | 10000 | 8334.4641 | 8334.4641 | 1665.5359 | 16.66% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 10000 | 0 | 8334.4641 | 1665.5359 | 16.66% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 10000 | 0 | 8334.4641 | 1665.5359 | 16.66% | 0 | 0 | 1719.2 | 1719.2 | 20.63%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 2062.7601 | 0 | 2062.7601 | 1719.2
Job Profitability Summary
| Beginning | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 1719.2 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 1719.2 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 20.63% | 20.63%

## J-2277
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | AAA Above Group |  |  |  |  | Steel | 22172.8353 | 0 | 0 | 0
Estimate Code |  | E00011757 |  |  |  |  | Bolts | 2157.2172 | 0 | 0 | 0
Contract Code |  | J-2277 |  |  |  |  | Purlin | 16999.996 | 0 | 0 | 0
Contract Name |  | 23-25 Seaside Parade, North Shore |  |  |  |  | Labour | 8292.5944 | 0 | 0 | 0
Customer |  | AAA Above Group |  |  |  |  | Processing | 4239.8982 | 0 | 0 | 0
Start Date |  | 27 Jan 2023 |  |  |  |  | Rigging | 24200.2022 | 0 | 0 | 0
Completion Date |  | 7 Oct 2022 |  |  |  |  | Freight | 1000.0011 | 0 | 0 | 0
Budgeted Revenue |  | 107499.99 |  |  |  |  | Shop Drawings | 1635.2867 | 0 | 0 | 0
Budgeted Job Expenditure |  | 89312.5664 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 16.92% |  |  |  |  | Box Frame | 6700.0036 | 0 | 0 | 0
Estimated Weight |  | 11.1381 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 16.92% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 100 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 900 | 0 | 0 | 0
[7 empty] | Other Materials | 478.4529 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 436.0794 | 0 | 0 | 0
[7 empty] | OH & Profit | 18187.4331 | 0 | 0 | 0
[7 empty] | Total | 107500 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 107500 | 107500 | 89312.5664 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Jan 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Feb 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Mar 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Apr 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
May 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Jun 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Jul 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Aug 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Sep 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 107500 | 0 | 89312.5664 | 18187.4336 | 16.92% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2023 | 0 | 0 | 0 | 0
Feb 2023 | 0 | 0 | 0 | 0
Mar 2023 | 0 | 0 | 0 | 0
Apr 2023 | 0 | 0 | 0 | 0
May 2023 | 0 | 0 | 0 | 0
Jun 2023 | 0 | 0 | 0 | 0
Jul 2023 | 0 | 0 | 0 | 0
Aug 2023 | 0 | 0 | 0 | 0
Sep 2023 | 0 | 0 | 0 | 0
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## J-2278
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Story Built Pty Ltd |  |  |  |  | Steel | 12036.3188 | 0 | 0 | 0
Estimate Code |  | E00014904 |  |  |  |  | Bolts | 766.5294 | 0 | 143.6364 | 0
Contract Code |  | J-2278 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 7 Fir Street, Bulleen |  |  |  |  | Labour | 5452.7186 | 0 | 1487.75 | 0
Customer |  | Story Built Pty Ltd |  |  |  |  | Processing | 2792.3571 | 0 | 1236.25 | 0
Start Date |  | 7 Mar 2025 |  |  |  |  | Rigging | 7000 | 0 | 0 | 0
Completion Date |  | 8 Jan 2025 |  |  |  |  | Freight | 600 | 0 | 0 | 0
Budgeted Revenue |  | 37000.01 |  |  |  |  | Shop Drawings | 2107.9558 | 0 | 1080 | 0
Budgeted Job Expenditure |  | 32307.4072 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 12.68% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 6.0227 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 5.6974 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 12.68% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1400.96 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 150.5683 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 4692.5925 | 0 | 0 | 0
[7 empty] | Total | 37000.0005 | 0 | 3947.6364 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 37000 | 37000 | 32307.4072 | 32307.4072 | 4692.5928 | 12.68% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 37000 | 0 | 32307.4072 | 4692.5928 | 12.68% | 0 | 0 | 3947.6364 | 3947.6364 | 12.22%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | 4521.0235 | 0 | 4521.0235 | 3947.6364
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 3947.6364 | #VALUE!
Closing WIP | Difference (GP Exc) | 3947.6364 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 12.22% | 12.22%

## J-2279
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | LSR Construction Group Pty Ltd |  |  |  |  | Steel | 116983.4571 | 0 | 0 | 0
Estimate Code |  | E00014423 |  |  |  |  | Bolts | 7438.1353 | 0 | 0 | 0
Contract Code |  | J-2279 |  |  |  |  | Purlin | 71277.0168 | 0 | 0 | 0
Contract Name |  | 128 Paramount Boulevard, Derrimut |  |  |  |  | Labour | 48223.3379 | 0 | 0 | 0
Customer |  | LSR Construction Group Pty Ltd |  |  |  |  | Processing | 26372.3442 | 0 | 0 | 0
Start Date |  | 17 Jan 2025 |  |  |  |  | Rigging | 89999.5859 | 0 | 0 | 0
Completion Date |  | 20 Sep 2024 |  |  |  |  | Freight | 2999.9985 | 0 | 0 | 0
Budgeted Revenue |  | 508000.01 |  |  |  |  | Shop Drawings | 7438.1909 | 0 | 0 | 0
Budgeted Job Expenditure |  | 419999.8383 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.32% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 67.6205 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 27999.9952 | 0 | 0 | 0
Current GP% |  | 17.32% |  |  |  |  | Handrails | 9900 | 0 | 0 | 0
[7 empty] | Galvanizing | 2141.57 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 8550 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 676.2053 | 0 | 0 | 0
[7 empty] | OH & Profit | 88000.1619 | 0 | 0 | 0
[7 empty] | Total | 507999.9991 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 508000 | 508000 | 419999.8383 | 419999.8383 | 88000.1617 | 17.32% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 508000 | 0 | 419999.8383 | 88000.1617 | 17.32% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 508000 | 0 | 419999.8383 | 88000.1617 | 17.32% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 508000 | 0 | 419999.8383 | 88000.1617 | 17.32% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0%

## J-2280
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Comfy Pod Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2280 |  |  |  |  | Purlin | 0 | 0 | 359.5 | 0
Contract Name |  | 1 Base 5110 x 31100 |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Comfy Pod Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0.55345 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 359.5 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 359.5 | 359.5 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | 0
Construction Costs | 0 | 0 | 359.5 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2281
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arkit |  |  |  |  | Steel | 0 | 0 | 408.5545 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2281 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Subfloor Components |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Arkit |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 408.5545 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 408.5545 | 408.5545 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | 0
Construction Costs | 0 | 0 | 408.5545 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2282
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 9675.7838 | 0 | 0 | 0
Estimate Code |  | E00015127 |  |  |  |  | Bolts | 709.506 | 0 | 0 | 0
Contract Code |  | J-2282 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 561 Grieve Parade, Brooklyn- Beams & PFC - HDG |  |  |  |  | Labour | 7916.06 | 0 | 0 | 0
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 2305.8945 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 9198.2383 | 0 | 0 | 0
Completion Date |  | 25 Feb 2025 |  |  |  |  | Freight | 722.9876 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 1672.407 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 5.5747 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 5067.9 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 139.3673 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 167.2407 | 0 | 0 | 0
[7 empty] | OH & Profit | 12073.1157 | 0 | 0 | 0
[7 empty] | Total | 49648.5007 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Feb 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-2283
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | A Grade Concrete Pty Ltd |  |  |  |  | Steel | 36490.1711 | 0 | 0 | 0
Estimate Code |  | E00014778 |  |  |  |  | Bolts | 2827.7817 | 0 | 0 | 0
Contract Code |  | J-2283 |  |  |  |  | Purlin | 25286.9998 | 0 | 0 | 0
Contract Name |  | Lot 14 Woodberry Way, Epping- Factory 1 & 2 |  |  |  |  | Labour | 15570.4377 | 0 | 0 | 0
Customer |  | A Grade Concrete Pty Ltd |  |  |  |  | Processing | 7943.9836 | 0 | 0 | 0
Start Date |  | 21 Mar 2025 |  |  |  |  | Rigging | 35999.8652 | 0 | 0 | 0
Completion Date |  | 28 Nov 2024 |  |  |  |  | Freight | 1599.9999 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 2717.8489 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 24000 | 0 | 0 | 0
Estimated Weight |  | 20.3229 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1558.0737 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 606.2946 | 0 | 0 | 0
[7 empty] | OH & Profit | 27398.5433 | 0 | 0 | 0
[7 empty] | Total | 181999.9996 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2284
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | PIPETEK Plumbing Pty Ltd |  |  |  |  | Steel | 1434.1887 | 0 | 0 | 0
Estimate Code |  | E00015158 |  |  |  |  | Bolts | 42.5705 | 0 | 0 | 0
Contract Code |  | J-2284 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 15 Everlasting Chase Whittlesea |  |  |  |  | Labour | 612.1428 | 0 | 0 | 0
Customer |  | PIPETEK Plumbing Pty Ltd |  |  |  |  | Processing | 276.7083 | 0 | 0 | 0
Start Date |  | 25 Mar 2025 |  |  |  |  | Rigging | 1300 | 0 | 480 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 26.7586 | 0 | 0 | 0
Budgeted Revenue |  | 5500.01 |  |  |  |  | Shop Drawings | 234.1378 | 0 | 0 | 0
Budgeted Job Expenditure |  | 3943.23 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 28.31% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0.66897 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 28.3% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 16.7241 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 1556.7687 | 0 | 0 | 0
[7 empty] | Total | 5499.9996 | 0 | 480 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 5500 | 5500 | 3943.2301 | 3943.2301 | 1556.77 | 28.3% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 5500 | 0 | 3943.2301 | 1556.77 | 28.3% | 5500 | 5500 | 480 | 480 | 12.17%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | 669.5019 | 5500 | -4830.4981 | -3463.2301
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 5500 | #VALUE!
Less Current Period Overbills | 0 | -4830.4981 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 480 | #VALUE!
Closing WIP | Difference (GP Exc) | -3463.2301 | 0
Total Costruction Cost | #VALUE! | 3943.2301 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 12.17% | 12.17%

## J-2285
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 104580.1994 | 0 | 0 | 0
Estimate Code |  | E00014996 |  |  |  |  | Bolts | 6701.0928 | 0 | 41.8364 | 0
Contract Code |  | J-2285 |  |  |  |  | Purlin | 19172.3174 | 0 | 0 | 0
Contract Name |  | 122 Harrick Road, Keilor Park |  |  |  |  | Labour | 31864.4487 | 0 | 147 | 0
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 21930.9595 | 0 | 0 | 0
Start Date |  | 8 Apr 2025 |  |  |  |  | Rigging | 61737.1211 | 0 | 0 | 0
Completion Date |  | 31 Jan 2025 |  |  |  |  | Freight | 2499.9716 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 6091.9023 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 60.919 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 6331.1789 | 0 | 0 | 0
[7 empty] | Grates | 7920 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 2752.9756 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 609.1902 | 0 | 0 | 0
[7 empty] | OH & Profit | 57808.6413 | 0 | 0 | 0
[7 empty] | Total | 329999.9989 | 0 | 188.8364 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 188.8364 | 188.8364 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 188.8364 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-2286
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Davies Henderson Pty Ltd |  |  |  |  | Steel | 29204.5258 | 0 | 0 | 0
Estimate Code |  | E00015147 |  |  |  |  | Bolts | 2007.5519 | 0 | 0 | 0
Contract Code |  | J-2286 |  |  |  |  | Purlin | 4232.4282 | 0 | 0 | 0
Contract Name |  | 29-31 St Georges Road, Toorak - Straight Fence Pos |  |  |  |  | Labour | 12784.1975 | 0 | 0 | 0
Customer |  | Davies Henderson Pty Ltd |  |  |  |  | Processing | 26547.1814 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 3 Mar 2025 |  |  |  |  | Freight | 1500 | 0 | 0 | 0
Budgeted Revenue |  | 83000 |  |  |  |  | Shop Drawings | 5520.7676 | 0 | 0 | 0
Budgeted Job Expenditure |  | 68716.9974 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 17.21% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 15.7736 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 17.21% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 14339.6557 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 394.3406 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 14469.354 | 0 | 0 | 0
[7 empty] | Total | 111000.0027 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 83000 | 83000 | 68716.9974 | 68716.9974 | 14283.0026 | 17.21% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 83000 | 0 | 68716.9974 | 14283.0026 | 17.21% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-2287
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | RBM Construction Group Pty Ltd |  |  |  |  | Steel | 11931.1067 | 0 | 0 | 0
Estimate Code |  | E00014014 |  |  |  |  | Bolts | 669.4758 | 0 | 0 | 0
Contract Code |  | J-2287 |  |  |  |  | Purlin | 2387.3199 | 0 | 0 | 0
Contract Name |  | 36 King Street, Airport West |  |  |  |  | Labour | 5552.6545 | 0 | 0 | 0
Customer |  | RBM Construction Group Pty Ltd |  |  |  |  | Processing | 2701.8132 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 12500 | 0 | 0 | 0
Completion Date |  | 1 Jul 2024 |  |  |  |  | Freight | 800 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 1841.0585 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 6.0084 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 131.5042 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 9485.0674 | 0 | 0 | 0
[7 empty] | Total | 48000.0002 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2288
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arjay Modular |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2288 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Gate 22, Melbourne Airport |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Arjay Modular |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2289
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Quadrant Building |  |  |  |  | Steel | 3562.6162 | 0 | 0 | 0
Estimate Code |  | E00015089 |  |  |  |  | Bolts | 249.0894 | 0 | 0 | 0
Contract Code |  | J-2289 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 2335 Mickleham Road, Mickleham |  |  |  |  | Labour | 2061.7037 | 0 | 0 | 0
Customer |  | Quadrant Building |  |  |  |  | Processing | 1005.2537 | 0 | 575 | 0
Start Date |  | 1 Mar 2025 |  |  |  |  | Rigging | 6000 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 200 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 684.9959 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 1.9571 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 1.8156 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1957.131 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 48.9283 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 3230.2818 | 0 | 0 | 0
[7 empty] | Total | 18999.9999 | 0 | 575 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2290
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Grow Constructions |  |  |  |  | Steel | 6607.909 | 0 | 0 | 0
Estimate Code |  | E00014487 |  |  |  |  | Bolts | 325.5784 | 0 | 0 | 0
Contract Code |  | J-2290 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 166 New Street, Brighton |  |  |  |  | Labour | 2383.4331 | 0 | 0 | 0
Customer |  | Grow Constructions |  |  |  |  | Processing | 2058.1298 | 0 | 0 | 0
Start Date |  | 23 Jan 2025 |  |  |  |  | Rigging | 5000 | 0 | 0 | 0
Completion Date |  | 3 Oct 2024 |  |  |  |  | Freight | 600 | 0 | 0 | 0
Budgeted Revenue |  | 23499.99 |  |  |  |  | Shop Drawings | 895.3406 | 0 | 0 | 0
Budgeted Job Expenditure |  | 17988.7638 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 23.45% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 2.5581 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 23.45% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 54.42 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 63.9529 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 5511.2362 | 0 | 0 | 0
[7 empty] | Total | 23500.0001 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 23500 | 23500 | 17988.7638 | 17988.7638 | 5511.2361 | 23.45% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 23500 | 0 | 17988.7638 | 5511.2361 | 23.45% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 23500 | 0 | 17988.7638 | 5511.2361 | 23.45% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 23500 | 0 | 17988.7638 | 5511.2361 | 23.45% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0%

## J-2291
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arcon Developments Pty Ltd |  |  |  |  | Steel | 36306.3821 | 0 | 0 | 0
Estimate Code |  | E00013684 |  |  |  |  | Bolts | 2202.3816 | 0 | 0 | 0
Contract Code |  | J-2291 |  |  |  |  | Purlin | 20019.9984 | 0 | 0 | 0
Contract Name |  | 1-11 Cherry Lane, Laverton North- Canopy Extension |  |  |  |  | Labour | 10930.2219 | 0 | 0 | 0
Customer |  | Arcon Developments Pty Ltd |  |  |  |  | Processing | 8687.8171 | 0 | 0 | 0
Start Date |  | 13 Jun 2024 |  |  |  |  | Rigging | 31999.4277 | 0 | 0 | 0
Completion Date |  | 19 Apr 2024 |  |  |  |  | Freight | 1499.9713 | 0 | 0 | 0
Budgeted Revenue |  | 169500.01 |  |  |  |  | Shop Drawings | 3603.7222 | 0 | 0 | 0
Budgeted Job Expenditure |  | 137771.6658 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 18.72% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 19.1856 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 18.72% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 20021.1197 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 1900 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 600.6235 | 0 | 0 | 0
[7 empty] | OH & Profit | 31728.3345 | 0 | 0 | 0
[7 empty] | Total | 169500.0001 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 169500 | 169500 | 137771.6658 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 169500 | 0 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 169500 | 0 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 169500 | 0 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 169500 | 0 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 169500 | 0 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 169500 | 0 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 169500 | 0 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 169500 | 0 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 169500 | 0 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 169500 | 0 | 137771.6658 | 31728.3342 | 18.72% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## J-2292
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | John Palazzolo |  |  |  |  | Steel | 6028.2052 | 0 | 0 | 0
Estimate Code |  | E00015203 |  |  |  |  | Bolts | 433.531 | 0 | 0 | 0
Contract Code |  | J-2292 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 3 Caroline Street Thomastown |  |  |  |  | Labour | 3584.1343 | 0 | 0 | 0
Customer |  | John Palazzolo |  |  |  |  | Processing | 1408.9757 | 0 | 0 | 0
Start Date |  | 1 Apr 2025 |  |  |  |  | Rigging | 4500 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 300 | 0 | 0 | 0
Budgeted Revenue |  | 23000 |  |  |  |  | Shop Drawings | 1192.2102 | 0 | 0 | 0
Budgeted Job Expenditure |  | 18493.416 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 19.59% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 3.4063 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 19.59% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 961.2 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 85.1579 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 4506.5857 | 0 | 0 | 0
[7 empty] | Total | 23000.0001 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 23000 | 23000 | 18493.416 | 18493.416 | 4506.584 | 19.59% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 23000 | 0 | 18493.416 | 4506.584 | 19.59% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-2293
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arch 10 Pty Ltd |  |  |  |  | Steel | 8398.3144 | 0 | 0 | 0
Estimate Code |  | E00012848 |  |  |  |  | Bolts | 435.218 | 0 | 0 | 0
Contract Code |  | J-2293 |  |  |  |  | Purlin | 226.2 | 0 | 0 | 0
Contract Name |  | 58 Whitehall Street, Footscray |  |  |  |  | Labour | 2755.323 | 0 | 0 | 0
Customer |  | Arch 10 Pty Ltd |  |  |  |  | Processing | 1756.4155 | 0 | 0 | 0
Start Date |  | 5 Oct 2023 |  |  |  |  | Rigging | 7000 | 0 | 0 | 0
Completion Date |  | 17 Aug 2023 |  |  |  |  | Freight | 400 | 0 | 0 | 0
Budgeted Revenue |  | 33999.99 |  |  |  |  | Shop Drawings | 1196.8495 | 0 | 0 | 0
Budgeted Job Expenditure |  | 25362.5087 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 25.4% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 3.5066 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 25.4% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 3108.7 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 85.4892 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 8637.4908 | 0 | 0 | 0
[7 empty] | Total | 34000.0004 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 34000 | 34000 | 25362.5087 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Oct 2023 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Nov 2023 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Dec 2023 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Jan 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Feb 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Mar 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Apr 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
May 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Jun 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Jul 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Aug 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Sep 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Oct 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Nov 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Dec 2024 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Jan 2025 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Feb 2025 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 34000 | 0 | 25362.5087 | 8637.4913 | 25.4% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Oct 2023 | 0 | 0 | 0 | 0
Nov 2023 | 0 | 0 | 0 | 0
Dec 2023 | 0 | 0 | 0 | 0
Jan 2024 | 0 | 0 | 0 | 0
Feb 2024 | 0 | 0 | 0 | 0
Mar 2024 | 0 | 0 | 0 | 0
Apr 2024 | 0 | 0 | 0 | 0
May 2024 | 0 | 0 | 0 | 0
Jun 2024 | 0 | 0 | 0 | 0
Jul 2024 | 0 | 0 | 0 | 0
Aug 2024 | 0 | 0 | 0 | 0
Sep 2024 | 0 | 0 | 0 | 0
Oct 2024 | 0 | 0 | 0 | 0
Nov 2024 | 0 | 0 | 0 | 0
Dec 2024 | 0 | 0 | 0 | 0
Jan 2025 | 0 | 0 | 0 | 0
Feb 2025 | 0 | 0 | 0 | 0
Mar 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Costruction Cost | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## J-2294
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arjay Modular |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00015220 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2294 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 3 Battery Enclosure |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Arjay Modular |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 20 Mar 2025 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-2295
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arjay Modular |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00015221 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2295 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Melbourne Airport |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Arjay Modular |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 20 Mar 2025 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-2296
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Arjay Modular |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00015222 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2296 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Zoo Project |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Arjay Modular |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 20 Mar 2025 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-2297
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Genis Steel (NSW) Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2297 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Moorebank Intermodal – WH S2 Signify Office Mezzan |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Genis Steel (NSW) Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 32.4872 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2021 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2022 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2023 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Apr 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
May 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jun 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jul 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Aug 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Sep 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Oct 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Nov 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Dec 2024 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Jan 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Feb 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 140463.23 | 140463.23 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2021 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2022 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2023 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Apr 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
May 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jun 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jul 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Aug 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Sep 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Oct 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Nov 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Dec 2024 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Jan 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Feb 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Mar 2025 | #DIV/0! | 140463.23 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Total
Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140463.23 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Revenue | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## J-2298
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | C3 Constructions Group |  |  |  |  | Steel | 41129.7815 | 0 | 0 | 0
Estimate Code |  | E00012852 |  |  |  |  | Bolts | 3995.3457 | 0 | 0 | 0
Contract Code |  | J-2298 |  |  |  |  | Purlin | 17129.2447 | 0 | 0 | 0
Contract Name |  | 561-569 GrieveParade, Brooklyn |  |  |  |  | Labour | 14941.4798 | 0 | 0 | 0
Customer |  | C3 Constructions Group |  |  |  |  | Processing | 9462.0432 | 0 | 0 | 0
Start Date |  | 6 Oct 2023 |  |  |  |  | Rigging | 29329.6055 | 0 | 0 | 0
Completion Date |  | 18 Aug 2023 |  |  |  |  | Freight | 1499.9841 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 3548.4048 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 10000 | 0 | 0 | 0
Estimated Weight |  | 23.6565 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 4719.86 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 3591.4127 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 615.0692 | 0 | 0 | 0
[7 empty] | OH & Profit | 25037.7701 | 0 | 0 | 0
[7 empty] | Total | 165000.0012 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2299
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Futura Homes |  |  |  |  | Steel | 11505.9151 | 0 | 0 | 0
Estimate Code |  | E00015069 |  |  |  |  | Bolts | 641.7236 | 0 | 0 | 0
Contract Code |  | J-2299 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 4 Stennis Street Pascoe Vale |  |  |  |  | Labour | 5252.5944 | 0 | 0 | 0
Customer |  | Futura Homes |  |  |  |  | Processing | 2589.8131 | 0 | 0 | 0
Start Date |  | 1 Apr 2025 |  |  |  |  | Rigging | 5500 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 600 | 0 | 0 | 0
Budgeted Revenue |  | 37000 |  |  |  |  | Shop Drawings | 1764.7399 | 0 | 0 | 0
Budgeted Job Expenditure |  | 29550.5911 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 20.13% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 5.0421 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 20.13% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 1569.75 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 126.0529 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 7449.411 | 0 | 0 | 0
[7 empty] | Total | 36999.9998 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 37000 | 37000 | 29550.5911 | 29550.5911 | 7449.4089 | 20.13% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 37000 | 0 | 29550.5911 | 7449.4089 | 20.13% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-2300
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | AusPro Steel |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00015230 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2300 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Lot 39, 13 Interchange Drive, Mickleham |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | AusPro Steel |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 21 Mar 2025 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 1560 |  |  |  |  | Shop Drawings | 1560 | 0 | 0 | 0
Budgeted Job Expenditure |  | 1560 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 0% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 0% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 1560 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 1560 | 1560 | 1560 | 1560 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 1560 | 0 | 1560 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%

## J-2301
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Leeda Projects Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E00015231 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2301 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Swanston Street Brunetti Oro - Screen Frames |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Leeda Projects Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date |  | 1 Apr 2025 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2302
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Protilt Constructions |  |  |  |  | Steel | 1071.3157 | 0 | 0 | 0
Estimate Code |  | E00015205 |  |  |  |  | Bolts | 60.8961 | 0 | 0 | 0
Contract Code |  | J-2302 |  |  |  |  | Purlin | 543.4002 | 0 | 0 | 0
Contract Name |  | 405-407 Hammond Road, Dandenong South |  |  |  |  | Labour | 832.5362 | 0 | 0 | 0
Customer |  | Protilt Constructions |  |  |  |  | Processing | 1754.3715 | 0 | 0 | 0
Start Date |  | 2 Jun 2025 |  |  |  |  | Rigging | 1830.148 | 0 | 0 | 0
Completion Date |  | 17 Mar 2025 |  |  |  |  | Freight | 519.1388 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 143.5407 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0.47847 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 11.9617 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 23.9234 | 0 | 0 | 0
[7 empty] | OH & Profit | 2186.3148 | 0 | 0 | 0
[7 empty] | Total | 8977.5471 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Mar 2025 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | #DIV/0! | 0 | #DIV/0! | #DIV/0!
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | #DIV/0! | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | #DIV/0! | 0
Total Costruction Cost | #VALUE! | #DIV/0! | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0! | #DIV/0!

## J-2303
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Genis Steel (NSW) Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code |  | E9991 |  |  |  |  | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2303 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | NSW McGrath Fit-out |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Genis Steel (NSW) Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date |  | 1 Mar 2021 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 31 Mar 2021 |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 100 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2304
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Corplex Pty Ltd |  |  |  |  | Steel | 0 | 0 | 0 | 0
Estimate Code | [6 empty] | Bolts | 0 | 0 | 0 | 0
Contract Code |  | J-2304 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | 10-15 Peet Street, Pakenham- Broadpro Pakenham |  |  |  |  | Labour | 0 | 0 | 0 | 0
Customer |  | Corplex Pty Ltd |  |  |  |  | Processing | 0 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | On-Going |  |  |  |  | Freight | 0 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 0 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2305
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | FDC Construction & Fitout (Vic) Pty Ltd |  |  |  |  | Steel | 435608.4195 | 0 | 0 | 0
Estimate Code |  | E00014509 |  |  |  |  | Bolts | 28412.2969 | 0 | 0 | 0
Contract Code |  | J-2305 |  |  |  |  | Purlin | 123799.4993 | 0 | 0 | 0
Contract Name |  | 6 Ferntree Place, Notting Hill- Olympus New Build |  |  |  |  | Labour | 185551.1392 | 0 | 0 | 0
Customer |  | FDC Construction & Fitout (Vic) Pty Ltd |  |  |  |  | Processing | 119426.9023 | 0 | 0 | 0
Start Date |  | 29 Jan 2025 |  |  |  |  | Rigging | 346000.6875 | 0 | 0 | 0
Completion Date |  | 8 Oct 2024 |  |  |  |  | Freight | 12600.0017 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 25829.3711 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 253.2167 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 53554.808 | 0 | 0 | 0
[7 empty] | Grates | 124500.1797 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 37900.2695 | 0 | 0 | 0
[7 empty] | Special Paint | 70000 | 0 | 0 | 0
[7 empty] | Quality Assurance | 2841.345 | 0 | 0 | 0
[7 empty] | OH & Profit | 377340.3325 | 0 | 0 | 0
[7 empty] | Total | 1943365.2523 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2306
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | FDC Construction & Fitout (Vic) Pty Ltd |  |  |  |  | Steel | 1193937.5448 | 0 | 0 | 0
Estimate Code |  | E00013359 |  |  |  |  | Bolts | 64699.6719 | 0 | 0 | 0
Contract Code |  | J-2306 |  |  |  |  | Purlin | 545819.4235 | 0 | 0 | 0
Contract Name |  | Lot 21-22 Melbourne Business Park- Makita |  |  |  |  | Labour | 469557.9414 | 0 | 0 | 0
Customer |  | FDC Construction & Fitout (Vic) Pty Ltd |  |  |  |  | Processing | 238380.7266 | 0 | 0 | 0
Start Date |  | 29 Mar 2024 |  |  |  |  | Rigging | 609226.2188 | 0 | 0 | 0
Completion Date |  | 7 Feb 2024 |  |  |  |  | Freight | 27330.459 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 45578.2383 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 576.3051 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 120044.5421 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 60413.8236 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 3834 | 0 | 0 | 0
[7 empty] | Other Materials | 68499.96 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 6759.4819 | 0 | 0 | 0
[7 empty] | OH & Profit | 782182.4688 | 0 | 0 | 0
[7 empty] | Total | 4236264.5006 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2307
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Cig Fab |  |  |  |  | Steel | 156800.0508 | 0 | 0 | 0
Estimate Code |  | E00014331 |  |  |  |  | Bolts | 6466.8501 | 0 | 0 | 0
Contract Code |  | J-2307 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Steel Truss Pedestrian Bridge- M80 Ring Road |  |  |  |  | Labour | 70668.4502 | 0 | 0 | 0
Customer |  | Cig Fab |  |  |  |  | Processing | 27715.0508 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 2 Sep 2024 |  |  |  |  | Freight | 150000 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 14697.4004 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 0 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 600 | 0 | 0 | 0
[7 empty] | Special Paint | 117650 | 0 | 0 | 0
[7 empty] | Quality Assurance | 8818.4297 | 0 | 0 | 0
[7 empty] | OH & Profit | 226583.77 | 0 | 0 | 0
[7 empty] | Total | 780000.0019 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2308
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Squared |  |  |  |  | Steel | 41242.3009 | 0 | 0 | 0
Estimate Code |  | E00014278 |  |  |  |  | Bolts | 5917.2778 | 0 | 0 | 0
Contract Code |  | J-2308 |  |  |  |  | Purlin | 0 | 0 | 0 | 0
Contract Name |  | Silk Street Pedestrian Bridge |  |  |  |  | Labour | 45394.6016 | 0 | 0 | 0
Customer |  | Squared |  |  |  |  | Processing | 13464.6418 | 0 | 0 | 0
Start Date |  | 7 Nov 2024 |  |  |  |  | Rigging | 0 | 0 | 0 | 0
Completion Date |  | 20 Aug 2024 |  |  |  |  | Freight | 12000 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 0 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 18.8667 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 4000 | 0 | 0 | 0
[7 empty] | Galvanizing | 0 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 3207.6671 | 0 | 0 | 0
[7 empty] | Special Paint | 54243.1992 | 0 | 0 | 0
[7 empty] | Quality Assurance | 9862.4004 | 0 | 0 | 0
[7 empty] | OH & Profit | 48367.9133 | 0 | 0 | 0
[7 empty] | Total | 237700.0021 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2309
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Squared |  |  |  |  | Steel | 42738.5673 | 0 | 0 | 0
Estimate Code |  | E00014456 |  |  |  |  | Bolts | 2904.2649 | 0 | 0 | 0
Contract Code |  | J-2309 |  |  |  |  | Purlin | 20015.4402 | 0 | 0 | 0
Contract Name |  | WTP Administration Building |  |  |  |  | Labour | 32403.2985 | 0 | 0 | 0
Customer |  | Squared |  |  |  |  | Processing | 11579.8223 | 0 | 0 | 0
Start Date | [6 empty] | Rigging | 46519.2227 | 0 | 0 | 0
Completion Date |  | 23 Sep 2024 |  |  |  |  | Freight | 3325.538 | 0 | 0 | 0
Budgeted Revenue |  | 0 |  |  |  |  | Shop Drawings | 6845.7676 | 0 | 0 | 0
Budgeted Job Expenditure |  | 0 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | #DIV/0! |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 22.8192 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | #DIV/0! |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 308.86 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 570.4806 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 1140.9613 | 0 | 0 | 0
[7 empty] | OH & Profit | 54109.6113 | 0 | 0 | 0
[7 empty] | Total | 222461.8347 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0!
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Job Profitability Summary
| Beginning | Total
Sales | 0 | #VALUE!
Less Current Period Overbills | 0 | #VALUE!
Plus Prior Period Overbills | 0
Total Revenue | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0
Construction Costs | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0
Total Costruction Cost | #VALUE! | #VALUE!
Gross Profit | #VALUE! | #VALUE!
% Completion | #DIV/0! | #DIV/0!

## J-2310
Job Report | [7 empty] | Estimated Budget | Variation $ | Actual $ | Adjusted $
Customer |  | Tony Gacovski |  |  |  |  | Steel | 26150.8795 | 0 | 0 | 0
Estimate Code |  | E00015024 |  |  |  |  | Bolts | 1512.5837 | 0 | 0 | 0
Contract Code |  | J-2310 |  |  |  |  | Purlin | 5581.5759 | 0 | 0 | 0
Contract Name |  | 491 Greenhalghs Road, Winter Valley |  |  |  |  | Labour | 12313.5586 | 0 | 0 | 0
Customer |  | Tony Gacovski |  |  |  |  | Processing | 6104.3562 | 0 | 0 | 0
Start Date |  | 16 Apr 2025 |  |  |  |  | Rigging | 22000 | 0 | 0 | 0
Completion Date |  | 7 Feb 2025 |  |  |  |  | Freight | 2500 | 0 | 0 | 0
Budgeted Revenue |  | 67700.33 |  |  |  |  | Shop Drawings | 5942.2935 | 0 | 0 | 0
Budgeted Job Expenditure |  | 59900.4114 |  |  |  |  | Panel Drawings | 0 | 0 | 0 | 0
Budgeted % |  | 11.52% |  |  |  |  | Box Frame | 0 | 0 | 0 | 0
Estimated Weight |  | 11.8846 |  |  |  |  | Light Weight Frame Delivery | 0 |  | 0
Actual Weight |  | 0 |  |  |  |  | Stairs | 0 | 0 | 0 | 0
Current GP% |  | 11.52% |  |  |  |  | Handrails | 0 | 0 | 0 | 0
[7 empty] | Galvanizing | 4469 | 0 | 0 | 0
[7 empty] | Grates | 0 | 0 | 0 | 0
[7 empty] | Grating | 0 | 0 | 0 | 0
[7 empty] | Bollards | 0 | 0 | 0 | 0
[7 empty] | Other Materials | 297.1147 | 0 | 0 | 0
[7 empty] | Special Paint | 0 | 0 | 0 | 0
[7 empty] | Quality Assurance | 0 | 0 | 0 | 0
[7 empty] | OH & Profit | 12128.6383 | 0 | 0 | 0
[7 empty] | Total | 99000.0004 | 0 | 0 | 0
Period | Budget Revenue |  | Budgeted Job Expenditure |  | Job Profitability | Job G.P. | Actual Revenue |  | Actual Cost |  | Completion %
Beginning | 67700.34 | 67700.34 | 59900.4114 | 59900.4114 | 7799.9286 | 11.52% | 0 | 0 | 0 | 0 | 0%
Mar 2025 | 0 | 67700.34 | 0 | 59900.4114 | 7799.9286 | 11.52% | 0 | 0 | 0 | 0 | 0%
Overbill / Underbill
Period | Should Have | Actually Did | Difference (GP Inc) | Difference (GP Exc)
Mar 2025 | 0 | 0 | 0 | 0
Job Profitability Summary
| Beginning | Mar 2025 | Total
Sales | 0 | 0 | #VALUE!
Less Current Period Overbills | 0 | 0 | #VALUE!
Plus Prior Period Overbills | 0 | 0
Total Revenue | #VALUE! | #VALUE! | #VALUE!
Less Construction Costs
Opening WIP | 0 | 0 | 0
Construction Costs | 0 | 0 | #VALUE!
Closing WIP | Difference (GP Exc) | 0 | 0
Total Costruction Cost | #VALUE! | 0 | #VALUE!
Gross Profit | #VALUE! | #VALUE! | #VALUE!
% Completion | 0 | 0% | 0%